## Dashboard
TECHNIJIAN — 180-DAY SEO CONTENT PLAN 2026
Mon-Thu: 1 Blog (persona rotation) + 1 Page/Person + SEO Tasks ¦ Friday: News + Page + SEO ¦ 8 Hrs/Day
WEEKLY CONTENT SCHEDULE
Day | Blog Writer | Others Do | All 4 Do | Pages/Day | SEO Plan Phase | News | Hrs/Person
Monday | Puneet (IT/HIPAA) | SEO tasks + backlinks | 1 Page each | 4 | Phase task | — | 8
Tuesday | Mohit (Software Dev) | SEO tasks + backlinks | 1 Page each | 4 | Phase task | — | 8
Wednesday | Saroj (SEO/Marketing) | SEO tasks + backlinks | 1 Page each | 4 | Phase task | — | 8
Thursday | Vaishali (AI Consulting) | SEO tasks + backlinks | 1 Page each | 4 | Phase task | — | 8
Friday | — (No blog) | SEO + weekly review | 1 Page each | 4 | Phase task | 1 News each | 8
DAILY 8-HOUR TIME BUDGET PER PERSON (Work Tasks Only)
Task | Blog Day |  | Non-Blog Day |  | Friday
Write Blog / News Article | 2.5 hrs |  | — |  | 1.5 hrs
Create/Update Landing Page | 2.0 hrs |  | 2.0 hrs |  | 2.0 hrs
180-Day SEO Plan Task | 1.5 hrs |  | 2.0 hrs |  | 1.5 hrs
Internal Links + Backlinks | 1.0 hrs |  | 2.0 hrs |  | 1.5 hrs
GBP + Social + Competitor Check | 0.5 hrs |  | 1.0 hrs |  | 0.5 hrs
Content Refresh (old posts) | 0.5 hrs |  | 1.0 hrs |  | 1.0 hrs
TOTAL | 8.0 hrs |  | 8.0 hrs |  | 8.0 hrs
26-WEEK OUTPUT |  |  | Per Person | Total (×4)
Blogs (1/persona Mon-Thu × 26) |  |  | 26 | 104
News Articles (1/person Friday × 26) |  |  | 26 | 104
Landing Pages (1/person/day × 130 days) |  |  | 130 | 520
180-Day SEO Tasks (daily per person) |  |  | 130 | 520
Case Study + Lead Magnet |  |  | 1 | 2
GRAND TOTAL |  |  | 313 | 1250
HOURS TRACKING
Daily/person |  |  | 8 hrs
Weekly/person |  |  | 40 hrs
Weekly all 4 |  |  | 160 hrs
26-Week/person |  |  | 1,040 hrs
26-Week total |  |  | 4,160 hrs
Team Member | Shift | Persona | Blogs | News | Pages | SEO Tasks | Hrs/Wk
Puneet Kumar | Eve 1PM-11PM | A–IT/HIPAA | 26 | 26 | 130 | 130 | 40
Mohit Pandey | Eve 1PM-11PM | B–Software | 26 | 26 | 130 | 130 | 40
Saroj Kumari | Morn 10:30-7:30 | C–SEO | 26 | 26 | 130 | 130 | 40
Vaishali Rathor | Morn 10:30-7:30 | D–AI | 26 | 26 | 130 | 130 | 40

## Daily Tickets
DAILY TICKET BOARD — WORK TASKS ONLY (8 Hrs/Day Per Person)
Morning: Saroj+Vaishali (10:30AM-7:30PM) ¦ Evening: Puneet+Mohit (1PM-11PM) ¦ Est vs Actual Hrs tracking
Week | Day | Person | Time | Task Type | Task Description | Est Hrs | Actual Hrs | Status
W1 | Monday | Saroj | 10:30 AM | AUDIT | SEMrush full site audit — technical errors + site health | 4.0 |  | Completed
W1 | Monday | Saroj | 2:30 PM | AUDIT | SEMrush keyword gap analysis — all 4 personas | 4.0 |  | Completed
W1 | Monday | Vaishali | 10:30 AM | AUDIT | SEMrush full site audit — technical errors + site health | 4.0 |  | Completed
W1 | Monday | Vaishali | 2:30 PM | AUDIT | SEMrush keyword gap analysis — all 4 personas | 4.0 |  | Completed
W1 | Monday | Puneet | 1:00 PM | AUDIT | SEMrush full site audit — technical errors + site health | 4.0 |  | Completed
W1 | Monday | Puneet | 5:00 PM | AUDIT | SEMrush keyword gap analysis — all 4 personas | 4.0 |  | Completed
W1 | Monday | Mohit | 1:00 PM | AUDIT | SEMrush full site audit — technical errors + site health | 4.0 |  | Completed
W1 | Monday | Mohit | 5:00 PM | AUDIT | SEMrush keyword gap analysis — all 4 personas | 4.0 |  | Completed
W1 | Tuesday | Saroj | 10:30 AM | AUDIT | Screaming Frog crawl — broken links, redirect chains, orphan pages | 4.0 |  | Completed
W1 | Tuesday | Saroj | 2:30 PM | AUDIT | Screaming Frog — duplicate titles, meta descriptions, H1 audit | 4.0 |  | Completed
W1 | Tuesday | Vaishali | 10:30 AM | AUDIT | Screaming Frog crawl — broken links, redirect chains, orphan pages | 4.0 |  | Completed
W1 | Tuesday | Vaishali | 2:30 PM | AUDIT | Screaming Frog — duplicate titles, meta descriptions, H1 audit | 4.0 |  | Completed
W1 | Tuesday | Puneet | 1:00 PM | AUDIT | Screaming Frog crawl — broken links, redirect chains, orphan pages | 4.0 |  | Completed
W1 | Tuesday | Puneet | 5:00 PM | AUDIT | Screaming Frog — duplicate titles, meta descriptions, H1 audit | 4.0 |  | Completed
W1 | Tuesday | Mohit | 1:00 PM | AUDIT | Screaming Frog crawl — broken links, redirect chains, orphan pages | 4.0 |  | Completed
W1 | Tuesday | Mohit | 5:00 PM | AUDIT | Screaming Frog — duplicate titles, meta descriptions, H1 audit | 4.0 |  | Completed
W1 | Wednesday | Saroj | 10:30 AM | AUDIT | GSC error review — index coverage, 404s, crawl errors | 4.0 |  | Completed
W1 | Wednesday | Saroj | 2:30 PM | AUDIT | GA4 + Core Web Vitals audit — LCP, FID, CLS across pages | 4.0 |  | Completed
W1 | Wednesday | Vaishali | 10:30 AM | AUDIT | GSC error review — index coverage, 404s, crawl errors | 4.0 |  | Completed
W1 | Wednesday | Vaishali | 2:30 PM | AUDIT | GA4 + Core Web Vitals audit — LCP, FID, CLS across pages | 4.0 |  | Completed
W1 | Wednesday | Puneet | 1:00 PM | AUDIT | GSC error review — index coverage, 404s, crawl errors | 4.0 |  | Completed
W1 | Wednesday | Puneet | 5:00 PM | AUDIT | GA4 + Core Web Vitals audit — LCP, FID, CLS across pages | 4.0 |  | Completed
W1 | Wednesday | Mohit | 1:00 PM | AUDIT | GSC error review — index coverage, 404s, crawl errors | 4.0 |  | Completed
W1 | Wednesday | Mohit | 5:00 PM | AUDIT | GA4 + Core Web Vitals audit — LCP, FID, CLS across pages | 4.0 |  | Completed
W1 | Thursday | Saroj | 10:30 AM | AUDIT | Competitor backlink analysis via SEMrush — top 3 competitors | 4.0 |  | Completed
W1 | Thursday | Saroj | 2:30 PM | AUDIT | Content gap report — missing topics vs competitors | 4.0 |  | Completed
W1 | Thursday | Vaishali | 10:30 AM | AUDIT | Competitor backlink analysis via SEMrush — top 3 competitors | 4.0 |  | Completed
W1 | Thursday | Vaishali | 2:30 PM | AUDIT | Content gap report — missing topics vs competitors | 4.0 |  | Completed
W1 | Thursday | Puneet | 1:00 PM | AUDIT | Competitor backlink analysis via SEMrush — top 3 competitors | 4.0 |  | Completed
W1 | Thursday | Puneet | 5:00 PM | AUDIT | Content gap report — missing topics vs competitors | 4.0 |  | Completed
W1 | Thursday | Mohit | 1:00 PM | AUDIT | Competitor backlink analysis via SEMrush — top 3 competitors | 4.0 |  | Completed
W1 | Thursday | Mohit | 5:00 PM | AUDIT | Content gap report — missing topics vs competitors | 4.0 |  | Completed
W2 | Monday | Saroj | 10:30 AM | PAGE | Page: SEO Services Costa Mesa | 2.0 |  | Not Started
W2 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Competitor content gap analysis | 2.0 |  | Not Started
W2 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W2 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W2 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W2 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W2 | Monday | Vaishali | 10:30 AM | PAGE | Page: AI Consulting Irvine | 2.0 |  | Not Started
W2 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Competitor content gap analysis | 2.0 |  | Not Started
W2 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W2 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W2 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W2 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W2 | Monday | Puneet | 1:00 PM | BLOG | Blog: 2026 HIPAA Compliance Checklist for OC | 2.5 |  | Not Started
W2 | Monday | Puneet | 3:30 PM | PAGE | Page: Managed IT Services Irvine | 2.0 |  | Not Started
W2 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Competitor content gap analysis | 1.5 |  | Not Started
W2 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W2 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W2 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W2 | Monday | Mohit | 1:00 PM | PAGE | Page: AI Software Development Irvine | 2.0 |  | Not Started
W2 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Competitor content gap analysis | 2.0 |  | Not Started
W2 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W2 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W2 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W2 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W2 | Tuesday | Saroj | 10:30 AM | PAGE | Page: Local SEO Anaheim | 2.0 |  | Not Started
W2 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Competitor content gap analysis | 2.0 |  | Not Started
W2 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W2 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W2 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W2 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W2 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: Copilot Implementation Downtown LA | 2.0 |  | Not Started
W2 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Competitor content gap analysis | 2.0 |  | Not Started
W2 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W2 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W2 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W2 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W2 | Tuesday | Puneet | 1:00 PM | PAGE | Page: HIPAA IT Support Newport Beach | 2.0 |  | Not Started
W2 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Competitor content gap analysis | 2.0 |  | Not Started
W2 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W2 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W2 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W2 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W2 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: AI-Native SDLC: Why Agile is Dead | 2.5 |  | Not Started
W2 | Tuesday | Mohit | 3:30 PM | PAGE | Page: Custom App Development Santa Monica | 2.0 |  | Not Started
W2 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Competitor content gap analysis | 1.5 |  | Not Started
W2 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W2 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W2 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W2 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: SEO Pricing OC 2026 | 2.5 |  | Not Started
W2 | Wednesday | Saroj | 12:30 PM | PAGE | Page: Technical SEO Long Beach | 2.0 |  | Not Started
W2 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Competitor content gap analysis | 1.5 |  | Not Started
W2 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W2 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W2 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W2 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: Gemini Integration Torrance | 2.0 |  | Not Started
W2 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Competitor content gap analysis | 2.0 |  | Not Started
W2 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W2 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W2 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W2 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W2 | Wednesday | Puneet | 1:00 PM | PAGE | Page: 24/7 IT Helpdesk Santa Ana | 2.0 |  | Not Started
W2 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Competitor content gap analysis | 2.0 |  | Not Started
W2 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W2 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W2 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W2 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W2 | Wednesday | Mohit | 1:00 PM | PAGE | Page: Enterprise Web Apps Culver City | 2.0 |  | Not Started
W2 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Competitor content gap analysis | 2.0 |  | Not Started
W2 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W2 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W2 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W2 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W2 | Thursday | Saroj | 10:30 AM | PAGE | Page: Answer Engine Optimization Tustin | 2.0 |  | Not Started
W2 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Competitor content gap analysis | 2.0 |  | Not Started
W2 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W2 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W2 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W2 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W2 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: Enterprise AI Guide 2026 | 2.5 |  | Not Started
W2 | Thursday | Vaishali | 12:30 PM | PAGE | Page: Enterprise AI Strategy Culver City | 2.0 |  | Not Started
W2 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Competitor content gap analysis | 1.5 |  | Not Started
W2 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W2 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W2 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W2 | Thursday | Puneet | 1:00 PM | PAGE | Page: Cybersecurity Services Anaheim | 2.0 |  | Not Started
W2 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Competitor content gap analysis | 2.0 |  | Not Started
W2 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W2 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W2 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W2 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W2 | Thursday | Mohit | 1:00 PM | PAGE | Page: .NET Development Downtown LA | 2.0 |  | Not Started
W2 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Competitor content gap analysis | 2.0 |  | Not Started
W2 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W2 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W2 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W2 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W2 | Friday | Saroj | 10:30 AM | NEWS | News: Google Core Update Local | 1.5 |  | Not Started
W2 | Friday | Saroj | 11:00 AM | PAGE | Page: Google Ads Management Culver City | 2.0 |  | Not Started
W2 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Competitor content gap analysis | 1.5 |  | Not Started
W2 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W2 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W2 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W2 | Friday | Vaishali | 10:30 AM | NEWS | News: Copilot 2026 Enterprise | 1.5 |  | Not Started
W2 | Friday | Vaishali | 11:00 AM | PAGE | Page: AI Security Consulting Santa Monica | 2.0 |  | Not Started
W2 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Competitor content gap analysis | 1.5 |  | Not Started
W2 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W2 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W2 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W2 | Friday | Puneet | 1:00 PM | NEWS | News: HIPAA Enforcement 2026 OC | 1.5 |  | Not Started
W2 | Friday | Puneet | 1:30 PM | PAGE | Page: Cloud Migration Costa Mesa | 2.0 |  | Not Started
W2 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Competitor content gap analysis | 1.5 |  | Not Started
W2 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W2 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W2 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W2 | Friday | Mohit | 1:00 PM | NEWS | News: CA AI Law Dev Impact | 1.5 |  | Not Started
W2 | Friday | Mohit | 1:30 PM | PAGE | Page: React Development Torrance | 2.0 |  | Not Started
W2 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Competitor content gap analysis | 1.5 |  | Not Started
W2 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W2 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W2 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W3 | Monday | Saroj | 10:30 AM | PAGE | Page: Content Marketing Irvine | 2.0 |  | Not Started
W3 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: AI-assisted content plan + topical authority mapping | 2.0 |  | Not Started
W3 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W3 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W3 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W3 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W3 | Monday | Vaishali | 10:30 AM | PAGE | Page: AI Automation Services Costa Mesa | 2.0 |  | Not Started
W3 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: AI-assisted content plan + topical authority mapping | 2.0 |  | Not Started
W3 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W3 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W3 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W3 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W3 | Monday | Puneet | 1:00 PM | BLOG | Blog: Why OC Businesses Need 24/7 IT Support | 2.5 |  | Not Started
W3 | Monday | Puneet | 3:30 PM | PAGE | Page: IT Disaster Recovery Long Beach | 2.0 |  | Not Started
W3 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: AI-assisted content plan + topical authority mapping | 1.5 |  | Not Started
W3 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W3 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W3 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W3 | Monday | Mohit | 1:00 PM | PAGE | Page: SaaS Development Costa Mesa | 2.0 |  | Not Started
W3 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: AI-assisted content plan + topical authority mapping | 2.0 |  | Not Started
W3 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W3 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W3 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W3 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W3 | Tuesday | Saroj | 10:30 AM | PAGE | Page: Link Building Newport Beach | 2.0 |  | Not Started
W3 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: AI-assisted content plan + topical authority mapping | 2.0 |  | Not Started
W3 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W3 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W3 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W3 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W3 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: Power BI AI Integration Anaheim | 2.0 |  | Not Started
W3 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: AI-assisted content plan + topical authority mapping | 2.0 |  | Not Started
W3 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W3 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W3 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W3 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W3 | Tuesday | Puneet | 1:00 PM | PAGE | Page: Network Monitoring Downtown LA | 2.0 |  | Not Started
W3 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: AI-assisted content plan + topical authority mapping | 2.0 |  | Not Started
W3 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W3 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W3 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W3 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W3 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: Build vs Buy: AI Agents 2026 | 2.5 |  | Not Started
W3 | Tuesday | Mohit | 3:30 PM | PAGE | Page: AI Agent Development Long Beach | 2.0 |  | Not Started
W3 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: AI-assisted content plan + topical authority mapping | 1.5 |  | Not Started
W3 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W3 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W3 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W3 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: SEO Guy Can't Rank You in ChatGPT | 2.5 |  | Not Started
W3 | Wednesday | Saroj | 12:30 PM | PAGE | Page: SEO Audit Santa Ana | 2.0 |  | Not Started
W3 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: AI-assisted content plan + topical authority mapping | 1.5 |  | Not Started
W3 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W3 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W3 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W3 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: AI Training Long Beach | 2.0 |  | Not Started
W3 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: AI-assisted content plan + topical authority mapping | 2.0 |  | Not Started
W3 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W3 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W3 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W3 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W3 | Wednesday | Puneet | 1:00 PM | PAGE | Page: Endpoint Security Torrance | 2.0 |  | Not Started
W3 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: AI-assisted content plan + topical authority mapping | 2.0 |  | Not Started
W3 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W3 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W3 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W3 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W3 | Wednesday | Mohit | 1:00 PM | PAGE | Page: CRM Development Anaheim | 2.0 |  | Not Started
W3 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: AI-assisted content plan + topical authority mapping | 2.0 |  | Not Started
W3 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W3 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W3 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W3 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W3 | Thursday | Saroj | 10:30 AM | PAGE | Page: E-Commerce SEO Downtown LA | 2.0 |  | Not Started
W3 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: AI-assisted content plan + topical authority mapping | 2.0 |  | Not Started
W3 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W3 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W3 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W3 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W3 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: Copilot vs Gemini vs ChatGPT | 2.5 |  | Not Started
W3 | Thursday | Vaishali | 12:30 PM | PAGE | Page: AI Penetration Testing Newport Beach | 2.0 |  | Not Started
W3 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: AI-assisted content plan + topical authority mapping | 1.5 |  | Not Started
W3 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W3 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W3 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W3 | Thursday | Puneet | 1:00 PM | PAGE | Page: Compliance IT Tustin | 2.0 |  | Not Started
W3 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: AI-assisted content plan + topical authority mapping | 2.0 |  | Not Started
W3 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W3 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W3 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W3 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W3 | Thursday | Mohit | 1:00 PM | PAGE | Page: Mobile App Dev Newport Beach | 2.0 |  | Not Started
W3 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: AI-assisted content plan + topical authority mapping | 2.0 |  | Not Started
W3 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W3 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W3 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W3 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W3 | Friday | Saroj | 10:30 AM | NEWS | News: ChatGPT Search Local | 1.5 |  | Not Started
W3 | Friday | Saroj | 11:00 AM | PAGE | Page: Schema Markup Services Torrance | 2.0 |  | Not Started
W3 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: AI-assisted content plan + topical authority mapping | 1.5 |  | Not Started
W3 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W3 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W3 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W3 | Friday | Vaishali | 10:30 AM | NEWS | News: Gemini Enterprise Impact | 1.5 |  | Not Started
W3 | Friday | Vaishali | 11:00 AM | PAGE | Page: AI Data Analytics Tustin | 2.0 |  | Not Started
W3 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: AI-assisted content plan + topical authority mapping | 1.5 |  | Not Started
W3 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W3 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W3 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W3 | Friday | Puneet | 1:00 PM | NEWS | News: Ransomware Hits SoCal Healthcare | 1.5 |  | Not Started
W3 | Friday | Puneet | 1:30 PM | PAGE | Page: IT Consulting Culver City | 2.0 |  | Not Started
W3 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: AI-assisted content plan + topical authority mapping | 1.5 |  | Not Started
W3 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W3 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W3 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W3 | Friday | Mohit | 1:00 PM | NEWS | News: React 19 Enterprise | 1.5 |  | Not Started
W3 | Friday | Mohit | 1:30 PM | PAGE | Page: API Development Tustin | 2.0 |  | Not Started
W3 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: AI-assisted content plan + topical authority mapping | 1.5 |  | Not Started
W3 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W3 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W3 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W4 | Monday | Saroj | 10:30 AM | PAGE | Page: Website Speed Optimization Santa Monica | 2.0 |  | Not Started
W4 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Technical SEO audit (crawl, index, Core Web Vitals) | 2.0 |  | Not Started
W4 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W4 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W4 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W4 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W4 | Monday | Vaishali | 10:30 AM | PAGE | Page: Digital Transformation Santa Ana | 2.0 |  | Not Started
W4 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Technical SEO audit (crawl, index, Core Web Vitals) | 2.0 |  | Not Started
W4 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W4 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W4 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W4 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W4 | Monday | Puneet | 1:00 PM | BLOG | Blog: Top 5 Ransomware Threats OC Healthcare 2026 | 2.5 |  | Not Started
W4 | Monday | Puneet | 3:30 PM | PAGE | Page: Server Management Santa Monica | 2.0 |  | Not Started
W4 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Technical SEO audit (crawl, index, Core Web Vitals) | 1.5 |  | Not Started
W4 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W4 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W4 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W4 | Monday | Mohit | 1:00 PM | PAGE | Page: Cloud App Development Santa Ana | 2.0 |  | Not Started
W4 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Technical SEO audit (crawl, index, Core Web Vitals) | 2.0 |  | Not Started
W4 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W4 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W4 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W4 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W4 | Tuesday | Saroj | 10:30 AM | PAGE | Page: Social Media Marketing Costa Mesa | 2.0 |  | Not Started
W4 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Technical SEO audit (crawl, index, Core Web Vitals) | 2.0 |  | Not Started
W4 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W4 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W4 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W4 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W4 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: AI Process Automation Irvine | 2.0 |  | Not Started
W4 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Technical SEO audit (crawl, index, Core Web Vitals) | 2.0 |  | Not Started
W4 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W4 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W4 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W4 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W4 | Tuesday | Puneet | 1:00 PM | PAGE | Page: Data Backup Solutions Irvine | 2.0 |  | Not Started
W4 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Technical SEO audit (crawl, index, Core Web Vitals) | 2.0 |  | Not Started
W4 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W4 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W4 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W4 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W4 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: .NET to .NET 8 Migration | 2.5 |  | Not Started
W4 | Tuesday | Mohit | 3:30 PM | PAGE | Page: DevOps Services Irvine | 2.0 |  | Not Started
W4 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Technical SEO audit (crawl, index, Core Web Vitals) | 1.5 |  | Not Started
W4 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W4 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W4 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W4 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: Google Ads vs SEO for OC | 2.5 |  | Not Started
W4 | Wednesday | Saroj | 12:30 PM | PAGE | Page: SEO Services Anaheim | 2.0 |  | Not Started
W4 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Technical SEO audit (crawl, index, Core Web Vitals) | 1.5 |  | Not Started
W4 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W4 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W4 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W4 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: AI Consulting Downtown LA | 2.0 |  | Not Started
W4 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Technical SEO audit (crawl, index, Core Web Vitals) | 2.0 |  | Not Started
W4 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W4 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W4 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W4 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W4 | Wednesday | Puneet | 1:00 PM | PAGE | Page: Managed IT Services Newport Beach | 2.0 |  | Not Started
W4 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Technical SEO audit (crawl, index, Core Web Vitals) | 2.0 |  | Not Started
W4 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W4 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W4 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W4 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W4 | Wednesday | Mohit | 1:00 PM | PAGE | Page: AI Software Development Santa Monica | 2.0 |  | Not Started
W4 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Technical SEO audit (crawl, index, Core Web Vitals) | 2.0 |  | Not Started
W4 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W4 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W4 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W4 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W4 | Thursday | Saroj | 10:30 AM | PAGE | Page: Local SEO Long Beach | 2.0 |  | Not Started
W4 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Technical SEO audit (crawl, index, Core Web Vitals) | 2.0 |  | Not Started
W4 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W4 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W4 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W4 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W4 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: Calculate ROI AI Projects | 2.5 |  | Not Started
W4 | Thursday | Vaishali | 12:30 PM | PAGE | Page: Copilot Implementation Torrance | 2.0 |  | Not Started
W4 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Technical SEO audit (crawl, index, Core Web Vitals) | 1.5 |  | Not Started
W4 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W4 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W4 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W4 | Thursday | Puneet | 1:00 PM | PAGE | Page: HIPAA IT Support Santa Ana | 2.0 |  | Not Started
W4 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Technical SEO audit (crawl, index, Core Web Vitals) | 2.0 |  | Not Started
W4 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W4 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W4 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W4 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W4 | Thursday | Mohit | 1:00 PM | PAGE | Page: Custom App Development Culver City | 2.0 |  | Not Started
W4 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Technical SEO audit (crawl, index, Core Web Vitals) | 2.0 |  | Not Started
W4 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W4 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W4 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W4 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W4 | Friday | Saroj | 10:30 AM | NEWS | News: GBP 2026 Features | 1.5 |  | Not Started
W4 | Friday | Saroj | 11:00 AM | PAGE | Page: Technical SEO Tustin | 2.0 |  | Not Started
W4 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Technical SEO audit (crawl, index, Core Web Vitals) | 1.5 |  | Not Started
W4 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W4 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W4 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W4 | Friday | Vaishali | 10:30 AM | NEWS | News: AI Regulation CA | 1.5 |  | Not Started
W4 | Friday | Vaishali | 11:00 AM | PAGE | Page: Gemini Integration Culver City | 2.0 |  | Not Started
W4 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Technical SEO audit (crawl, index, Core Web Vitals) | 1.5 |  | Not Started
W4 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W4 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W4 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W4 | Friday | Puneet | 1:00 PM | NEWS | News: OC Data Breach Lessons | 1.5 |  | Not Started
W4 | Friday | Puneet | 1:30 PM | PAGE | Page: 24/7 IT Helpdesk Anaheim | 2.0 |  | Not Started
W4 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Technical SEO audit (crawl, index, Core Web Vitals) | 1.5 |  | Not Started
W4 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W4 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W4 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W4 | Friday | Mohit | 1:00 PM | NEWS | News: .NET 9 Preview | 1.5 |  | Not Started
W4 | Friday | Mohit | 1:30 PM | PAGE | Page: Enterprise Web Apps Downtown LA | 2.0 |  | Not Started
W4 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Technical SEO audit (crawl, index, Core Web Vitals) | 1.5 |  | Not Started
W4 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W4 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W4 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W5 | Monday | Saroj | 10:30 AM | PAGE | Page: Answer Engine Optimization Culver City | 2.0 |  | Not Started
W5 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Site structure + internal linking plan | 2.0 |  | Not Started
W5 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W5 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W5 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W5 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W5 | Monday | Vaishali | 10:30 AM | PAGE | Page: Enterprise AI Strategy Santa Monica | 2.0 |  | Not Started
W5 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Site structure + internal linking plan | 2.0 |  | Not Started
W5 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W5 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W5 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W5 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W5 | Monday | Puneet | 1:00 PM | BLOG | Blog: FINRA IT Checklist Newport Beach | 2.5 |  | Not Started
W5 | Monday | Puneet | 3:30 PM | PAGE | Page: Cybersecurity Services Costa Mesa | 2.0 |  | Not Started
W5 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Site structure + internal linking plan | 1.5 |  | Not Started
W5 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W5 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W5 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W5 | Monday | Mohit | 1:00 PM | PAGE | Page: .NET Development Torrance | 2.0 |  | Not Started
W5 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Site structure + internal linking plan | 2.0 |  | Not Started
W5 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W5 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W5 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W5 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W5 | Tuesday | Saroj | 10:30 AM | PAGE | Page: Google Ads Management Irvine | 2.0 |  | Not Started
W5 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Site structure + internal linking plan | 2.0 |  | Not Started
W5 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W5 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W5 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W5 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W5 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: AI Security Consulting Costa Mesa | 2.0 |  | Not Started
W5 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Site structure + internal linking plan | 2.0 |  | Not Started
W5 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W5 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W5 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W5 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W5 | Tuesday | Puneet | 1:00 PM | PAGE | Page: Cloud Migration Long Beach | 2.0 |  | Not Started
W5 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Site structure + internal linking plan | 2.0 |  | Not Started
W5 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W5 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W5 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W5 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W5 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: React 18 vs Blazor Enterprise | 2.5 |  | Not Started
W5 | Tuesday | Mohit | 3:30 PM | PAGE | Page: React Development Costa Mesa | 2.0 |  | Not Started
W5 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Site structure + internal linking plan | 1.5 |  | Not Started
W5 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W5 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W5 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W5 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: AI Search Kills Traffic Fix It | 2.5 |  | Not Started
W5 | Wednesday | Saroj | 12:30 PM | PAGE | Page: Content Marketing Newport Beach | 2.0 |  | Not Started
W5 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Site structure + internal linking plan | 1.5 |  | Not Started
W5 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W5 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W5 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W5 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: AI Automation Services Anaheim | 2.0 |  | Not Started
W5 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Site structure + internal linking plan | 2.0 |  | Not Started
W5 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W5 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W5 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W5 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W5 | Wednesday | Puneet | 1:00 PM | PAGE | Page: IT Disaster Recovery Downtown LA | 2.0 |  | Not Started
W5 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Site structure + internal linking plan | 2.0 |  | Not Started
W5 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W5 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W5 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W5 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W5 | Wednesday | Mohit | 1:00 PM | PAGE | Page: SaaS Development Long Beach | 2.0 |  | Not Started
W5 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Site structure + internal linking plan | 2.0 |  | Not Started
W5 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W5 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W5 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W5 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W5 | Thursday | Saroj | 10:30 AM | PAGE | Page: Link Building Santa Ana | 2.0 |  | Not Started
W5 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Site structure + internal linking plan | 2.0 |  | Not Started
W5 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W5 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W5 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W5 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W5 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: AI Security & Compliance | 2.5 |  | Not Started
W5 | Thursday | Vaishali | 12:30 PM | PAGE | Page: Power BI AI Integration Long Beach | 2.0 |  | Not Started
W5 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Site structure + internal linking plan | 1.5 |  | Not Started
W5 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W5 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W5 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W5 | Thursday | Puneet | 1:00 PM | PAGE | Page: Network Monitoring Torrance | 2.0 |  | Not Started
W5 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Site structure + internal linking plan | 2.0 |  | Not Started
W5 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W5 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W5 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W5 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W5 | Thursday | Mohit | 1:00 PM | PAGE | Page: AI Agent Development Anaheim | 2.0 |  | Not Started
W5 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Site structure + internal linking plan | 2.0 |  | Not Started
W5 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W5 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W5 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W5 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W5 | Friday | Saroj | 10:30 AM | NEWS | News: Perplexity Business Listings | 1.5 |  | Not Started
W5 | Friday | Saroj | 11:00 AM | PAGE | Page: SEO Audit Downtown LA | 2.0 |  | Not Started
W5 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Site structure + internal linking plan | 1.5 |  | Not Started
W5 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W5 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W5 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W5 | Friday | Vaishali | 10:30 AM | NEWS | News: Enterprise AI SoCal | 1.5 |  | Not Started
W5 | Friday | Vaishali | 11:00 AM | PAGE | Page: AI Training Newport Beach | 2.0 |  | Not Started
W5 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Site structure + internal linking plan | 1.5 |  | Not Started
W5 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W5 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W5 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W5 | Friday | Puneet | 1:00 PM | NEWS | News: Cyber Insurance Tightens OC | 1.5 |  | Not Started
W5 | Friday | Puneet | 1:30 PM | PAGE | Page: Endpoint Security Tustin | 2.0 |  | Not Started
W5 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Site structure + internal linking plan | 1.5 |  | Not Started
W5 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W5 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W5 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W5 | Friday | Mohit | 1:00 PM | NEWS | News: AI Low-Code Opportunity | 1.5 |  | Not Started
W5 | Friday | Mohit | 1:30 PM | PAGE | Page: CRM Development Newport Beach | 2.0 |  | Not Started
W5 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Site structure + internal linking plan | 1.5 |  | Not Started
W5 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W5 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W5 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W6 | Monday | Saroj | 10:30 AM | PAGE | Page: E-Commerce SEO Torrance | 2.0 |  | Not Started
W6 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W6 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W6 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W6 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W6 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W6 | Monday | Vaishali | 10:30 AM | PAGE | Page: AI Penetration Testing Tustin | 2.0 |  | Not Started
W6 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W6 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W6 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W6 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W6 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W6 | Monday | Puneet | 1:00 PM | BLOG | Blog: Cost of HIPAA Non-Compliance CA | 2.5 |  | Not Started
W6 | Monday | Puneet | 3:30 PM | PAGE | Page: Compliance IT Culver City | 2.0 |  | Not Started
W6 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 1.5 |  | Not Started
W6 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W6 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W6 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W6 | Monday | Mohit | 1:00 PM | PAGE | Page: Mobile App Dev Tustin | 2.0 |  | Not Started
W6 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W6 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W6 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W6 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W6 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W6 | Tuesday | Saroj | 10:30 AM | PAGE | Page: Schema Markup Services Santa Monica | 2.0 |  | Not Started
W6 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W6 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W6 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W6 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W6 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W6 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: AI Data Analytics Santa Ana | 2.0 |  | Not Started
W6 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W6 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W6 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W6 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W6 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W6 | Tuesday | Puneet | 1:00 PM | PAGE | Page: IT Consulting Santa Monica | 2.0 |  | Not Started
W6 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W6 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W6 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W6 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W6 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W6 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: Contract-First Dev Explained | 2.5 |  | Not Started
W6 | Tuesday | Mohit | 3:30 PM | PAGE | Page: API Development Santa Ana | 2.0 |  | Not Started
W6 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 1.5 |  | Not Started
W6 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W6 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W6 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W6 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: Local SEO Checklist OC 2026 | 2.5 |  | Not Started
W6 | Wednesday | Saroj | 12:30 PM | PAGE | Page: Website Speed Optimization Costa Mesa | 2.0 |  | Not Started
W6 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 1.5 |  | Not Started
W6 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W6 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W6 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W6 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: Digital Transformation Irvine | 2.0 |  | Not Started
W6 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W6 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W6 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W6 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W6 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W6 | Wednesday | Puneet | 1:00 PM | PAGE | Page: Server Management Irvine | 2.0 |  | Not Started
W6 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W6 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W6 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W6 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W6 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W6 | Wednesday | Mohit | 1:00 PM | PAGE | Page: Cloud App Development Irvine | 2.0 |  | Not Started
W6 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W6 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W6 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W6 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W6 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W6 | Thursday | Saroj | 10:30 AM | PAGE | Page: Social Media Marketing Anaheim | 2.0 |  | Not Started
W6 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W6 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W6 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W6 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W6 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W6 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: HackGPT AI Pen Testing | 2.5 |  | Not Started
W6 | Thursday | Vaishali | 12:30 PM | PAGE | Page: AI Process Automation Downtown LA | 2.0 |  | Not Started
W6 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 1.5 |  | Not Started
W6 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W6 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W6 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W6 | Thursday | Puneet | 1:00 PM | PAGE | Page: Data Backup Solutions Newport Beach | 2.0 |  | Not Started
W6 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W6 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W6 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W6 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W6 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W6 | Thursday | Mohit | 1:00 PM | PAGE | Page: DevOps Services Santa Monica | 2.0 |  | Not Started
W6 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W6 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W6 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W6 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W6 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W6 | Friday | Saroj | 10:30 AM | NEWS | News: AI Overviews CTR Impact | 1.5 |  | Not Started
W6 | Friday | Saroj | 11:00 AM | PAGE | Page: SEO Services Long Beach | 2.0 |  | Not Started
W6 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 1.5 |  | Not Started
W6 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W6 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W6 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W6 | Friday | Vaishali | 10:30 AM | NEWS | News: OpenAI vs Copilot | 1.5 |  | Not Started
W6 | Friday | Vaishali | 11:00 AM | PAGE | Page: AI Consulting Torrance | 2.0 |  | Not Started
W6 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 1.5 |  | Not Started
W6 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W6 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W6 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W6 | Friday | Puneet | 1:00 PM | NEWS | News: CMMC 2.0 OC Deadline | 1.5 |  | Not Started
W6 | Friday | Puneet | 1:30 PM | PAGE | Page: Managed IT Services Santa Ana | 2.0 |  | Not Started
W6 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 1.5 |  | Not Started
W6 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W6 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W6 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W6 | Friday | Mohit | 1:00 PM | NEWS | News: SoCal Startup Funding | 1.5 |  | Not Started
W6 | Friday | Mohit | 1:30 PM | PAGE | Page: AI Software Development Culver City | 2.0 |  | Not Started
W6 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 1.5 |  | Not Started
W6 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W6 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W6 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W7 | Monday | Saroj | 10:30 AM | PAGE | Page: Local SEO Tustin | 2.0 |  | Not Started
W7 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W7 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W7 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W7 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W7 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W7 | Monday | Vaishali | 10:30 AM | PAGE | Page: Copilot Implementation Culver City | 2.0 |  | Not Started
W7 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W7 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W7 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W7 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W7 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W7 | Monday | Puneet | 1:00 PM | BLOG | Blog: Choose HIPAA-Compliant IT in OC | 2.5 |  | Not Started
W7 | Monday | Puneet | 3:30 PM | PAGE | Page: HIPAA IT Support Anaheim | 2.0 |  | Not Started
W7 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 1.5 |  | Not Started
W7 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W7 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W7 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W7 | Monday | Mohit | 1:00 PM | PAGE | Page: Custom App Development Downtown LA | 2.0 |  | Not Started
W7 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W7 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W7 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W7 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W7 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W7 | Tuesday | Saroj | 10:30 AM | PAGE | Page: Technical SEO Culver City | 2.0 |  | Not Started
W7 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W7 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W7 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W7 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W7 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W7 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: Gemini Integration Santa Monica | 2.0 |  | Not Started
W7 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W7 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W7 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W7 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W7 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W7 | Tuesday | Puneet | 1:00 PM | PAGE | Page: 24/7 IT Helpdesk Costa Mesa | 2.0 |  | Not Started
W7 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W7 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W7 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W7 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W7 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W7 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: Enterprise Software 6 Weeks AI | 2.5 |  | Not Started
W7 | Tuesday | Mohit | 3:30 PM | PAGE | Page: Enterprise Web Apps Torrance | 2.0 |  | Not Started
W7 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 1.5 |  | Not Started
W7 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W7 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W7 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W7 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: Google Reviews Without Begging | 2.5 |  | Not Started
W7 | Wednesday | Saroj | 12:30 PM | PAGE | Page: Answer Engine Optimization Irvine | 2.0 |  | Not Started
W7 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 1.5 |  | Not Started
W7 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W7 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W7 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W7 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: Enterprise AI Strategy Costa Mesa | 2.0 |  | Not Started
W7 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W7 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W7 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W7 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W7 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W7 | Wednesday | Puneet | 1:00 PM | PAGE | Page: Cybersecurity Services Long Beach | 2.0 |  | Not Started
W7 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W7 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W7 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W7 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W7 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W7 | Wednesday | Mohit | 1:00 PM | PAGE | Page: .NET Development Costa Mesa | 2.0 |  | Not Started
W7 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W7 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W7 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W7 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W7 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W7 | Thursday | Saroj | 10:30 AM | PAGE | Page: Google Ads Management Newport Beach | 2.0 |  | Not Started
W7 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W7 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W7 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W7 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W7 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W7 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: AI Strategy Roadmap Enterprise | 2.5 |  | Not Started
W7 | Thursday | Vaishali | 12:30 PM | PAGE | Page: AI Security Consulting Anaheim | 2.0 |  | Not Started
W7 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 1.5 |  | Not Started
W7 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W7 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W7 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W7 | Thursday | Puneet | 1:00 PM | PAGE | Page: Cloud Migration Downtown LA | 2.0 |  | Not Started
W7 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W7 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W7 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W7 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W7 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W7 | Thursday | Mohit | 1:00 PM | PAGE | Page: React Development Long Beach | 2.0 |  | Not Started
W7 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 2.0 |  | Not Started
W7 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W7 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W7 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W7 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W7 | Friday | Saroj | 10:30 AM | NEWS | News: Voice Search Local | 1.5 |  | Not Started
W7 | Friday | Saroj | 11:00 AM | PAGE | Page: Content Marketing Santa Ana | 2.0 |  | Not Started
W7 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 1.5 |  | Not Started
W7 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W7 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W7 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W7 | Friday | Vaishali | 10:30 AM | NEWS | News: AI Healthcare OC | 1.5 |  | Not Started
W7 | Friday | Vaishali | 11:00 AM | PAGE | Page: AI Automation Services Long Beach | 2.0 |  | Not Started
W7 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 1.5 |  | Not Started
W7 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W7 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W7 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W7 | Friday | Puneet | 1:00 PM | NEWS | News: CPRA Enforcement OC | 1.5 |  | Not Started
W7 | Friday | Puneet | 1:30 PM | PAGE | Page: IT Disaster Recovery Torrance | 2.0 |  | Not Started
W7 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 1.5 |  | Not Started
W7 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W7 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W7 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W7 | Friday | Mohit | 1:00 PM | NEWS | News: Azure AI 2026 | 1.5 |  | Not Started
W7 | Friday | Mohit | 1:30 PM | PAGE | Page: SaaS Development Anaheim | 2.0 |  | Not Started
W7 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Publish high-quality pillar content | 1.5 |  | Not Started
W7 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W7 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W7 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W8 | Monday | Saroj | 10:30 AM | PAGE | Page: Link Building Downtown LA | 2.0 |  | Not Started
W8 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: On-page SEO (titles, headings, entities, FAQs) | 2.0 |  | Not Started
W8 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W8 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W8 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W8 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W8 | Monday | Vaishali | 10:30 AM | PAGE | Page: Power BI AI Integration Newport Beach | 2.0 |  | Not Started
W8 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: On-page SEO (titles, headings, entities, FAQs) | 2.0 |  | Not Started
W8 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W8 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W8 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W8 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W8 | Monday | Puneet | 1:00 PM | BLOG | Blog: Managed IT vs Break-Fix for OC | 2.5 |  | Not Started
W8 | Monday | Puneet | 3:30 PM | PAGE | Page: Network Monitoring Tustin | 2.0 |  | Not Started
W8 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: On-page SEO (titles, headings, entities, FAQs) | 1.5 |  | Not Started
W8 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W8 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W8 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W8 | Monday | Mohit | 1:00 PM | PAGE | Page: AI Agent Development Newport Beach | 2.0 |  | Not Started
W8 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: On-page SEO (titles, headings, entities, FAQs) | 2.0 |  | Not Started
W8 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W8 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W8 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W8 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W8 | Tuesday | Saroj | 10:30 AM | PAGE | Page: SEO Audit Torrance | 2.0 |  | Not Started
W8 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: On-page SEO (titles, headings, entities, FAQs) | 2.0 |  | Not Started
W8 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W8 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W8 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W8 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W8 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: AI Training Tustin | 2.0 |  | Not Started
W8 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: On-page SEO (titles, headings, entities, FAQs) | 2.0 |  | Not Started
W8 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W8 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W8 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W8 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W8 | Tuesday | Puneet | 1:00 PM | PAGE | Page: Endpoint Security Culver City | 2.0 |  | Not Started
W8 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: On-page SEO (titles, headings, entities, FAQs) | 2.0 |  | Not Started
W8 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W8 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W8 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W8 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W8 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: MVP Timeline 2026 | 2.5 |  | Not Started
W8 | Tuesday | Mohit | 3:30 PM | PAGE | Page: CRM Development Tustin | 2.0 |  | Not Started
W8 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: On-page SEO (titles, headings, entities, FAQs) | 1.5 |  | Not Started
W8 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W8 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W8 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W8 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: Website Not Ranking Code Issue | 2.5 |  | Not Started
W8 | Wednesday | Saroj | 12:30 PM | PAGE | Page: E-Commerce SEO Santa Monica | 2.0 |  | Not Started
W8 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: On-page SEO (titles, headings, entities, FAQs) | 1.5 |  | Not Started
W8 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W8 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W8 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W8 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: AI Penetration Testing Santa Ana | 2.0 |  | Not Started
W8 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: On-page SEO (titles, headings, entities, FAQs) | 2.0 |  | Not Started
W8 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W8 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W8 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W8 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W8 | Wednesday | Puneet | 1:00 PM | PAGE | Page: Compliance IT Santa Monica | 2.0 |  | Not Started
W8 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: On-page SEO (titles, headings, entities, FAQs) | 2.0 |  | Not Started
W8 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W8 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W8 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W8 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W8 | Wednesday | Mohit | 1:00 PM | PAGE | Page: Mobile App Dev Santa Ana | 2.0 |  | Not Started
W8 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: On-page SEO (titles, headings, entities, FAQs) | 2.0 |  | Not Started
W8 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W8 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W8 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W8 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W8 | Thursday | Saroj | 10:30 AM | PAGE | Page: Schema Markup Services Costa Mesa | 2.0 |  | Not Started
W8 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: On-page SEO (titles, headings, entities, FAQs) | 2.0 |  | Not Started
W8 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W8 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W8 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W8 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W8 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: Copilot M365 Setup OC | 2.5 |  | Not Started
W8 | Thursday | Vaishali | 12:30 PM | PAGE | Page: AI Data Analytics Irvine | 2.0 |  | Not Started
W8 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: On-page SEO (titles, headings, entities, FAQs) | 1.5 |  | Not Started
W8 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W8 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W8 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W8 | Thursday | Puneet | 1:00 PM | PAGE | Page: IT Consulting Irvine | 2.0 |  | Not Started
W8 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: On-page SEO (titles, headings, entities, FAQs) | 2.0 |  | Not Started
W8 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W8 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W8 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W8 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W8 | Thursday | Mohit | 1:00 PM | PAGE | Page: API Development Irvine | 2.0 |  | Not Started
W8 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: On-page SEO (titles, headings, entities, FAQs) | 2.0 |  | Not Started
W8 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W8 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W8 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W8 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W8 | Friday | Saroj | 10:30 AM | NEWS | News: Google Ads OC Update | 1.5 |  | Not Started
W8 | Friday | Saroj | 11:00 AM | PAGE | Page: Website Speed Optimization Anaheim | 2.0 |  | Not Started
W8 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: On-page SEO (titles, headings, entities, FAQs) | 1.5 |  | Not Started
W8 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W8 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W8 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W8 | Friday | Vaishali | 10:30 AM | NEWS | News: Claude Enterprise | 1.5 |  | Not Started
W8 | Friday | Vaishali | 11:00 AM | PAGE | Page: Digital Transformation Downtown LA | 2.0 |  | Not Started
W8 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: On-page SEO (titles, headings, entities, FAQs) | 1.5 |  | Not Started
W8 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W8 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W8 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W8 | Friday | Puneet | 1:00 PM | NEWS | News: Mid-Year Cyber Threats OC | 1.5 |  | Not Started
W8 | Friday | Puneet | 1:30 PM | PAGE | Page: Server Management Newport Beach | 2.0 |  | Not Started
W8 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: On-page SEO (titles, headings, entities, FAQs) | 1.5 |  | Not Started
W8 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W8 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W8 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W8 | Friday | Mohit | 1:00 PM | NEWS | News: SaaS H2 2026 SoCal | 1.5 |  | Not Started
W8 | Friday | Mohit | 1:30 PM | PAGE | Page: Cloud App Development Santa Monica | 2.0 |  | Not Started
W8 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: On-page SEO (titles, headings, entities, FAQs) | 1.5 |  | Not Started
W8 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W8 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W8 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W9 | Monday | Saroj | 10:30 AM | PAGE | Page: Social Media Marketing Long Beach | 2.0 |  | Not Started
W9 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Schema markup (Article, FAQ, Organization) | 2.0 |  | Not Started
W9 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W9 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W9 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W9 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W9 | Monday | Vaishali | 10:30 AM | PAGE | Page: AI Process Automation Torrance | 2.0 |  | Not Started
W9 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Schema markup (Article, FAQ, Organization) | 2.0 |  | Not Started
W9 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W9 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W9 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W9 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W9 | Monday | Puneet | 1:00 PM | BLOG | Blog: Cybersecurity for Irvine Medical Offices | 2.5 |  | Not Started
W9 | Monday | Puneet | 3:30 PM | PAGE | Page: Data Backup Solutions Santa Ana | 2.0 |  | Not Started
W9 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Schema markup (Article, FAQ, Organization) | 1.5 |  | Not Started
W9 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W9 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W9 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W9 | Monday | Mohit | 1:00 PM | PAGE | Page: DevOps Services Culver City | 2.0 |  | Not Started
W9 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Schema markup (Article, FAQ, Organization) | 2.0 |  | Not Started
W9 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W9 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W9 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W9 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W9 | Tuesday | Saroj | 10:30 AM | PAGE | Page: SEO Services Tustin | 2.0 |  | Not Started
W9 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Schema markup (Article, FAQ, Organization) | 2.0 |  | Not Started
W9 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W9 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W9 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W9 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W9 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: AI Consulting Culver City | 2.0 |  | Not Started
W9 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Schema markup (Article, FAQ, Organization) | 2.0 |  | Not Started
W9 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W9 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W9 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W9 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W9 | Tuesday | Puneet | 1:00 PM | PAGE | Page: Managed IT Services Anaheim | 2.0 |  | Not Started
W9 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Schema markup (Article, FAQ, Organization) | 2.0 |  | Not Started
W9 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W9 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W9 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W9 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W9 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: Santa Monica Hybrid Dev Teams | 2.5 |  | Not Started
W9 | Tuesday | Mohit | 3:30 PM | PAGE | Page: AI Software Development Downtown LA | 2.0 |  | Not Started
W9 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Schema markup (Article, FAQ, Organization) | 1.5 |  | Not Started
W9 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W9 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W9 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W9 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: AEO Complete Guide 2026 | 2.5 |  | Not Started
W9 | Wednesday | Saroj | 12:30 PM | PAGE | Page: Local SEO Culver City | 2.0 |  | Not Started
W9 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Schema markup (Article, FAQ, Organization) | 1.5 |  | Not Started
W9 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W9 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W9 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W9 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: Copilot Implementation Santa Monica | 2.0 |  | Not Started
W9 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Schema markup (Article, FAQ, Organization) | 2.0 |  | Not Started
W9 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W9 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W9 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W9 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W9 | Wednesday | Puneet | 1:00 PM | PAGE | Page: HIPAA IT Support Costa Mesa | 2.0 |  | Not Started
W9 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Schema markup (Article, FAQ, Organization) | 2.0 |  | Not Started
W9 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W9 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W9 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W9 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W9 | Wednesday | Mohit | 1:00 PM | PAGE | Page: Custom App Development Torrance | 2.0 |  | Not Started
W9 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Schema markup (Article, FAQ, Organization) | 2.0 |  | Not Started
W9 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W9 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W9 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W9 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W9 | Thursday | Saroj | 10:30 AM | PAGE | Page: Technical SEO Irvine | 2.0 |  | Not Started
W9 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Schema markup (Article, FAQ, Organization) | 2.0 |  | Not Started
W9 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W9 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W9 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W9 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W9 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: AI Privacy GenAI No Leaks | 2.5 |  | Not Started
W9 | Thursday | Vaishali | 12:30 PM | PAGE | Page: Gemini Integration Costa Mesa | 2.0 |  | Not Started
W9 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Schema markup (Article, FAQ, Organization) | 1.5 |  | Not Started
W9 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W9 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W9 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W9 | Thursday | Puneet | 1:00 PM | PAGE | Page: 24/7 IT Helpdesk Long Beach | 2.0 |  | Not Started
W9 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Schema markup (Article, FAQ, Organization) | 2.0 |  | Not Started
W9 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W9 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W9 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W9 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W9 | Thursday | Mohit | 1:00 PM | PAGE | Page: Enterprise Web Apps Costa Mesa | 2.0 |  | Not Started
W9 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Schema markup (Article, FAQ, Organization) | 2.0 |  | Not Started
W9 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W9 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W9 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W9 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W9 | Friday | Saroj | 10:30 AM | NEWS | News: Yelp OC Restaurant SEO | 1.5 |  | Not Started
W9 | Friday | Saroj | 11:00 AM | PAGE | Page: Answer Engine Optimization Newport Beach | 2.0 |  | Not Started
W9 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Schema markup (Article, FAQ, Organization) | 1.5 |  | Not Started
W9 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W9 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W9 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W9 | Friday | Vaishali | 10:30 AM | NEWS | News: ISO 42001 Governance | 1.5 |  | Not Started
W9 | Friday | Vaishali | 11:00 AM | PAGE | Page: Enterprise AI Strategy Anaheim | 2.0 |  | Not Started
W9 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Schema markup (Article, FAQ, Organization) | 1.5 |  | Not Started
W9 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W9 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W9 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W9 | Friday | Puneet | 1:00 PM | NEWS | News: Microsoft Zero-Day Patch | 1.5 |  | Not Started
W9 | Friday | Puneet | 1:30 PM | PAGE | Page: Cybersecurity Services Downtown LA | 2.0 |  | Not Started
W9 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Schema markup (Article, FAQ, Organization) | 1.5 |  | Not Started
W9 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W9 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W9 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W9 | Friday | Mohit | 1:00 PM | NEWS | News: GitHub Copilot Workspace | 1.5 |  | Not Started
W9 | Friday | Mohit | 1:30 PM | PAGE | Page: .NET Development Long Beach | 2.0 |  | Not Started
W9 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Schema markup (Article, FAQ, Organization) | 1.5 |  | Not Started
W9 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W9 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W9 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W10 | Monday | Saroj | 10:30 AM | PAGE | Page: Google Ads Management Santa Ana | 2.0 |  | Not Started
W10 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Indexing optimization + sitemap check | 2.0 |  | Not Started
W10 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W10 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W10 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W10 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W10 | Monday | Vaishali | 10:30 AM | PAGE | Page: AI Security Consulting Long Beach | 2.0 |  | Not Started
W10 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Indexing optimization + sitemap check | 2.0 |  | Not Started
W10 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W10 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W10 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W10 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W10 | Monday | Puneet | 1:00 PM | BLOG | Blog: SOC 2 Compliance: Why OC Needs It | 2.5 |  | Not Started
W10 | Monday | Puneet | 3:30 PM | PAGE | Page: Cloud Migration Torrance | 2.0 |  | Not Started
W10 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Indexing optimization + sitemap check | 1.5 |  | Not Started
W10 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W10 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W10 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W10 | Monday | Mohit | 1:00 PM | PAGE | Page: React Development Anaheim | 2.0 |  | Not Started
W10 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Indexing optimization + sitemap check | 2.0 |  | Not Started
W10 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W10 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W10 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W10 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W10 | Tuesday | Saroj | 10:30 AM | PAGE | Page: Content Marketing Downtown LA | 2.0 |  | Not Started
W10 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Indexing optimization + sitemap check | 2.0 |  | Not Started
W10 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W10 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W10 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W10 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W10 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: AI Automation Services Newport Beach | 2.0 |  | Not Started
W10 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Indexing optimization + sitemap check | 2.0 |  | Not Started
W10 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W10 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W10 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W10 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W10 | Tuesday | Puneet | 1:00 PM | PAGE | Page: IT Disaster Recovery Tustin | 2.0 |  | Not Started
W10 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Indexing optimization + sitemap check | 2.0 |  | Not Started
W10 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W10 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W10 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W10 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W10 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: API-First Architecture SaaS | 2.5 |  | Not Started
W10 | Tuesday | Mohit | 3:30 PM | PAGE | Page: SaaS Development Newport Beach | 2.0 |  | Not Started
W10 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Indexing optimization + sitemap check | 1.5 |  | Not Started
W10 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W10 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W10 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W10 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: Schema Markup OC Business | 2.5 |  | Not Started
W10 | Wednesday | Saroj | 12:30 PM | PAGE | Page: Link Building Torrance | 2.0 |  | Not Started
W10 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Indexing optimization + sitemap check | 1.5 |  | Not Started
W10 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W10 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W10 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W10 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: Power BI AI Integration Tustin | 2.0 |  | Not Started
W10 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Indexing optimization + sitemap check | 2.0 |  | Not Started
W10 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W10 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W10 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W10 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W10 | Wednesday | Puneet | 1:00 PM | PAGE | Page: Network Monitoring Culver City | 2.0 |  | Not Started
W10 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Indexing optimization + sitemap check | 2.0 |  | Not Started
W10 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W10 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W10 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W10 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W10 | Wednesday | Mohit | 1:00 PM | PAGE | Page: AI Agent Development Tustin | 2.0 |  | Not Started
W10 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Indexing optimization + sitemap check | 2.0 |  | Not Started
W10 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W10 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W10 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W10 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W10 | Thursday | Saroj | 10:30 AM | PAGE | Page: SEO Audit Santa Monica | 2.0 |  | Not Started
W10 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Indexing optimization + sitemap check | 2.0 |  | Not Started
W10 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W10 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W10 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W10 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W10 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: RAG Architecture Enterprise | 2.5 |  | Not Started
W10 | Thursday | Vaishali | 12:30 PM | PAGE | Page: AI Training Santa Ana | 2.0 |  | Not Started
W10 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Indexing optimization + sitemap check | 1.5 |  | Not Started
W10 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W10 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W10 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W10 | Thursday | Puneet | 1:00 PM | PAGE | Page: Endpoint Security Santa Monica | 2.0 |  | Not Started
W10 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Indexing optimization + sitemap check | 2.0 |  | Not Started
W10 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W10 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W10 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W10 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W10 | Thursday | Mohit | 1:00 PM | PAGE | Page: CRM Development Santa Ana | 2.0 |  | Not Started
W10 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Indexing optimization + sitemap check | 2.0 |  | Not Started
W10 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W10 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W10 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W10 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W10 | Friday | Saroj | 10:30 AM | NEWS | News: Instagram SEO Local | 1.5 |  | Not Started
W10 | Friday | Saroj | 11:00 AM | PAGE | Page: E-Commerce SEO Costa Mesa | 2.0 |  | Not Started
W10 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Indexing optimization + sitemap check | 1.5 |  | Not Started
W10 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W10 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W10 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W10 | Friday | Vaishali | 10:30 AM | NEWS | News: SoCal AI Summit | 1.5 |  | Not Started
W10 | Friday | Vaishali | 11:00 AM | PAGE | Page: AI Penetration Testing Irvine | 2.0 |  | Not Started
W10 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Indexing optimization + sitemap check | 1.5 |  | Not Started
W10 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W10 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W10 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W10 | Friday | Puneet | 1:00 PM | NEWS | News: FBI Phishing Alert OC | 1.5 |  | Not Started
W10 | Friday | Puneet | 1:30 PM | PAGE | Page: Compliance IT Irvine | 2.0 |  | Not Started
W10 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Indexing optimization + sitemap check | 1.5 |  | Not Started
W10 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W10 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W10 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W10 | Friday | Mohit | 1:00 PM | NEWS | News: Kubernetes 2026 | 1.5 |  | Not Started
W10 | Friday | Mohit | 1:30 PM | PAGE | Page: Mobile App Dev Irvine | 2.0 |  | Not Started
W10 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Indexing optimization + sitemap check | 1.5 |  | Not Started
W10 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W10 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W10 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W11 | Monday | Saroj | 10:30 AM | PAGE | Page: Schema Markup Services Anaheim | 2.0 |  | Not Started
W11 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Authority content publishing (case studies, guides) | 2.0 |  | Not Started
W11 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W11 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W11 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W11 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W11 | Monday | Vaishali | 10:30 AM | PAGE | Page: AI Data Analytics Downtown LA | 2.0 |  | Not Started
W11 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Authority content publishing (case studies, guides) | 2.0 |  | Not Started
W11 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W11 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W11 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W11 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W11 | Monday | Puneet | 1:00 PM | BLOG | Blog: Ransomware Targets Small Clinics | 2.5 |  | Not Started
W11 | Monday | Puneet | 3:30 PM | PAGE | Page: IT Consulting Newport Beach | 2.0 |  | Not Started
W11 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Authority content publishing (case studies, guides) | 1.5 |  | Not Started
W11 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W11 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W11 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W11 | Monday | Mohit | 1:00 PM | PAGE | Page: API Development Santa Monica | 2.0 |  | Not Started
W11 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Authority content publishing (case studies, guides) | 2.0 |  | Not Started
W11 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W11 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W11 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W11 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W11 | Tuesday | Saroj | 10:30 AM | PAGE | Page: Website Speed Optimization Long Beach | 2.0 |  | Not Started
W11 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Authority content publishing (case studies, guides) | 2.0 |  | Not Started
W11 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W11 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W11 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W11 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W11 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: Digital Transformation Torrance | 2.0 |  | Not Started
W11 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Authority content publishing (case studies, guides) | 2.0 |  | Not Started
W11 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W11 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W11 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W11 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W11 | Tuesday | Puneet | 1:00 PM | PAGE | Page: Server Management Santa Ana | 2.0 |  | Not Started
W11 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Authority content publishing (case studies, guides) | 2.0 |  | Not Started
W11 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W11 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W11 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W11 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W11 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: AI Code Review Saves 40% | 2.5 |  | Not Started
W11 | Tuesday | Mohit | 3:30 PM | PAGE | Page: Cloud App Development Culver City | 2.0 |  | Not Started
W11 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Authority content publishing (case studies, guides) | 1.5 |  | Not Started
W11 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W11 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W11 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W11 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: Fix LCP FID CLS Shopify | 2.5 |  | Not Started
W11 | Wednesday | Saroj | 12:30 PM | PAGE | Page: Social Media Marketing Tustin | 2.0 |  | Not Started
W11 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Authority content publishing (case studies, guides) | 1.5 |  | Not Started
W11 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W11 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W11 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W11 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: AI Process Automation Culver City | 2.0 |  | Not Started
W11 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Authority content publishing (case studies, guides) | 2.0 |  | Not Started
W11 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W11 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W11 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W11 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W11 | Wednesday | Puneet | 1:00 PM | PAGE | Page: Data Backup Solutions Anaheim | 2.0 |  | Not Started
W11 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Authority content publishing (case studies, guides) | 2.0 |  | Not Started
W11 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W11 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W11 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W11 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W11 | Wednesday | Mohit | 1:00 PM | PAGE | Page: DevOps Services Downtown LA | 2.0 |  | Not Started
W11 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Authority content publishing (case studies, guides) | 2.0 |  | Not Started
W11 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W11 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W11 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W11 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W11 | Thursday | Saroj | 10:30 AM | PAGE | Page: SEO Services Culver City | 2.0 |  | Not Started
W11 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Authority content publishing (case studies, guides) | 2.0 |  | Not Started
W11 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W11 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W11 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W11 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W11 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: AI HR Automation 2026 | 2.5 |  | Not Started
W11 | Thursday | Vaishali | 12:30 PM | PAGE | Page: AI Consulting Santa Monica | 2.0 |  | Not Started
W11 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Authority content publishing (case studies, guides) | 1.5 |  | Not Started
W11 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W11 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W11 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W11 | Thursday | Puneet | 1:00 PM | PAGE | Page: Managed IT Services Costa Mesa | 2.0 |  | Not Started
W11 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Authority content publishing (case studies, guides) | 2.0 |  | Not Started
W11 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W11 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W11 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W11 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W11 | Thursday | Mohit | 1:00 PM | PAGE | Page: AI Software Development Torrance | 2.0 |  | Not Started
W11 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Authority content publishing (case studies, guides) | 2.0 |  | Not Started
W11 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W11 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W11 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W11 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W11 | Friday | Saroj | 10:30 AM | NEWS | News: TikTok Search OC | 1.5 |  | Not Started
W11 | Friday | Saroj | 11:00 AM | PAGE | Page: Local SEO Irvine | 2.0 |  | Not Started
W11 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Authority content publishing (case studies, guides) | 1.5 |  | Not Started
W11 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W11 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W11 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W11 | Friday | Vaishali | 10:30 AM | NEWS | News: Power BI AI Release | 1.5 |  | Not Started
W11 | Friday | Vaishali | 11:00 AM | PAGE | Page: Copilot Implementation Costa Mesa | 2.0 |  | Not Started
W11 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Authority content publishing (case studies, guides) | 1.5 |  | Not Started
W11 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W11 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W11 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W11 | Friday | Puneet | 1:00 PM | NEWS | News: Hospital Ransomware Lessons | 1.5 |  | Not Started
W11 | Friday | Puneet | 1:30 PM | PAGE | Page: HIPAA IT Support Long Beach | 2.0 |  | Not Started
W11 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Authority content publishing (case studies, guides) | 1.5 |  | Not Started
W11 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W11 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W11 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W11 | Friday | Mohit | 1:00 PM | NEWS | News: TypeScript 6.0 | 1.5 |  | Not Started
W11 | Friday | Mohit | 1:30 PM | PAGE | Page: Custom App Development Costa Mesa | 2.0 |  | Not Started
W11 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Authority content publishing (case studies, guides) | 1.5 |  | Not Started
W11 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W11 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W11 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W12 | Monday | Saroj | 10:30 AM | PAGE | Page: Technical SEO Newport Beach | 2.0 |  | Not Started
W12 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Linkable asset creation (data, templates, tools) | 2.0 |  | Not Started
W12 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W12 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W12 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W12 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W12 | Monday | Vaishali | 10:30 AM | PAGE | Page: Gemini Integration Anaheim | 2.0 |  | Not Started
W12 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Linkable asset creation (data, templates, tools) | 2.0 |  | Not Started
W12 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W12 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W12 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W12 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W12 | Monday | Puneet | 1:00 PM | BLOG | Blog: Zero Trust Security for OC | 2.5 |  | Not Started
W12 | Monday | Puneet | 3:30 PM | PAGE | Page: 24/7 IT Helpdesk Downtown LA | 2.0 |  | Not Started
W12 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Linkable asset creation (data, templates, tools) | 1.5 |  | Not Started
W12 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W12 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W12 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W12 | Monday | Mohit | 1:00 PM | PAGE | Page: Enterprise Web Apps Long Beach | 2.0 |  | Not Started
W12 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Linkable asset creation (data, templates, tools) | 2.0 |  | Not Started
W12 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W12 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W12 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W12 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W12 | Tuesday | Saroj | 10:30 AM | PAGE | Page: Answer Engine Optimization Santa Ana | 2.0 |  | Not Started
W12 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Linkable asset creation (data, templates, tools) | 2.0 |  | Not Started
W12 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W12 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W12 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W12 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W12 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: Enterprise AI Strategy Long Beach | 2.0 |  | Not Started
W12 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Linkable asset creation (data, templates, tools) | 2.0 |  | Not Started
W12 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W12 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W12 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W12 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W12 | Tuesday | Puneet | 1:00 PM | PAGE | Page: Cybersecurity Services Torrance | 2.0 |  | Not Started
W12 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Linkable asset creation (data, templates, tools) | 2.0 |  | Not Started
W12 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W12 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W12 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W12 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W12 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: Custom CRM vs Salesforce | 2.5 |  | Not Started
W12 | Tuesday | Mohit | 3:30 PM | PAGE | Page: .NET Development Anaheim | 2.0 |  | Not Started
W12 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Linkable asset creation (data, templates, tools) | 1.5 |  | Not Started
W12 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W12 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W12 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W12 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: Rank in Google AI Overviews | 2.5 |  | Not Started
W12 | Wednesday | Saroj | 12:30 PM | PAGE | Page: Google Ads Management Downtown LA | 2.0 |  | Not Started
W12 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Linkable asset creation (data, templates, tools) | 1.5 |  | Not Started
W12 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W12 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W12 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W12 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: AI Security Consulting Newport Beach | 2.0 |  | Not Started
W12 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Linkable asset creation (data, templates, tools) | 2.0 |  | Not Started
W12 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W12 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W12 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W12 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W12 | Wednesday | Puneet | 1:00 PM | PAGE | Page: Cloud Migration Tustin | 2.0 |  | Not Started
W12 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Linkable asset creation (data, templates, tools) | 2.0 |  | Not Started
W12 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W12 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W12 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W12 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W12 | Wednesday | Mohit | 1:00 PM | PAGE | Page: React Development Newport Beach | 2.0 |  | Not Started
W12 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Linkable asset creation (data, templates, tools) | 2.0 |  | Not Started
W12 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W12 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W12 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W12 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W12 | Thursday | Saroj | 10:30 AM | PAGE | Page: Content Marketing Torrance | 2.0 |  | Not Started
W12 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Linkable asset creation (data, templates, tools) | 2.0 |  | Not Started
W12 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W12 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W12 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W12 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W12 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: AI POC in 2 Weeks | 2.5 |  | Not Started
W12 | Thursday | Vaishali | 12:30 PM | PAGE | Page: AI Automation Services Tustin | 2.0 |  | Not Started
W12 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Linkable asset creation (data, templates, tools) | 1.5 |  | Not Started
W12 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W12 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W12 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W12 | Thursday | Puneet | 1:00 PM | PAGE | Page: IT Disaster Recovery Culver City | 2.0 |  | Not Started
W12 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Linkable asset creation (data, templates, tools) | 2.0 |  | Not Started
W12 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W12 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W12 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W12 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W12 | Thursday | Mohit | 1:00 PM | PAGE | Page: SaaS Development Tustin | 2.0 |  | Not Started
W12 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Linkable asset creation (data, templates, tools) | 2.0 |  | Not Started
W12 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W12 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W12 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W12 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W12 | Friday | Saroj | 10:30 AM | NEWS | News: Apple Maps OC Changes | 1.5 |  | Not Started
W12 | Friday | Saroj | 11:00 AM | PAGE | Page: Link Building Santa Monica | 2.0 |  | Not Started
W12 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Linkable asset creation (data, templates, tools) | 1.5 |  | Not Started
W12 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W12 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W12 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W12 | Friday | Vaishali | 10:30 AM | NEWS | News: Salesforce Einstein | 1.5 |  | Not Started
W12 | Friday | Vaishali | 11:00 AM | PAGE | Page: Power BI AI Integration Santa Ana | 2.0 |  | Not Started
W12 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Linkable asset creation (data, templates, tools) | 1.5 |  | Not Started
W12 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W12 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W12 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W12 | Friday | Puneet | 1:00 PM | NEWS | News: Cloud Security 2026 | 1.5 |  | Not Started
W12 | Friday | Puneet | 1:30 PM | PAGE | Page: Network Monitoring Santa Monica | 2.0 |  | Not Started
W12 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Linkable asset creation (data, templates, tools) | 1.5 |  | Not Started
W12 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W12 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W12 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W12 | Friday | Mohit | 1:00 PM | NEWS | News: Irvine Tech Growth | 1.5 |  | Not Started
W12 | Friday | Mohit | 1:30 PM | PAGE | Page: AI Agent Development Santa Ana | 2.0 |  | Not Started
W12 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Linkable asset creation (data, templates, tools) | 1.5 |  | Not Started
W12 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W12 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W12 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W13 | Monday | Saroj | 10:30 AM | PAGE | Page: SEO Audit Costa Mesa | 2.0 |  | Not Started
W13 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Digital PR outreach | 2.0 |  | Not Started
W13 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W13 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W13 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W13 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W13 | Monday | Vaishali | 10:30 AM | PAGE | Page: AI Training Irvine | 2.0 |  | Not Started
W13 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Digital PR outreach | 2.0 |  | Not Started
W13 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W13 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W13 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W13 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W13 | Monday | Puneet | 1:00 PM | BLOG | Blog: Cloud Backup for HIPAA Practices | 2.5 |  | Not Started
W13 | Monday | Puneet | 3:30 PM | PAGE | Page: Endpoint Security Irvine | 2.0 |  | Not Started
W13 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Digital PR outreach | 1.5 |  | Not Started
W13 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W13 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W13 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W13 | Monday | Mohit | 1:00 PM | PAGE | Page: CRM Development Irvine | 2.0 |  | Not Started
W13 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Digital PR outreach | 2.0 |  | Not Started
W13 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W13 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W13 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W13 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W13 | Tuesday | Saroj | 10:30 AM | PAGE | Page: E-Commerce SEO Anaheim | 2.0 |  | Not Started
W13 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Digital PR outreach | 2.0 |  | Not Started
W13 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W13 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W13 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W13 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W13 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: AI Penetration Testing Downtown LA | 2.0 |  | Not Started
W13 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Digital PR outreach | 2.0 |  | Not Started
W13 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W13 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W13 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W13 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W13 | Tuesday | Puneet | 1:00 PM | PAGE | Page: Compliance IT Newport Beach | 2.0 |  | Not Started
W13 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Digital PR outreach | 2.0 |  | Not Started
W13 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W13 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W13 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W13 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W13 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: Microservices vs Monolith Startups | 2.5 |  | Not Started
W13 | Tuesday | Mohit | 3:30 PM | PAGE | Page: Mobile App Dev Santa Monica | 2.0 |  | Not Started
W13 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Digital PR outreach | 1.5 |  | Not Started
W13 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W13 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W13 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W13 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: Local vs National SEO OC | 2.5 |  | Not Started
W13 | Wednesday | Saroj | 12:30 PM | PAGE | Page: Schema Markup Services Long Beach | 2.0 |  | Not Started
W13 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Digital PR outreach | 1.5 |  | Not Started
W13 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W13 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W13 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W13 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: AI Data Analytics Torrance | 2.0 |  | Not Started
W13 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Digital PR outreach | 2.0 |  | Not Started
W13 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W13 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W13 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W13 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W13 | Wednesday | Puneet | 1:00 PM | PAGE | Page: IT Consulting Santa Ana | 2.0 |  | Not Started
W13 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Digital PR outreach | 2.0 |  | Not Started
W13 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W13 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W13 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W13 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W13 | Wednesday | Mohit | 1:00 PM | PAGE | Page: API Development Culver City | 2.0 |  | Not Started
W13 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Digital PR outreach | 2.0 |  | Not Started
W13 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W13 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W13 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W13 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W13 | Thursday | Saroj | 10:30 AM | PAGE | Page: Website Speed Optimization Tustin | 2.0 |  | Not Started
W13 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Digital PR outreach | 2.0 |  | Not Started
W13 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W13 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W13 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W13 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W13 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: Shadow AI Risks Management | 2.5 |  | Not Started
W13 | Thursday | Vaishali | 12:30 PM | PAGE | Page: Digital Transformation Culver City | 2.0 |  | Not Started
W13 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Digital PR outreach | 1.5 |  | Not Started
W13 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W13 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W13 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W13 | Thursday | Puneet | 1:00 PM | PAGE | Page: Server Management Anaheim | 2.0 |  | Not Started
W13 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Digital PR outreach | 2.0 |  | Not Started
W13 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W13 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W13 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W13 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W13 | Thursday | Mohit | 1:00 PM | PAGE | Page: Cloud App Development Downtown LA | 2.0 |  | Not Started
W13 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Digital PR outreach | 2.0 |  | Not Started
W13 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W13 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W13 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W13 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W13 | Friday | Saroj | 10:30 AM | NEWS | News: Bing AI Local Rankings | 1.5 |  | Not Started
W13 | Friday | Saroj | 11:00 AM | PAGE | Page: Social Media Marketing Culver City | 2.0 |  | Not Started
W13 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Digital PR outreach | 1.5 |  | Not Started
W13 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W13 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W13 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W13 | Friday | Vaishali | 10:30 AM | NEWS | News: AI Legal OC | 1.5 |  | Not Started
W13 | Friday | Vaishali | 11:00 AM | PAGE | Page: AI Process Automation Santa Monica | 2.0 |  | Not Started
W13 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Digital PR outreach | 1.5 |  | Not Started
W13 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W13 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W13 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W13 | Friday | Puneet | 1:00 PM | NEWS | News: New HIPAA Penalties CA | 1.5 |  | Not Started
W13 | Friday | Puneet | 1:30 PM | PAGE | Page: Data Backup Solutions Costa Mesa | 2.0 |  | Not Started
W13 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Digital PR outreach | 1.5 |  | Not Started
W13 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W13 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W13 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W13 | Friday | Mohit | 1:00 PM | NEWS | News: Vercel vs Netlify 2026 | 1.5 |  | Not Started
W13 | Friday | Mohit | 1:30 PM | PAGE | Page: DevOps Services Torrance | 2.0 |  | Not Started
W13 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Digital PR outreach | 1.5 |  | Not Started
W13 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W13 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W13 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W14 | Monday | Saroj | 10:30 AM | PAGE | Page: SEO Services Irvine | 2.0 |  | Not Started
W14 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Internal linking optimization | 2.0 |  | Not Started
W14 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W14 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W14 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W14 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W14 | Monday | Vaishali | 10:30 AM | PAGE | Page: AI Consulting Costa Mesa | 2.0 |  | Not Started
W14 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Internal linking optimization | 2.0 |  | Not Started
W14 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W14 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W14 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W14 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W14 | Monday | Puneet | 1:00 PM | BLOG | Blog: Prepare for HIPAA Audit 2026 | 2.5 |  | Not Started
W14 | Monday | Puneet | 3:30 PM | PAGE | Page: Managed IT Services Long Beach | 2.0 |  | Not Started
W14 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Internal linking optimization | 1.5 |  | Not Started
W14 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W14 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W14 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W14 | Monday | Mohit | 1:00 PM | PAGE | Page: AI Software Development Costa Mesa | 2.0 |  | Not Started
W14 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Internal linking optimization | 2.0 |  | Not Started
W14 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W14 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W14 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W14 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W14 | Tuesday | Saroj | 10:30 AM | PAGE | Page: Local SEO Newport Beach | 2.0 |  | Not Started
W14 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Internal linking optimization | 2.0 |  | Not Started
W14 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W14 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W14 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W14 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W14 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: Copilot Implementation Anaheim | 2.0 |  | Not Started
W14 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Internal linking optimization | 2.0 |  | Not Started
W14 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W14 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W14 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W14 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W14 | Tuesday | Puneet | 1:00 PM | PAGE | Page: HIPAA IT Support Downtown LA | 2.0 |  | Not Started
W14 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Internal linking optimization | 2.0 |  | Not Started
W14 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W14 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W14 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W14 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W14 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: Technical Debt Cost OC Startups | 2.5 |  | Not Started
W14 | Tuesday | Mohit | 3:30 PM | PAGE | Page: Custom App Development Long Beach | 2.0 |  | Not Started
W14 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Internal linking optimization | 1.5 |  | Not Started
W14 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W14 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W14 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W14 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: Optimize GBP for Calls | 2.5 |  | Not Started
W14 | Wednesday | Saroj | 12:30 PM | PAGE | Page: Technical SEO Santa Ana | 2.0 |  | Not Started
W14 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Internal linking optimization | 1.5 |  | Not Started
W14 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W14 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W14 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W14 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: Gemini Integration Long Beach | 2.0 |  | Not Started
W14 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Internal linking optimization | 2.0 |  | Not Started
W14 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W14 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W14 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W14 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W14 | Wednesday | Puneet | 1:00 PM | PAGE | Page: 24/7 IT Helpdesk Torrance | 2.0 |  | Not Started
W14 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Internal linking optimization | 2.0 |  | Not Started
W14 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W14 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W14 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W14 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W14 | Wednesday | Mohit | 1:00 PM | PAGE | Page: Enterprise Web Apps Anaheim | 2.0 |  | Not Started
W14 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Internal linking optimization | 2.0 |  | Not Started
W14 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W14 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W14 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W14 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W14 | Thursday | Saroj | 10:30 AM | PAGE | Page: Answer Engine Optimization Downtown LA | 2.0 |  | Not Started
W14 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Internal linking optimization | 2.0 |  | Not Started
W14 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W14 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W14 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W14 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W14 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: Power BI AI for OC | 2.5 |  | Not Started
W14 | Thursday | Vaishali | 12:30 PM | PAGE | Page: Enterprise AI Strategy Newport Beach | 2.0 |  | Not Started
W14 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Internal linking optimization | 1.5 |  | Not Started
W14 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W14 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W14 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W14 | Thursday | Puneet | 1:00 PM | PAGE | Page: Cybersecurity Services Tustin | 2.0 |  | Not Started
W14 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Internal linking optimization | 2.0 |  | Not Started
W14 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W14 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W14 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W14 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W14 | Thursday | Mohit | 1:00 PM | PAGE | Page: .NET Development Newport Beach | 2.0 |  | Not Started
W14 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Internal linking optimization | 2.0 |  | Not Started
W14 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W14 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W14 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W14 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W14 | Friday | Saroj | 10:30 AM | NEWS | News: Reddit SEO Google | 1.5 |  | Not Started
W14 | Friday | Saroj | 11:00 AM | PAGE | Page: Google Ads Management Torrance | 2.0 |  | Not Started
W14 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Internal linking optimization | 1.5 |  | Not Started
W14 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W14 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W14 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W14 | Friday | Vaishali | 10:30 AM | NEWS | News: Meta AI Enterprise | 1.5 |  | Not Started
W14 | Friday | Vaishali | 11:00 AM | PAGE | Page: AI Security Consulting Tustin | 2.0 |  | Not Started
W14 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Internal linking optimization | 1.5 |  | Not Started
W14 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W14 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W14 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W14 | Friday | Puneet | 1:00 PM | NEWS | News: OC School Data Breach | 1.5 |  | Not Started
W14 | Friday | Puneet | 1:30 PM | PAGE | Page: Cloud Migration Culver City | 2.0 |  | Not Started
W14 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Internal linking optimization | 1.5 |  | Not Started
W14 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W14 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W14 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W14 | Friday | Mohit | 1:00 PM | NEWS | News: OpenAI API Impact | 1.5 |  | Not Started
W14 | Friday | Mohit | 1:30 PM | PAGE | Page: React Development Tustin | 2.0 |  | Not Started
W14 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Internal linking optimization | 1.5 |  | Not Started
W14 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W14 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W14 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W15 | Monday | Saroj | 10:30 AM | PAGE | Page: Content Marketing Santa Monica | 2.0 |  | Not Started
W15 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Content refresh (update old posts) | 2.0 |  | Not Started
W15 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W15 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W15 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W15 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W15 | Monday | Vaishali | 10:30 AM | PAGE | Page: AI Automation Services Santa Ana | 2.0 |  | Not Started
W15 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Content refresh (update old posts) | 2.0 |  | Not Started
W15 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W15 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W15 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W15 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W15 | Monday | Puneet | 1:00 PM | BLOG | Blog: IT Disaster Recovery Newport Beach | 2.5 |  | Not Started
W15 | Monday | Puneet | 3:30 PM | PAGE | Page: IT Disaster Recovery Santa Monica | 2.0 |  | Not Started
W15 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Content refresh (update old posts) | 1.5 |  | Not Started
W15 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W15 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W15 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W15 | Monday | Mohit | 1:00 PM | PAGE | Page: SaaS Development Santa Ana | 2.0 |  | Not Started
W15 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Content refresh (update old posts) | 2.0 |  | Not Started
W15 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W15 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W15 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W15 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W15 | Tuesday | Saroj | 10:30 AM | PAGE | Page: Link Building Costa Mesa | 2.0 |  | Not Started
W15 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Content refresh (update old posts) | 2.0 |  | Not Started
W15 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W15 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W15 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W15 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W15 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: Power BI AI Integration Irvine | 2.0 |  | Not Started
W15 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Content refresh (update old posts) | 2.0 |  | Not Started
W15 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W15 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W15 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W15 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W15 | Tuesday | Puneet | 1:00 PM | PAGE | Page: Network Monitoring Irvine | 2.0 |  | Not Started
W15 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Content refresh (update old posts) | 2.0 |  | Not Started
W15 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W15 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W15 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W15 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W15 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: Software Dev RFP 2026 | 2.5 |  | Not Started
W15 | Tuesday | Mohit | 3:30 PM | PAGE | Page: AI Agent Development Irvine | 2.0 |  | Not Started
W15 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Content refresh (update old posts) | 1.5 |  | Not Started
W15 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W15 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W15 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W15 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: Technical SEO Audit Checklist | 2.5 |  | Not Started
W15 | Wednesday | Saroj | 12:30 PM | PAGE | Page: SEO Audit Anaheim | 2.0 |  | Not Started
W15 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Content refresh (update old posts) | 1.5 |  | Not Started
W15 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W15 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W15 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W15 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: AI Training Downtown LA | 2.0 |  | Not Started
W15 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Content refresh (update old posts) | 2.0 |  | Not Started
W15 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W15 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W15 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W15 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W15 | Wednesday | Puneet | 1:00 PM | PAGE | Page: Endpoint Security Newport Beach | 2.0 |  | Not Started
W15 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Content refresh (update old posts) | 2.0 |  | Not Started
W15 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W15 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W15 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W15 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W15 | Wednesday | Mohit | 1:00 PM | PAGE | Page: CRM Development Santa Monica | 2.0 |  | Not Started
W15 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Content refresh (update old posts) | 2.0 |  | Not Started
W15 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W15 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W15 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W15 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W15 | Thursday | Saroj | 10:30 AM | PAGE | Page: E-Commerce SEO Long Beach | 2.0 |  | Not Started
W15 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Content refresh (update old posts) | 2.0 |  | Not Started
W15 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W15 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W15 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W15 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W15 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: AI Chatbot vs Agent 2026 | 2.5 |  | Not Started
W15 | Thursday | Vaishali | 12:30 PM | PAGE | Page: AI Penetration Testing Torrance | 2.0 |  | Not Started
W15 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Content refresh (update old posts) | 1.5 |  | Not Started
W15 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W15 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W15 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W15 | Thursday | Puneet | 1:00 PM | PAGE | Page: Compliance IT Santa Ana | 2.0 |  | Not Started
W15 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Content refresh (update old posts) | 2.0 |  | Not Started
W15 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W15 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W15 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W15 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W15 | Thursday | Mohit | 1:00 PM | PAGE | Page: Mobile App Dev Culver City | 2.0 |  | Not Started
W15 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Content refresh (update old posts) | 2.0 |  | Not Started
W15 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W15 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W15 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W15 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W15 | Friday | Saroj | 10:30 AM | NEWS | News: YouTube Shorts SEO | 1.5 |  | Not Started
W15 | Friday | Saroj | 11:00 AM | PAGE | Page: Schema Markup Services Tustin | 2.0 |  | Not Started
W15 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Content refresh (update old posts) | 1.5 |  | Not Started
W15 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W15 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W15 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W15 | Friday | Vaishali | 10:30 AM | NEWS | News: SoCal Manufacturing AI | 1.5 |  | Not Started
W15 | Friday | Vaishali | 11:00 AM | PAGE | Page: AI Data Analytics Culver City | 2.0 |  | Not Started
W15 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Content refresh (update old posts) | 1.5 |  | Not Started
W15 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W15 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W15 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W15 | Friday | Puneet | 1:00 PM | NEWS | News: Zero Trust Federal Mandate OC | 1.5 |  | Not Started
W15 | Friday | Puneet | 1:30 PM | PAGE | Page: IT Consulting Anaheim | 2.0 |  | Not Started
W15 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Content refresh (update old posts) | 1.5 |  | Not Started
W15 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W15 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W15 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W15 | Friday | Mohit | 1:00 PM | NEWS | News: YC SoCal Startups | 1.5 |  | Not Started
W15 | Friday | Mohit | 1:30 PM | PAGE | Page: API Development Downtown LA | 2.0 |  | Not Started
W15 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Content refresh (update old posts) | 1.5 |  | Not Started
W15 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W15 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W15 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W16 | Monday | Saroj | 10:30 AM | PAGE | Page: Website Speed Optimization Culver City | 2.0 |  | Not Started
W16 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: UX + engagement optimization | 2.0 |  | Not Started
W16 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W16 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W16 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W16 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W16 | Monday | Vaishali | 10:30 AM | PAGE | Page: Digital Transformation Santa Monica | 2.0 |  | Not Started
W16 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: UX + engagement optimization | 2.0 |  | Not Started
W16 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W16 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W16 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W16 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W16 | Monday | Puneet | 1:00 PM | BLOG | Blog: OC Dental Practices Need Managed IT | 2.5 |  | Not Started
W16 | Monday | Puneet | 3:30 PM | PAGE | Page: Server Management Costa Mesa | 2.0 |  | Not Started
W16 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: UX + engagement optimization | 1.5 |  | Not Started
W16 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W16 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W16 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W16 | Monday | Mohit | 1:00 PM | PAGE | Page: Cloud App Development Torrance | 2.0 |  | Not Started
W16 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: UX + engagement optimization | 2.0 |  | Not Started
W16 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W16 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W16 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W16 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W16 | Tuesday | Saroj | 10:30 AM | PAGE | Page: Social Media Marketing Irvine | 2.0 |  | Not Started
W16 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: UX + engagement optimization | 2.0 |  | Not Started
W16 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W16 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W16 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W16 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W16 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: AI Process Automation Costa Mesa | 2.0 |  | Not Started
W16 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: UX + engagement optimization | 2.0 |  | Not Started
W16 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W16 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W16 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W16 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W16 | Tuesday | Puneet | 1:00 PM | PAGE | Page: Data Backup Solutions Long Beach | 2.0 |  | Not Started
W16 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: UX + engagement optimization | 2.0 |  | Not Started
W16 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W16 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W16 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W16 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W16 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: CI/CD Pipeline Startups | 2.5 |  | Not Started
W16 | Tuesday | Mohit | 3:30 PM | PAGE | Page: DevOps Services Costa Mesa | 2.0 |  | Not Started
W16 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: UX + engagement optimization | 1.5 |  | Not Started
W16 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W16 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W16 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W16 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: Page Speed OC Restaurants | 2.5 |  | Not Started
W16 | Wednesday | Saroj | 12:30 PM | PAGE | Page: SEO Services Newport Beach | 2.0 |  | Not Started
W16 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: UX + engagement optimization | 1.5 |  | Not Started
W16 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W16 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W16 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W16 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: AI Consulting Anaheim | 2.0 |  | Not Started
W16 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: UX + engagement optimization | 2.0 |  | Not Started
W16 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W16 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W16 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W16 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W16 | Wednesday | Puneet | 1:00 PM | PAGE | Page: Managed IT Services Downtown LA | 2.0 |  | Not Started
W16 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: UX + engagement optimization | 2.0 |  | Not Started
W16 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W16 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W16 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W16 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W16 | Wednesday | Mohit | 1:00 PM | PAGE | Page: AI Software Development Long Beach | 2.0 |  | Not Started
W16 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: UX + engagement optimization | 2.0 |  | Not Started
W16 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W16 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W16 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W16 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W16 | Thursday | Saroj | 10:30 AM | PAGE | Page: Local SEO Santa Ana | 2.0 |  | Not Started
W16 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: UX + engagement optimization | 2.0 |  | Not Started
W16 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W16 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W16 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W16 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W16 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: AI ROI Metrics That Matter | 2.5 |  | Not Started
W16 | Thursday | Vaishali | 12:30 PM | PAGE | Page: Copilot Implementation Long Beach | 2.0 |  | Not Started
W16 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: UX + engagement optimization | 1.5 |  | Not Started
W16 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W16 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W16 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W16 | Thursday | Puneet | 1:00 PM | PAGE | Page: HIPAA IT Support Torrance | 2.0 |  | Not Started
W16 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: UX + engagement optimization | 2.0 |  | Not Started
W16 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W16 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W16 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W16 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W16 | Thursday | Mohit | 1:00 PM | PAGE | Page: Custom App Development Anaheim | 2.0 |  | Not Started
W16 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: UX + engagement optimization | 2.0 |  | Not Started
W16 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W16 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W16 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W16 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W16 | Friday | Saroj | 10:30 AM | NEWS | News: Google LSA OC | 1.5 |  | Not Started
W16 | Friday | Saroj | 11:00 AM | PAGE | Page: Technical SEO Downtown LA | 2.0 |  | Not Started
W16 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: UX + engagement optimization | 1.5 |  | Not Started
W16 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W16 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W16 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W16 | Friday | Vaishali | 10:30 AM | NEWS | News: ServiceNow AI | 1.5 |  | Not Started
W16 | Friday | Vaishali | 11:00 AM | PAGE | Page: Gemini Integration Newport Beach | 2.0 |  | Not Started
W16 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: UX + engagement optimization | 1.5 |  | Not Started
W16 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W16 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W16 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W16 | Friday | Puneet | 1:00 PM | NEWS | News: Managed IT SoCal Trends | 1.5 |  | Not Started
W16 | Friday | Puneet | 1:30 PM | PAGE | Page: 24/7 IT Helpdesk Tustin | 2.0 |  | Not Started
W16 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: UX + engagement optimization | 1.5 |  | Not Started
W16 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W16 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W16 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W16 | Friday | Mohit | 1:00 PM | NEWS | News: Docker Security Enterprise | 1.5 |  | Not Started
W16 | Friday | Mohit | 1:30 PM | PAGE | Page: Enterprise Web Apps Newport Beach | 2.0 |  | Not Started
W16 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: UX + engagement optimization | 1.5 |  | Not Started
W16 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W16 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W16 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W17 | Monday | Saroj | 10:30 AM | PAGE | Page: Answer Engine Optimization Torrance | 2.0 |  | Not Started
W17 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Featured snippet optimization | 2.0 |  | Not Started
W17 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W17 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W17 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W17 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W17 | Monday | Vaishali | 10:30 AM | PAGE | Page: Enterprise AI Strategy Tustin | 2.0 |  | Not Started
W17 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Featured snippet optimization | 2.0 |  | Not Started
W17 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W17 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W17 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W17 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W17 | Monday | Puneet | 1:00 PM | BLOG | Blog: EDR: Protecting OC Offices | 2.5 |  | Not Started
W17 | Monday | Puneet | 3:30 PM | PAGE | Page: Cybersecurity Services Culver City | 2.0 |  | Not Started
W17 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Featured snippet optimization | 1.5 |  | Not Started
W17 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W17 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W17 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W17 | Monday | Mohit | 1:00 PM | PAGE | Page: .NET Development Tustin | 2.0 |  | Not Started
W17 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Featured snippet optimization | 2.0 |  | Not Started
W17 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W17 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W17 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W17 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W17 | Tuesday | Saroj | 10:30 AM | PAGE | Page: Google Ads Management Santa Monica | 2.0 |  | Not Started
W17 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Featured snippet optimization | 2.0 |  | Not Started
W17 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W17 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W17 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W17 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W17 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: AI Security Consulting Santa Ana | 2.0 |  | Not Started
W17 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Featured snippet optimization | 2.0 |  | Not Started
W17 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W17 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W17 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W17 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W17 | Tuesday | Puneet | 1:00 PM | PAGE | Page: Cloud Migration Santa Monica | 2.0 |  | Not Started
W17 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Featured snippet optimization | 2.0 |  | Not Started
W17 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W17 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W17 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W17 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W17 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: Offshore Dev = Spaghetti Code | 2.5 |  | Not Started
W17 | Tuesday | Mohit | 3:30 PM | PAGE | Page: React Development Santa Ana | 2.0 |  | Not Started
W17 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Featured snippet optimization | 1.5 |  | Not Started
W17 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W17 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W17 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W17 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: Link Building OC Businesses | 2.5 |  | Not Started
W17 | Wednesday | Saroj | 12:30 PM | PAGE | Page: Content Marketing Costa Mesa | 2.0 |  | Not Started
W17 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Featured snippet optimization | 1.5 |  | Not Started
W17 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W17 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W17 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W17 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: AI Automation Services Irvine | 2.0 |  | Not Started
W17 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Featured snippet optimization | 2.0 |  | Not Started
W17 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W17 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W17 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W17 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W17 | Wednesday | Puneet | 1:00 PM | PAGE | Page: IT Disaster Recovery Irvine | 2.0 |  | Not Started
W17 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Featured snippet optimization | 2.0 |  | Not Started
W17 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W17 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W17 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W17 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W17 | Wednesday | Mohit | 1:00 PM | PAGE | Page: SaaS Development Irvine | 2.0 |  | Not Started
W17 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Featured snippet optimization | 2.0 |  | Not Started
W17 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W17 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W17 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W17 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W17 | Thursday | Saroj | 10:30 AM | PAGE | Page: Link Building Anaheim | 2.0 |  | Not Started
W17 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Featured snippet optimization | 2.0 |  | Not Started
W17 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W17 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W17 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W17 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W17 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: AI Governance Framework | 2.5 |  | Not Started
W17 | Thursday | Vaishali | 12:30 PM | PAGE | Page: Power BI AI Integration Downtown LA | 2.0 |  | Not Started
W17 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Featured snippet optimization | 1.5 |  | Not Started
W17 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W17 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W17 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W17 | Thursday | Puneet | 1:00 PM | PAGE | Page: Network Monitoring Newport Beach | 2.0 |  | Not Started
W17 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Featured snippet optimization | 2.0 |  | Not Started
W17 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W17 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W17 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W17 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W17 | Thursday | Mohit | 1:00 PM | PAGE | Page: AI Agent Development Santa Monica | 2.0 |  | Not Started
W17 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Featured snippet optimization | 2.0 |  | Not Started
W17 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W17 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W17 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W17 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W17 | Friday | Saroj | 10:30 AM | NEWS | News: Schema.org 2026 | 1.5 |  | Not Started
W17 | Friday | Saroj | 11:00 AM | PAGE | Page: SEO Audit Long Beach | 2.0 |  | Not Started
W17 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Featured snippet optimization | 1.5 |  | Not Started
W17 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W17 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W17 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W17 | Friday | Vaishali | 10:30 AM | NEWS | News: AI Privacy CA Laws | 1.5 |  | Not Started
W17 | Friday | Vaishali | 11:00 AM | PAGE | Page: AI Training Torrance | 2.0 |  | Not Started
W17 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Featured snippet optimization | 1.5 |  | Not Started
W17 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W17 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W17 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W17 | Friday | Puneet | 1:00 PM | NEWS | News: Fortinet Vulnerability Alert | 1.5 |  | Not Started
W17 | Friday | Puneet | 1:30 PM | PAGE | Page: Endpoint Security Santa Ana | 2.0 |  | Not Started
W17 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Featured snippet optimization | 1.5 |  | Not Started
W17 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W17 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W17 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W17 | Friday | Mohit | 1:00 PM | NEWS | News: Silicon Beach Dev | 1.5 |  | Not Started
W17 | Friday | Mohit | 1:30 PM | PAGE | Page: CRM Development Culver City | 2.0 |  | Not Started
W17 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Featured snippet optimization | 1.5 |  | Not Started
W17 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W17 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W17 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W18 | Monday | Saroj | 10:30 AM | PAGE | Page: E-Commerce SEO Tustin | 2.0 |  | Not Started
W18 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Conversion optimization | 2.0 |  | Not Started
W18 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W18 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W18 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W18 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W18 | Monday | Vaishali | 10:30 AM | PAGE | Page: AI Penetration Testing Culver City | 2.0 |  | Not Started
W18 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Conversion optimization | 2.0 |  | Not Started
W18 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W18 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W18 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W18 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W18 | Monday | Puneet | 1:00 PM | BLOG | Blog: MFA: Protect Patient Data | 2.5 |  | Not Started
W18 | Monday | Puneet | 3:30 PM | PAGE | Page: Compliance IT Anaheim | 2.0 |  | Not Started
W18 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Conversion optimization | 1.5 |  | Not Started
W18 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W18 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W18 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W18 | Monday | Mohit | 1:00 PM | PAGE | Page: Mobile App Dev Downtown LA | 2.0 |  | Not Started
W18 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Conversion optimization | 2.0 |  | Not Started
W18 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W18 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W18 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W18 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W18 | Tuesday | Saroj | 10:30 AM | PAGE | Page: Schema Markup Services Culver City | 2.0 |  | Not Started
W18 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Conversion optimization | 2.0 |  | Not Started
W18 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W18 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W18 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W18 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W18 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: AI Data Analytics Santa Monica | 2.0 |  | Not Started
W18 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Conversion optimization | 2.0 |  | Not Started
W18 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W18 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W18 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W18 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W18 | Tuesday | Puneet | 1:00 PM | PAGE | Page: IT Consulting Costa Mesa | 2.0 |  | Not Started
W18 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Conversion optimization | 2.0 |  | Not Started
W18 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W18 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W18 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W18 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W18 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: Azure vs AWS SoCal Enterprise | 2.5 |  | Not Started
W18 | Tuesday | Mohit | 3:30 PM | PAGE | Page: API Development Torrance | 2.0 |  | Not Started
W18 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Conversion optimization | 1.5 |  | Not Started
W18 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W18 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W18 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W18 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: Fix Duplicate Content | 2.5 |  | Not Started
W18 | Wednesday | Saroj | 12:30 PM | PAGE | Page: Website Speed Optimization Irvine | 2.0 |  | Not Started
W18 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Conversion optimization | 1.5 |  | Not Started
W18 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W18 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W18 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W18 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: Digital Transformation Costa Mesa | 2.0 |  | Not Started
W18 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Conversion optimization | 2.0 |  | Not Started
W18 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W18 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W18 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W18 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W18 | Wednesday | Puneet | 1:00 PM | PAGE | Page: Server Management Long Beach | 2.0 |  | Not Started
W18 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Conversion optimization | 2.0 |  | Not Started
W18 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W18 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W18 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W18 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W18 | Wednesday | Mohit | 1:00 PM | PAGE | Page: Cloud App Development Costa Mesa | 2.0 |  | Not Started
W18 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Conversion optimization | 2.0 |  | Not Started
W18 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W18 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W18 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W18 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W18 | Thursday | Saroj | 10:30 AM | PAGE | Page: Social Media Marketing Newport Beach | 2.0 |  | Not Started
W18 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Conversion optimization | 2.0 |  | Not Started
W18 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W18 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W18 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W18 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W18 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: Gemini Business Use Cases | 2.5 |  | Not Started
W18 | Thursday | Vaishali | 12:30 PM | PAGE | Page: AI Process Automation Anaheim | 2.0 |  | Not Started
W18 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Conversion optimization | 1.5 |  | Not Started
W18 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W18 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W18 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W18 | Thursday | Puneet | 1:00 PM | PAGE | Page: Data Backup Solutions Downtown LA | 2.0 |  | Not Started
W18 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Conversion optimization | 2.0 |  | Not Started
W18 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W18 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W18 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W18 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W18 | Thursday | Mohit | 1:00 PM | PAGE | Page: DevOps Services Long Beach | 2.0 |  | Not Started
W18 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Conversion optimization | 2.0 |  | Not Started
W18 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W18 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W18 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W18 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W18 | Friday | Saroj | 10:30 AM | NEWS | News: CWV Threshold Changes | 1.5 |  | Not Started
W18 | Friday | Saroj | 11:00 AM | PAGE | Page: SEO Services Santa Ana | 2.0 |  | Not Started
W18 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Conversion optimization | 1.5 |  | Not Started
W18 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W18 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W18 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W18 | Friday | Vaishali | 10:30 AM | NEWS | News: Gartner AI Hype Cycle | 1.5 |  | Not Started
W18 | Friday | Vaishali | 11:00 AM | PAGE | Page: AI Consulting Long Beach | 2.0 |  | Not Started
W18 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Conversion optimization | 1.5 |  | Not Started
W18 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W18 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W18 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W18 | Friday | Puneet | 1:00 PM | NEWS | News: SEC Cyber Rules OC | 1.5 |  | Not Started
W18 | Friday | Puneet | 1:30 PM | PAGE | Page: Managed IT Services Torrance | 2.0 |  | Not Started
W18 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Conversion optimization | 1.5 |  | Not Started
W18 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W18 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W18 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W18 | Friday | Mohit | 1:00 PM | NEWS | News: MS Build 2026 | 1.5 |  | Not Started
W18 | Friday | Mohit | 1:30 PM | PAGE | Page: AI Software Development Anaheim | 2.0 |  | Not Started
W18 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Conversion optimization | 1.5 |  | Not Started
W18 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W18 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W18 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W19 | Monday | Saroj | 10:30 AM | PAGE | Page: Local SEO Downtown LA | 2.0 |  | Not Started
W19 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Topical authority expansion content | 2.0 |  | Not Started
W19 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W19 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W19 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W19 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W19 | Monday | Vaishali | 10:30 AM | PAGE | Page: Copilot Implementation Newport Beach | 2.0 |  | Not Started
W19 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Topical authority expansion content | 2.0 |  | Not Started
W19 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W19 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W19 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W19 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W19 | Monday | Puneet | 1:00 PM | BLOG | Blog: Downtime Costs OC $10K+/Hour | 2.5 |  | Not Started
W19 | Monday | Puneet | 3:30 PM | PAGE | Page: HIPAA IT Support Tustin | 2.0 |  | Not Started
W19 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Topical authority expansion content | 1.5 |  | Not Started
W19 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W19 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W19 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W19 | Monday | Mohit | 1:00 PM | PAGE | Page: Custom App Development Newport Beach | 2.0 |  | Not Started
W19 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Topical authority expansion content | 2.0 |  | Not Started
W19 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W19 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W19 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W19 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W19 | Tuesday | Saroj | 10:30 AM | PAGE | Page: Technical SEO Torrance | 2.0 |  | Not Started
W19 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Topical authority expansion content | 2.0 |  | Not Started
W19 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W19 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W19 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W19 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W19 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: Gemini Integration Tustin | 2.0 |  | Not Started
W19 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Topical authority expansion content | 2.0 |  | Not Started
W19 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W19 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W19 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W19 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W19 | Tuesday | Puneet | 1:00 PM | PAGE | Page: 24/7 IT Helpdesk Culver City | 2.0 |  | Not Started
W19 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Topical authority expansion content | 2.0 |  | Not Started
W19 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W19 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W19 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W19 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W19 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: AI Agents Supply Chain | 2.5 |  | Not Started
W19 | Tuesday | Mohit | 3:30 PM | PAGE | Page: Enterprise Web Apps Tustin | 2.0 |  | Not Started
W19 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Topical authority expansion content | 1.5 |  | Not Started
W19 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W19 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W19 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W19 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: SEO for OC HVAC | 2.5 |  | Not Started
W19 | Wednesday | Saroj | 12:30 PM | PAGE | Page: Answer Engine Optimization Santa Monica | 2.0 |  | Not Started
W19 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Topical authority expansion content | 1.5 |  | Not Started
W19 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W19 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W19 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W19 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: Enterprise AI Strategy Santa Ana | 2.0 |  | Not Started
W19 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Topical authority expansion content | 2.0 |  | Not Started
W19 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W19 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W19 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W19 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W19 | Wednesday | Puneet | 1:00 PM | PAGE | Page: Cybersecurity Services Santa Monica | 2.0 |  | Not Started
W19 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Topical authority expansion content | 2.0 |  | Not Started
W19 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W19 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W19 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W19 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W19 | Wednesday | Mohit | 1:00 PM | PAGE | Page: .NET Development Santa Ana | 2.0 |  | Not Started
W19 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Topical authority expansion content | 2.0 |  | Not Started
W19 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W19 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W19 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W19 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W19 | Thursday | Saroj | 10:30 AM | PAGE | Page: Google Ads Management Costa Mesa | 2.0 |  | Not Started
W19 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Topical authority expansion content | 2.0 |  | Not Started
W19 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W19 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W19 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W19 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W19 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: AI Predictive Maintenance OC | 2.5 |  | Not Started
W19 | Thursday | Vaishali | 12:30 PM | PAGE | Page: AI Security Consulting Irvine | 2.0 |  | Not Started
W19 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Topical authority expansion content | 1.5 |  | Not Started
W19 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W19 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W19 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W19 | Thursday | Puneet | 1:00 PM | PAGE | Page: Cloud Migration Irvine | 2.0 |  | Not Started
W19 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Topical authority expansion content | 2.0 |  | Not Started
W19 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W19 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W19 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W19 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W19 | Thursday | Mohit | 1:00 PM | PAGE | Page: React Development Irvine | 2.0 |  | Not Started
W19 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Topical authority expansion content | 2.0 |  | Not Started
W19 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W19 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W19 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W19 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W19 | Friday | Saroj | 10:30 AM | NEWS | News: Google Reviews Crackdown | 1.5 |  | Not Started
W19 | Friday | Saroj | 11:00 AM | PAGE | Page: Content Marketing Anaheim | 2.0 |  | Not Started
W19 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Topical authority expansion content | 1.5 |  | Not Started
W19 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W19 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W19 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W19 | Friday | Vaishali | 10:30 AM | NEWS | News: OC CIO AI Survey | 1.5 |  | Not Started
W19 | Friday | Vaishali | 11:00 AM | PAGE | Page: AI Automation Services Downtown LA | 2.0 |  | Not Started
W19 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Topical authority expansion content | 1.5 |  | Not Started
W19 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W19 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W19 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W19 | Friday | Puneet | 1:00 PM | NEWS | News: Workspace Healthcare Security | 1.5 |  | Not Started
W19 | Friday | Puneet | 1:30 PM | PAGE | Page: IT Disaster Recovery Newport Beach | 2.0 |  | Not Started
W19 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Topical authority expansion content | 1.5 |  | Not Started
W19 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W19 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W19 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W19 | Friday | Mohit | 1:00 PM | NEWS | News: AI Coding Benchmarks | 1.5 |  | Not Started
W19 | Friday | Mohit | 1:30 PM | PAGE | Page: SaaS Development Santa Monica | 2.0 |  | Not Started
W19 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Topical authority expansion content | 1.5 |  | Not Started
W19 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W19 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W19 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W20 | Monday | Saroj | 10:30 AM | PAGE | Page: Link Building Long Beach | 2.0 |  | Not Started
W20 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: High-quality backlink partnerships | 2.0 |  | Not Started
W20 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W20 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W20 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W20 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W20 | Monday | Vaishali | 10:30 AM | PAGE | Page: Power BI AI Integration Torrance | 2.0 |  | Not Started
W20 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: High-quality backlink partnerships | 2.0 |  | Not Started
W20 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W20 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W20 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W20 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W20 | Monday | Puneet | 1:00 PM | BLOG | Blog: PCI Compliance for OC Retail | 2.5 |  | Not Started
W20 | Monday | Puneet | 3:30 PM | PAGE | Page: Network Monitoring Santa Ana | 2.0 |  | Not Started
W20 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: High-quality backlink partnerships | 1.5 |  | Not Started
W20 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W20 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W20 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W20 | Monday | Mohit | 1:00 PM | PAGE | Page: AI Agent Development Culver City | 2.0 |  | Not Started
W20 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: High-quality backlink partnerships | 2.0 |  | Not Started
W20 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W20 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W20 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W20 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W20 | Tuesday | Saroj | 10:30 AM | PAGE | Page: SEO Audit Tustin | 2.0 |  | Not Started
W20 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: High-quality backlink partnerships | 2.0 |  | Not Started
W20 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W20 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W20 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W20 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W20 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: AI Training Culver City | 2.0 |  | Not Started
W20 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: High-quality backlink partnerships | 2.0 |  | Not Started
W20 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W20 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W20 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W20 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W20 | Tuesday | Puneet | 1:00 PM | PAGE | Page: Endpoint Security Anaheim | 2.0 |  | Not Started
W20 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: High-quality backlink partnerships | 2.0 |  | Not Started
W20 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W20 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W20 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W20 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W20 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: Real-Time Dashboard 2026 | 2.5 |  | Not Started
W20 | Tuesday | Mohit | 3:30 PM | PAGE | Page: CRM Development Downtown LA | 2.0 |  | Not Started
W20 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: High-quality backlink partnerships | 1.5 |  | Not Started
W20 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W20 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W20 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W20 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: ChatGPT Recommends Businesses | 2.5 |  | Not Started
W20 | Wednesday | Saroj | 12:30 PM | PAGE | Page: E-Commerce SEO Culver City | 2.0 |  | Not Started
W20 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: High-quality backlink partnerships | 1.5 |  | Not Started
W20 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W20 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W20 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W20 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: AI Penetration Testing Santa Monica | 2.0 |  | Not Started
W20 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: High-quality backlink partnerships | 2.0 |  | Not Started
W20 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W20 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W20 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W20 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W20 | Wednesday | Puneet | 1:00 PM | PAGE | Page: Compliance IT Costa Mesa | 2.0 |  | Not Started
W20 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: High-quality backlink partnerships | 2.0 |  | Not Started
W20 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W20 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W20 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W20 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W20 | Wednesday | Mohit | 1:00 PM | PAGE | Page: Mobile App Dev Torrance | 2.0 |  | Not Started
W20 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: High-quality backlink partnerships | 2.0 |  | Not Started
W20 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W20 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W20 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W20 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W20 | Thursday | Saroj | 10:30 AM | PAGE | Page: Schema Markup Services Irvine | 2.0 |  | Not Started
W20 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: High-quality backlink partnerships | 2.0 |  | Not Started
W20 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W20 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W20 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W20 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W20 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: Choose AI Consulting Partner | 2.5 |  | Not Started
W20 | Thursday | Vaishali | 12:30 PM | PAGE | Page: AI Data Analytics Costa Mesa | 2.0 |  | Not Started
W20 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: High-quality backlink partnerships | 1.5 |  | Not Started
W20 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W20 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W20 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W20 | Thursday | Puneet | 1:00 PM | PAGE | Page: IT Consulting Long Beach | 2.0 |  | Not Started
W20 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: High-quality backlink partnerships | 2.0 |  | Not Started
W20 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W20 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W20 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W20 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W20 | Thursday | Mohit | 1:00 PM | PAGE | Page: API Development Costa Mesa | 2.0 |  | Not Started
W20 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: High-quality backlink partnerships | 2.0 |  | Not Started
W20 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W20 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W20 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W20 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W20 | Friday | Saroj | 10:30 AM | NEWS | News: AI Content Detection | 1.5 |  | Not Started
W20 | Friday | Saroj | 11:00 AM | PAGE | Page: Website Speed Optimization Newport Beach | 2.0 |  | Not Started
W20 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: High-quality backlink partnerships | 1.5 |  | Not Started
W20 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W20 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W20 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W20 | Friday | Vaishali | 10:30 AM | NEWS | News: Fabric AI Analytics | 1.5 |  | Not Started
W20 | Friday | Vaishali | 11:00 AM | PAGE | Page: Digital Transformation Anaheim | 2.0 |  | Not Started
W20 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: High-quality backlink partnerships | 1.5 |  | Not Started
W20 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W20 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W20 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W20 | Friday | Puneet | 1:00 PM | NEWS | News: Phishing 300% Surge OC | 1.5 |  | Not Started
W20 | Friday | Puneet | 1:30 PM | PAGE | Page: Server Management Downtown LA | 2.0 |  | Not Started
W20 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: High-quality backlink partnerships | 1.5 |  | Not Started
W20 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W20 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W20 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W20 | Friday | Mohit | 1:00 PM | NEWS | News: SoCal DX Stories | 1.5 |  | Not Started
W20 | Friday | Mohit | 1:30 PM | PAGE | Page: Cloud App Development Long Beach | 2.0 |  | Not Started
W20 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: High-quality backlink partnerships | 1.5 |  | Not Started
W20 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W20 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W20 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W21 | Monday | Saroj | 10:30 AM | PAGE | Page: Social Media Marketing Santa Ana | 2.0 |  | Not Started
W21 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Brand search optimization | 2.0 |  | Not Started
W21 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W21 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W21 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W21 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W21 | Monday | Vaishali | 10:30 AM | PAGE | Page: AI Process Automation Long Beach | 2.0 |  | Not Started
W21 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Brand search optimization | 2.0 |  | Not Started
W21 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W21 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W21 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W21 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W21 | Monday | Puneet | 1:00 PM | BLOG | Blog: Remote Work Security OC Healthcare | 2.5 |  | Not Started
W21 | Monday | Puneet | 3:30 PM | PAGE | Page: Data Backup Solutions Torrance | 2.0 |  | Not Started
W21 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Brand search optimization | 1.5 |  | Not Started
W21 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W21 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W21 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W21 | Monday | Mohit | 1:00 PM | PAGE | Page: DevOps Services Anaheim | 2.0 |  | Not Started
W21 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Brand search optimization | 2.0 |  | Not Started
W21 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W21 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W21 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W21 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W21 | Tuesday | Saroj | 10:30 AM | PAGE | Page: SEO Services Downtown LA | 2.0 |  | Not Started
W21 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Brand search optimization | 2.0 |  | Not Started
W21 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W21 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W21 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W21 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W21 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: AI Consulting Newport Beach | 2.0 |  | Not Started
W21 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Brand search optimization | 2.0 |  | Not Started
W21 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W21 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W21 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W21 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W21 | Tuesday | Puneet | 1:00 PM | PAGE | Page: Managed IT Services Tustin | 2.0 |  | Not Started
W21 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Brand search optimization | 2.0 |  | Not Started
W21 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W21 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W21 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W21 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W21 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: Evaluate Software Dev Partner | 2.5 |  | Not Started
W21 | Tuesday | Mohit | 3:30 PM | PAGE | Page: AI Software Development Newport Beach | 2.0 |  | Not Started
W21 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Brand search optimization | 1.5 |  | Not Started
W21 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W21 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W21 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W21 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: Content ROI Measure SEO 2026 | 2.5 |  | Not Started
W21 | Wednesday | Saroj | 12:30 PM | PAGE | Page: Local SEO Torrance | 2.0 |  | Not Started
W21 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Brand search optimization | 1.5 |  | Not Started
W21 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W21 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W21 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W21 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: Copilot Implementation Tustin | 2.0 |  | Not Started
W21 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Brand search optimization | 2.0 |  | Not Started
W21 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W21 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W21 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W21 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W21 | Wednesday | Puneet | 1:00 PM | PAGE | Page: HIPAA IT Support Culver City | 2.0 |  | Not Started
W21 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Brand search optimization | 2.0 |  | Not Started
W21 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W21 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W21 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W21 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W21 | Wednesday | Mohit | 1:00 PM | PAGE | Page: Custom App Development Tustin | 2.0 |  | Not Started
W21 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Brand search optimization | 2.0 |  | Not Started
W21 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W21 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W21 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W21 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W21 | Thursday | Saroj | 10:30 AM | PAGE | Page: Technical SEO Santa Monica | 2.0 |  | Not Started
W21 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Brand search optimization | 2.0 |  | Not Started
W21 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W21 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W21 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W21 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W21 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: AI Financial Compliance | 2.5 |  | Not Started
W21 | Thursday | Vaishali | 12:30 PM | PAGE | Page: Gemini Integration Santa Ana | 2.0 |  | Not Started
W21 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Brand search optimization | 1.5 |  | Not Started
W21 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W21 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W21 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W21 | Thursday | Puneet | 1:00 PM | PAGE | Page: 24/7 IT Helpdesk Santa Monica | 2.0 |  | Not Started
W21 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Brand search optimization | 2.0 |  | Not Started
W21 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W21 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W21 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W21 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W21 | Thursday | Mohit | 1:00 PM | PAGE | Page: Enterprise Web Apps Santa Ana | 2.0 |  | Not Started
W21 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Brand search optimization | 2.0 |  | Not Started
W21 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W21 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W21 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W21 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W21 | Friday | Saroj | 10:30 AM | NEWS | News: SEMrush vs Ahrefs 2026 | 1.5 |  | Not Started
W21 | Friday | Saroj | 11:00 AM | PAGE | Page: Answer Engine Optimization Costa Mesa | 2.0 |  | Not Started
W21 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Brand search optimization | 1.5 |  | Not Started
W21 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W21 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W21 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W21 | Friday | Vaishali | 10:30 AM | NEWS | News: AI Pen Test Tools | 1.5 |  | Not Started
W21 | Friday | Vaishali | 11:00 AM | PAGE | Page: Enterprise AI Strategy Irvine | 2.0 |  | Not Started
W21 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Brand search optimization | 1.5 |  | Not Started
W21 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W21 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W21 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W21 | Friday | Puneet | 1:00 PM | NEWS | News: CA AG Privacy Standards | 1.5 |  | Not Started
W21 | Friday | Puneet | 1:30 PM | PAGE | Page: Cybersecurity Services Irvine | 2.0 |  | Not Started
W21 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Brand search optimization | 1.5 |  | Not Started
W21 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W21 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W21 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W21 | Friday | Mohit | 1:00 PM | NEWS | News: PostgreSQL vs MongoDB | 1.5 |  | Not Started
W21 | Friday | Mohit | 1:30 PM | PAGE | Page: .NET Development Irvine | 2.0 |  | Not Started
W21 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Brand search optimization | 1.5 |  | Not Started
W21 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W21 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W21 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W22 | Monday | Saroj | 10:30 AM | PAGE | Page: Google Ads Management Anaheim | 2.0 |  | Not Started
W22 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: AI search optimization (LLM visibility) | 2.0 |  | Not Started
W22 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W22 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W22 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W22 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W22 | Monday | Vaishali | 10:30 AM | PAGE | Page: AI Security Consulting Downtown LA | 2.0 |  | Not Started
W22 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: AI search optimization (LLM visibility) | 2.0 |  | Not Started
W22 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W22 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W22 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W22 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W22 | Monday | Puneet | 1:00 PM | BLOG | Blog: Phishing Prevention OC Medical | 2.5 |  | Not Started
W22 | Monday | Puneet | 3:30 PM | PAGE | Page: Cloud Migration Newport Beach | 2.0 |  | Not Started
W22 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: AI search optimization (LLM visibility) | 1.5 |  | Not Started
W22 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W22 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W22 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W22 | Monday | Mohit | 1:00 PM | PAGE | Page: React Development Santa Monica | 2.0 |  | Not Started
W22 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: AI search optimization (LLM visibility) | 2.0 |  | Not Started
W22 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W22 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W22 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W22 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W22 | Tuesday | Saroj | 10:30 AM | PAGE | Page: Content Marketing Long Beach | 2.0 |  | Not Started
W22 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: AI search optimization (LLM visibility) | 2.0 |  | Not Started
W22 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W22 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W22 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W22 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W22 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: AI Automation Services Torrance | 2.0 |  | Not Started
W22 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: AI search optimization (LLM visibility) | 2.0 |  | Not Started
W22 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W22 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W22 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W22 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W22 | Tuesday | Puneet | 1:00 PM | PAGE | Page: IT Disaster Recovery Santa Ana | 2.0 |  | Not Started
W22 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: AI search optimization (LLM visibility) | 2.0 |  | Not Started
W22 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W22 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W22 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W22 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W22 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: PWA vs Native OC Business | 2.5 |  | Not Started
W22 | Tuesday | Mohit | 3:30 PM | PAGE | Page: SaaS Development Culver City | 2.0 |  | Not Started
W22 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: AI search optimization (LLM visibility) | 1.5 |  | Not Started
W22 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W22 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W22 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W22 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: Optimize Perplexity & Gemini | 2.5 |  | Not Started
W22 | Wednesday | Saroj | 12:30 PM | PAGE | Page: Link Building Tustin | 2.0 |  | Not Started
W22 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: AI search optimization (LLM visibility) | 1.5 |  | Not Started
W22 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W22 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W22 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W22 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: Power BI AI Integration Culver City | 2.0 |  | Not Started
W22 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: AI search optimization (LLM visibility) | 2.0 |  | Not Started
W22 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W22 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W22 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W22 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W22 | Wednesday | Puneet | 1:00 PM | PAGE | Page: Network Monitoring Anaheim | 2.0 |  | Not Started
W22 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: AI search optimization (LLM visibility) | 2.0 |  | Not Started
W22 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W22 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W22 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W22 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W22 | Wednesday | Mohit | 1:00 PM | PAGE | Page: AI Agent Development Downtown LA | 2.0 |  | Not Started
W22 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: AI search optimization (LLM visibility) | 2.0 |  | Not Started
W22 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W22 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W22 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W22 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W22 | Thursday | Saroj | 10:30 AM | PAGE | Page: SEO Audit Culver City | 2.0 |  | Not Started
W22 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: AI search optimization (LLM visibility) | 2.0 |  | Not Started
W22 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W22 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W22 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W22 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W22 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: Prompt Engineering Teams | 2.5 |  | Not Started
W22 | Thursday | Vaishali | 12:30 PM | PAGE | Page: AI Training Santa Monica | 2.0 |  | Not Started
W22 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: AI search optimization (LLM visibility) | 1.5 |  | Not Started
W22 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W22 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W22 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W22 | Thursday | Puneet | 1:00 PM | PAGE | Page: Endpoint Security Costa Mesa | 2.0 |  | Not Started
W22 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: AI search optimization (LLM visibility) | 2.0 |  | Not Started
W22 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W22 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W22 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W22 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W22 | Thursday | Mohit | 1:00 PM | PAGE | Page: CRM Development Torrance | 2.0 |  | Not Started
W22 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: AI search optimization (LLM visibility) | 2.0 |  | Not Started
W22 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W22 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W22 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W22 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W22 | Friday | Saroj | 10:30 AM | NEWS | News: OC Marketing Survey | 1.5 |  | Not Started
W22 | Friday | Saroj | 11:00 AM | PAGE | Page: E-Commerce SEO Irvine | 2.0 |  | Not Started
W22 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: AI search optimization (LLM visibility) | 1.5 |  | Not Started
W22 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W22 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W22 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W22 | Friday | Vaishali | 10:30 AM | NEWS | News: SoCal AI Startups | 1.5 |  | Not Started
W22 | Friday | Vaishali | 11:00 AM | PAGE | Page: AI Penetration Testing Costa Mesa | 2.0 |  | Not Started
W22 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: AI search optimization (LLM visibility) | 1.5 |  | Not Started
W22 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W22 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W22 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W22 | Friday | Puneet | 1:00 PM | NEWS | News: EMR Vulnerability Alert | 1.5 |  | Not Started
W22 | Friday | Puneet | 1:30 PM | PAGE | Page: Compliance IT Long Beach | 2.0 |  | Not Started
W22 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: AI search optimization (LLM visibility) | 1.5 |  | Not Started
W22 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W22 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W22 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W22 | Friday | Mohit | 1:00 PM | NEWS | News: Irvine Tech Launches | 1.5 |  | Not Started
W22 | Friday | Mohit | 1:30 PM | PAGE | Page: Mobile App Dev Costa Mesa | 2.0 |  | Not Started
W22 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: AI search optimization (LLM visibility) | 1.5 |  | Not Started
W22 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W22 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W22 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W23 | Monday | Saroj | 10:30 AM | PAGE | Page: Schema Markup Services Newport Beach | 2.0 |  | Not Started
W23 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Performance audit + ranking analysis | 2.0 |  | Not Started
W23 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W23 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W23 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W23 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W23 | Monday | Vaishali | 10:30 AM | PAGE | Page: AI Data Analytics Anaheim | 2.0 |  | Not Started
W23 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Performance audit + ranking analysis | 2.0 |  | Not Started
W23 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W23 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W23 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W23 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W23 | Monday | Puneet | 1:00 PM | BLOG | Blog: IT SLA: OC Response Times | 2.5 |  | Not Started
W23 | Monday | Puneet | 3:30 PM | PAGE | Page: IT Consulting Downtown LA | 2.0 |  | Not Started
W23 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Performance audit + ranking analysis | 1.5 |  | Not Started
W23 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W23 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W23 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W23 | Monday | Mohit | 1:00 PM | PAGE | Page: API Development Long Beach | 2.0 |  | Not Started
W23 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Performance audit + ranking analysis | 2.0 |  | Not Started
W23 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W23 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W23 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W23 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W23 | Tuesday | Saroj | 10:30 AM | PAGE | Page: Website Speed Optimization Santa Ana | 2.0 |  | Not Started
W23 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Performance audit + ranking analysis | 2.0 |  | Not Started
W23 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W23 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W23 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W23 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W23 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: Digital Transformation Long Beach | 2.0 |  | Not Started
W23 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Performance audit + ranking analysis | 2.0 |  | Not Started
W23 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W23 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W23 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W23 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W23 | Tuesday | Puneet | 1:00 PM | PAGE | Page: Server Management Torrance | 2.0 |  | Not Started
W23 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Performance audit + ranking analysis | 2.0 |  | Not Started
W23 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W23 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W23 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W23 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W23 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: Database Architecture Decisions | 2.5 |  | Not Started
W23 | Tuesday | Mohit | 3:30 PM | PAGE | Page: Cloud App Development Anaheim | 2.0 |  | Not Started
W23 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Performance audit + ranking analysis | 1.5 |  | Not Started
W23 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W23 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W23 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W23 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: SEO Costa Mesa Dental | 2.5 |  | Not Started
W23 | Wednesday | Saroj | 12:30 PM | PAGE | Page: Social Media Marketing Downtown LA | 2.0 |  | Not Started
W23 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Performance audit + ranking analysis | 1.5 |  | Not Started
W23 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W23 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W23 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W23 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: AI Process Automation Newport Beach | 2.0 |  | Not Started
W23 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Performance audit + ranking analysis | 2.0 |  | Not Started
W23 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W23 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W23 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W23 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W23 | Wednesday | Puneet | 1:00 PM | PAGE | Page: Data Backup Solutions Tustin | 2.0 |  | Not Started
W23 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Performance audit + ranking analysis | 2.0 |  | Not Started
W23 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W23 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W23 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W23 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W23 | Wednesday | Mohit | 1:00 PM | PAGE | Page: DevOps Services Newport Beach | 2.0 |  | Not Started
W23 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Performance audit + ranking analysis | 2.0 |  | Not Started
W23 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W23 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W23 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W23 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W23 | Thursday | Saroj | 10:30 AM | PAGE | Page: SEO Services Torrance | 2.0 |  | Not Started
W23 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Performance audit + ranking analysis | 2.0 |  | Not Started
W23 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W23 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W23 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W23 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W23 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: AI Changes PM 2026 | 2.5 |  | Not Started
W23 | Thursday | Vaishali | 12:30 PM | PAGE | Page: AI Consulting Tustin | 2.0 |  | Not Started
W23 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Performance audit + ranking analysis | 1.5 |  | Not Started
W23 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W23 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W23 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W23 | Thursday | Puneet | 1:00 PM | PAGE | Page: Managed IT Services Culver City | 2.0 |  | Not Started
W23 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Performance audit + ranking analysis | 2.0 |  | Not Started
W23 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W23 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W23 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W23 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W23 | Thursday | Mohit | 1:00 PM | PAGE | Page: AI Software Development Tustin | 2.0 |  | Not Started
W23 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Performance audit + ranking analysis | 2.0 |  | Not Started
W23 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W23 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W23 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W23 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W23 | Friday | Saroj | 10:30 AM | NEWS | News: Facebook Meta SEO | 1.5 |  | Not Started
W23 | Friday | Saroj | 11:00 AM | PAGE | Page: Local SEO Santa Monica | 2.0 |  | Not Started
W23 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Performance audit + ranking analysis | 1.5 |  | Not Started
W23 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W23 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W23 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W23 | Friday | Vaishali | 10:30 AM | NEWS | News: ChatGPT vs Copilot | 1.5 |  | Not Started
W23 | Friday | Vaishali | 11:00 AM | PAGE | Page: Copilot Implementation Santa Ana | 2.0 |  | Not Started
W23 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Performance audit + ranking analysis | 1.5 |  | Not Started
W23 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W23 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W23 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W23 | Friday | Puneet | 1:00 PM | NEWS | News: SoCal IT Security Predictions | 1.5 |  | Not Started
W23 | Friday | Puneet | 1:30 PM | PAGE | Page: HIPAA IT Support Santa Monica | 2.0 |  | Not Started
W23 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Performance audit + ranking analysis | 1.5 |  | Not Started
W23 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W23 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W23 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W23 | Friday | Mohit | 1:00 PM | NEWS | News: OWASP 2026 | 1.5 |  | Not Started
W23 | Friday | Mohit | 1:30 PM | PAGE | Page: Custom App Development Santa Ana | 2.0 |  | Not Started
W23 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Performance audit + ranking analysis | 1.5 |  | Not Started
W23 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W23 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W23 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W24 | Monday | Saroj | 10:30 AM | PAGE | Page: Technical SEO Costa Mesa | 2.0 |  | Not Started
W24 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Content pruning (remove weak pages) | 2.0 |  | Not Started
W24 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W24 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W24 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W24 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W24 | Monday | Vaishali | 10:30 AM | PAGE | Page: Gemini Integration Irvine | 2.0 |  | Not Started
W24 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Content pruning (remove weak pages) | 2.0 |  | Not Started
W24 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W24 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W24 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W24 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W24 | Monday | Puneet | 1:00 PM | BLOG | Blog: M365 Security for HIPAA | 2.5 |  | Not Started
W24 | Monday | Puneet | 3:30 PM | PAGE | Page: 24/7 IT Helpdesk Irvine | 2.0 |  | Not Started
W24 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Content pruning (remove weak pages) | 1.5 |  | Not Started
W24 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W24 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W24 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W24 | Monday | Mohit | 1:00 PM | PAGE | Page: Enterprise Web Apps Irvine | 2.0 |  | Not Started
W24 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Content pruning (remove weak pages) | 2.0 |  | Not Started
W24 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W24 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W24 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W24 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W24 | Tuesday | Saroj | 10:30 AM | PAGE | Page: Answer Engine Optimization Anaheim | 2.0 |  | Not Started
W24 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Content pruning (remove weak pages) | 2.0 |  | Not Started
W24 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W24 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W24 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W24 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W24 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: Enterprise AI Strategy Downtown LA | 2.0 |  | Not Started
W24 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Content pruning (remove weak pages) | 2.0 |  | Not Started
W24 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W24 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W24 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W24 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W24 | Tuesday | Puneet | 1:00 PM | PAGE | Page: Cybersecurity Services Newport Beach | 2.0 |  | Not Started
W24 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Content pruning (remove weak pages) | 2.0 |  | Not Started
W24 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W24 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W24 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W24 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W24 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: Irvine Logistics AI | 2.5 |  | Not Started
W24 | Tuesday | Mohit | 3:30 PM | PAGE | Page: .NET Development Santa Monica | 2.0 |  | Not Started
W24 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Content pruning (remove weak pages) | 1.5 |  | Not Started
W24 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W24 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W24 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W24 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: Mobile-First OC Ready? | 2.5 |  | Not Started
W24 | Wednesday | Saroj | 12:30 PM | PAGE | Page: Google Ads Management Long Beach | 2.0 |  | Not Started
W24 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Content pruning (remove weak pages) | 1.5 |  | Not Started
W24 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W24 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W24 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W24 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: AI Security Consulting Torrance | 2.0 |  | Not Started
W24 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Content pruning (remove weak pages) | 2.0 |  | Not Started
W24 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W24 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W24 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W24 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W24 | Wednesday | Puneet | 1:00 PM | PAGE | Page: Cloud Migration Santa Ana | 2.0 |  | Not Started
W24 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Content pruning (remove weak pages) | 2.0 |  | Not Started
W24 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W24 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W24 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W24 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W24 | Wednesday | Mohit | 1:00 PM | PAGE | Page: React Development Culver City | 2.0 |  | Not Started
W24 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Content pruning (remove weak pages) | 2.0 |  | Not Started
W24 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W24 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W24 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W24 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W24 | Thursday | Saroj | 10:30 AM | PAGE | Page: Content Marketing Tustin | 2.0 |  | Not Started
W24 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Content pruning (remove weak pages) | 2.0 |  | Not Started
W24 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W24 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W24 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W24 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W24 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: AI Legacy Integration | 2.5 |  | Not Started
W24 | Thursday | Vaishali | 12:30 PM | PAGE | Page: AI Automation Services Culver City | 2.0 |  | Not Started
W24 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Content pruning (remove weak pages) | 1.5 |  | Not Started
W24 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W24 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W24 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W24 | Thursday | Puneet | 1:00 PM | PAGE | Page: IT Disaster Recovery Anaheim | 2.0 |  | Not Started
W24 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Content pruning (remove weak pages) | 2.0 |  | Not Started
W24 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W24 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W24 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W24 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W24 | Thursday | Mohit | 1:00 PM | PAGE | Page: SaaS Development Downtown LA | 2.0 |  | Not Started
W24 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Content pruning (remove weak pages) | 2.0 |  | Not Started
W24 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W24 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W24 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W24 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W24 | Friday | Saroj | 10:30 AM | NEWS | News: Search Console 2026 | 1.5 |  | Not Started
W24 | Friday | Saroj | 11:00 AM | PAGE | Page: Link Building Culver City | 2.0 |  | Not Started
W24 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Content pruning (remove weak pages) | 1.5 |  | Not Started
W24 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W24 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W24 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W24 | Friday | Vaishali | 10:30 AM | NEWS | News: AI Supply Chain | 1.5 |  | Not Started
W24 | Friday | Vaishali | 11:00 AM | PAGE | Page: Power BI AI Integration Santa Monica | 2.0 |  | Not Started
W24 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Content pruning (remove weak pages) | 1.5 |  | Not Started
W24 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W24 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W24 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W24 | Friday | Puneet | 1:00 PM | NEWS | News: FTC Safeguards OC | 1.5 |  | Not Started
W24 | Friday | Puneet | 1:30 PM | PAGE | Page: Network Monitoring Costa Mesa | 2.0 |  | Not Started
W24 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Content pruning (remove weak pages) | 1.5 |  | Not Started
W24 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W24 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W24 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W24 | Friday | Mohit | 1:00 PM | NEWS | News: OC Accelerators | 1.5 |  | Not Started
W24 | Friday | Mohit | 1:30 PM | PAGE | Page: AI Agent Development Torrance | 2.0 |  | Not Started
W24 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Content pruning (remove weak pages) | 1.5 |  | Not Started
W24 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W24 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W24 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W25 | Monday | Saroj | 10:30 AM | PAGE | Page: SEO Audit Irvine | 2.0 |  | Not Started
W25 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: ROI tracking + analytics review | 2.0 |  | Not Started
W25 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W25 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W25 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W25 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W25 | Monday | Vaishali | 10:30 AM | PAGE | Page: AI Training Costa Mesa | 2.0 |  | Not Started
W25 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: ROI tracking + analytics review | 2.0 |  | Not Started
W25 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W25 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W25 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W25 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W25 | Monday | Puneet | 1:00 PM | BLOG | Blog: Securing OC Law Firm Data 2026 | 2.5 |  | Not Started
W25 | Monday | Puneet | 3:30 PM | PAGE | Page: Endpoint Security Long Beach | 2.0 |  | Not Started
W25 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: ROI tracking + analytics review | 1.5 |  | Not Started
W25 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W25 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W25 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W25 | Monday | Mohit | 1:00 PM | PAGE | Page: CRM Development Costa Mesa | 2.0 |  | Not Started
W25 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: ROI tracking + analytics review | 2.0 |  | Not Started
W25 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W25 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W25 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W25 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W25 | Tuesday | Saroj | 10:30 AM | PAGE | Page: E-Commerce SEO Newport Beach | 2.0 |  | Not Started
W25 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: ROI tracking + analytics review | 2.0 |  | Not Started
W25 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W25 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W25 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W25 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W25 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: AI Penetration Testing Anaheim | 2.0 |  | Not Started
W25 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: ROI tracking + analytics review | 2.0 |  | Not Started
W25 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W25 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W25 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W25 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W25 | Tuesday | Puneet | 1:00 PM | PAGE | Page: Compliance IT Downtown LA | 2.0 |  | Not Started
W25 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: ROI tracking + analytics review | 2.0 |  | Not Started
W25 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W25 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W25 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W25 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W25 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: Software IP Protection Guide | 2.5 |  | Not Started
W25 | Tuesday | Mohit | 3:30 PM | PAGE | Page: Mobile App Dev Long Beach | 2.0 |  | Not Started
W25 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: ROI tracking + analytics review | 1.5 |  | Not Started
W25 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W25 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W25 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W25 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: SEO Content That Converts | 2.5 |  | Not Started
W25 | Wednesday | Saroj | 12:30 PM | PAGE | Page: Schema Markup Services Santa Ana | 2.0 |  | Not Started
W25 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: ROI tracking + analytics review | 1.5 |  | Not Started
W25 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W25 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W25 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W25 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: AI Data Analytics Long Beach | 2.0 |  | Not Started
W25 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: ROI tracking + analytics review | 2.0 |  | Not Started
W25 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W25 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W25 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W25 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W25 | Wednesday | Puneet | 1:00 PM | PAGE | Page: IT Consulting Torrance | 2.0 |  | Not Started
W25 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: ROI tracking + analytics review | 2.0 |  | Not Started
W25 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W25 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W25 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W25 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W25 | Wednesday | Mohit | 1:00 PM | PAGE | Page: API Development Anaheim | 2.0 |  | Not Started
W25 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: ROI tracking + analytics review | 2.0 |  | Not Started
W25 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W25 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W25 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W25 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W25 | Thursday | Saroj | 10:30 AM | PAGE | Page: Website Speed Optimization Downtown LA | 2.0 |  | Not Started
W25 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: ROI tracking + analytics review | 2.0 |  | Not Started
W25 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W25 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W25 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W25 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W25 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: AI Tech Stack 2026 | 2.5 |  | Not Started
W25 | Thursday | Vaishali | 12:30 PM | PAGE | Page: Digital Transformation Newport Beach | 2.0 |  | Not Started
W25 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: ROI tracking + analytics review | 1.5 |  | Not Started
W25 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W25 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W25 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W25 | Thursday | Puneet | 1:00 PM | PAGE | Page: Server Management Tustin | 2.0 |  | Not Started
W25 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: ROI tracking + analytics review | 2.0 |  | Not Started
W25 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W25 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W25 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W25 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W25 | Thursday | Mohit | 1:00 PM | PAGE | Page: Cloud App Development Newport Beach | 2.0 |  | Not Started
W25 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: ROI tracking + analytics review | 2.0 |  | Not Started
W25 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W25 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W25 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W25 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W25 | Friday | Saroj | 10:30 AM | NEWS | News: Local Pack Testing | 1.5 |  | Not Started
W25 | Friday | Saroj | 11:00 AM | PAGE | Page: Social Media Marketing Torrance | 2.0 |  | Not Started
W25 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: ROI tracking + analytics review | 1.5 |  | Not Started
W25 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W25 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W25 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W25 | Friday | Vaishali | 10:30 AM | NEWS | News: OC Healthcare AI | 1.5 |  | Not Started
W25 | Friday | Vaishali | 11:00 AM | PAGE | Page: AI Process Automation Tustin | 2.0 |  | Not Started
W25 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: ROI tracking + analytics review | 1.5 |  | Not Started
W25 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W25 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W25 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W25 | Friday | Puneet | 1:00 PM | NEWS | News: Dental Ransomware OC | 1.5 |  | Not Started
W25 | Friday | Puneet | 1:30 PM | PAGE | Page: Data Backup Solutions Culver City | 2.0 |  | Not Started
W25 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: ROI tracking + analytics review | 1.5 |  | Not Started
W25 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W25 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W25 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W25 | Friday | Mohit | 1:00 PM | NEWS | News: Blazor .NET 9 | 1.5 |  | Not Started
W25 | Friday | Mohit | 1:30 PM | PAGE | Page: DevOps Services Tustin | 2.0 |  | Not Started
W25 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: ROI tracking + analytics review | 1.5 |  | Not Started
W25 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W25 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W25 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W26 | Monday | Saroj | 10:30 AM | PAGE | Page: SEO Services Santa Monica | 2.0 |  | Not Started
W26 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Next 6-month SEO strategy planning | 2.0 |  | Not Started
W26 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W26 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W26 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W26 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W26 | Monday | Vaishali | 10:30 AM | PAGE | Page: AI Consulting Santa Ana | 2.0 |  | Not Started
W26 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Next 6-month SEO strategy planning | 2.0 |  | Not Started
W26 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W26 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W26 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W26 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W26 | Monday | Puneet | 1:00 PM | BLOG | Blog: 24/7 Network Monitoring OC | 2.5 |  | Not Started
W26 | Monday | Puneet | 3:30 PM | PAGE | Page: Managed IT Services Santa Monica | 2.0 |  | Not Started
W26 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Next 6-month SEO strategy planning | 1.5 |  | Not Started
W26 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W26 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W26 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W26 | Monday | Mohit | 1:00 PM | PAGE | Page: AI Software Development Santa Ana | 2.0 |  | Not Started
W26 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Next 6-month SEO strategy planning | 2.0 |  | Not Started
W26 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W26 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W26 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W26 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W26 | Tuesday | Saroj | 10:30 AM | PAGE | Page: Local SEO Costa Mesa | 2.0 |  | Not Started
W26 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Next 6-month SEO strategy planning | 2.0 |  | Not Started
W26 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W26 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W26 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W26 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W26 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: Copilot Implementation Irvine | 2.0 |  | Not Started
W26 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Next 6-month SEO strategy planning | 2.0 |  | Not Started
W26 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W26 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W26 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W26 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W26 | Tuesday | Puneet | 1:00 PM | PAGE | Page: HIPAA IT Support Irvine | 2.0 |  | Not Started
W26 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Next 6-month SEO strategy planning | 2.0 |  | Not Started
W26 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W26 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W26 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W26 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W26 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: DevOps Scaling SaaS | 2.5 |  | Not Started
W26 | Tuesday | Mohit | 3:30 PM | PAGE | Page: Custom App Development Irvine | 2.0 |  | Not Started
W26 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Next 6-month SEO strategy planning | 1.5 |  | Not Started
W26 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W26 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W26 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W26 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: OC SEO Mistakes & Fixes | 2.5 |  | Not Started
W26 | Wednesday | Saroj | 12:30 PM | PAGE | Page: Technical SEO Anaheim | 2.0 |  | Not Started
W26 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Next 6-month SEO strategy planning | 1.5 |  | Not Started
W26 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W26 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W26 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W26 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: Gemini Integration Downtown LA | 2.0 |  | Not Started
W26 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Next 6-month SEO strategy planning | 2.0 |  | Not Started
W26 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W26 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W26 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W26 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W26 | Wednesday | Puneet | 1:00 PM | PAGE | Page: 24/7 IT Helpdesk Newport Beach | 2.0 |  | Not Started
W26 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Next 6-month SEO strategy planning | 2.0 |  | Not Started
W26 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W26 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W26 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W26 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W26 | Wednesday | Mohit | 1:00 PM | PAGE | Page: Enterprise Web Apps Santa Monica | 2.0 |  | Not Started
W26 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Next 6-month SEO strategy planning | 2.0 |  | Not Started
W26 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W26 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W26 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W26 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W26 | Thursday | Saroj | 10:30 AM | PAGE | Page: Answer Engine Optimization Long Beach | 2.0 |  | Not Started
W26 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Next 6-month SEO strategy planning | 2.0 |  | Not Started
W26 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W26 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W26 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W26 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W26 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: AI Sales Copilot Revenue | 2.5 |  | Not Started
W26 | Thursday | Vaishali | 12:30 PM | PAGE | Page: Enterprise AI Strategy Torrance | 2.0 |  | Not Started
W26 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Next 6-month SEO strategy planning | 1.5 |  | Not Started
W26 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W26 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W26 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W26 | Thursday | Puneet | 1:00 PM | PAGE | Page: Cybersecurity Services Santa Ana | 2.0 |  | Not Started
W26 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Next 6-month SEO strategy planning | 2.0 |  | Not Started
W26 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W26 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W26 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W26 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W26 | Thursday | Mohit | 1:00 PM | PAGE | Page: .NET Development Culver City | 2.0 |  | Not Started
W26 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Next 6-month SEO strategy planning | 2.0 |  | Not Started
W26 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W26 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W26 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W26 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W26 | Friday | Saroj | 10:30 AM | NEWS | News: E-E-A-T Authority | 1.5 |  | Not Started
W26 | Friday | Saroj | 11:00 AM | PAGE | Page: Google Ads Management Tustin | 2.0 |  | Not Started
W26 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Next 6-month SEO strategy planning | 1.5 |  | Not Started
W26 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W26 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W26 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W26 | Friday | Vaishali | 10:30 AM | NEWS | News: NVIDIA Enterprise GPUs | 1.5 |  | Not Started
W26 | Friday | Vaishali | 11:00 AM | PAGE | Page: AI Security Consulting Culver City | 2.0 |  | Not Started
W26 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Next 6-month SEO strategy planning | 1.5 |  | Not Started
W26 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W26 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W26 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W26 | Friday | Puneet | 1:00 PM | NEWS | News: M365 Outage Lessons | 1.5 |  | Not Started
W26 | Friday | Puneet | 1:30 PM | PAGE | Page: Cloud Migration Anaheim | 2.0 |  | Not Started
W26 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Next 6-month SEO strategy planning | 1.5 |  | Not Started
W26 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W26 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W26 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W26 | Friday | Mohit | 1:00 PM | NEWS | News: SoCal DevOps Highlights | 1.5 |  | Not Started
W26 | Friday | Mohit | 1:30 PM | PAGE | Page: React Development Downtown LA | 2.0 |  | Not Started
W26 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Next 6-month SEO strategy planning | 1.5 |  | Not Started
W26 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W26 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W26 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W27 | Monday | Saroj | 10:30 AM | PAGE | Page: Content Marketing Culver City | 2.0 |  | Not Started
W27 | Monday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Ongoing optimization | 2.0 |  | Not Started
W27 | Monday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W27 | Monday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W27 | Monday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W27 | Monday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W27 | Monday | Vaishali | 10:30 AM | PAGE | Page: AI Automation Services Santa Monica | 2.0 |  | Not Started
W27 | Monday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Ongoing optimization | 2.0 |  | Not Started
W27 | Monday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W27 | Monday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W27 | Monday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W27 | Monday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W27 | Monday | Puneet | 1:00 PM | BLOG | Blog: Data Encryption for OC Advisors | 2.5 |  | Not Started
W27 | Monday | Puneet | 3:30 PM | PAGE | Page: IT Disaster Recovery Costa Mesa | 2.0 |  | Not Started
W27 | Monday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Ongoing optimization | 1.5 |  | Not Started
W27 | Monday | Puneet | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W27 | Monday | Puneet | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W27 | Monday | Puneet | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W27 | Monday | Mohit | 1:00 PM | PAGE | Page: SaaS Development Torrance | 2.0 |  | Not Started
W27 | Monday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Ongoing optimization | 2.0 |  | Not Started
W27 | Monday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W27 | Monday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W27 | Monday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W27 | Monday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W27 | Tuesday | Saroj | 10:30 AM | PAGE | Page: Link Building Irvine | 2.0 |  | Not Started
W27 | Tuesday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Ongoing optimization | 2.0 |  | Not Started
W27 | Tuesday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W27 | Tuesday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W27 | Tuesday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W27 | Tuesday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W27 | Tuesday | Vaishali | 10:30 AM | PAGE | Page: Power BI AI Integration Costa Mesa | 2.0 |  | Not Started
W27 | Tuesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Ongoing optimization | 2.0 |  | Not Started
W27 | Tuesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W27 | Tuesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W27 | Tuesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W27 | Tuesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W27 | Tuesday | Puneet | 1:00 PM | PAGE | Page: Network Monitoring Long Beach | 2.0 |  | Not Started
W27 | Tuesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Ongoing optimization | 2.0 |  | Not Started
W27 | Tuesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W27 | Tuesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W27 | Tuesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W27 | Tuesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W27 | Tuesday | Mohit | 1:00 PM | BLOG | Blog: Headless CMS Enterprise | 2.5 |  | Not Started
W27 | Tuesday | Mohit | 3:30 PM | PAGE | Page: AI Agent Development Costa Mesa | 2.0 |  | Not Started
W27 | Tuesday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Ongoing optimization | 1.5 |  | Not Started
W27 | Tuesday | Mohit | 7:00 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W27 | Tuesday | Mohit | 8:30 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W27 | Tuesday | Mohit | 9:30 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W27 | Wednesday | Saroj | 10:30 AM | BLOG | Blog: Voice Search OC Business | 2.5 |  | Not Started
W27 | Wednesday | Saroj | 12:30 PM | PAGE | Page: SEO Audit Newport Beach | 2.0 |  | Not Started
W27 | Wednesday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Ongoing optimization | 1.5 |  | Not Started
W27 | Wednesday | Saroj | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W27 | Wednesday | Saroj | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W27 | Wednesday | Saroj | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W27 | Wednesday | Vaishali | 10:30 AM | PAGE | Page: AI Training Anaheim | 2.0 |  | Not Started
W27 | Wednesday | Vaishali | 11:00 AM | SEO PLAN | 180-Day: Ongoing optimization | 2.0 |  | Not Started
W27 | Wednesday | Vaishali | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W27 | Wednesday | Vaishali | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W27 | Wednesday | Vaishali | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W27 | Wednesday | Vaishali | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W27 | Wednesday | Puneet | 1:00 PM | PAGE | Page: Endpoint Security Downtown LA | 2.0 |  | Not Started
W27 | Wednesday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Ongoing optimization | 2.0 |  | Not Started
W27 | Wednesday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W27 | Wednesday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W27 | Wednesday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W27 | Wednesday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W27 | Wednesday | Mohit | 1:00 PM | PAGE | Page: CRM Development Long Beach | 2.0 |  | Not Started
W27 | Wednesday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Ongoing optimization | 2.0 |  | Not Started
W27 | Wednesday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W27 | Wednesday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W27 | Wednesday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W27 | Wednesday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W27 | Thursday | Saroj | 10:30 AM | PAGE | Page: E-Commerce SEO Santa Ana | 2.0 |  | Not Started
W27 | Thursday | Saroj | 11:00 AM | SEO PLAN | 180-Day: Ongoing optimization | 2.0 |  | Not Started
W27 | Thursday | Saroj | 2:00 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W27 | Thursday | Saroj | 3:30 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W27 | Thursday | Saroj | 5:00 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W27 | Thursday | Saroj | 6:00 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W27 | Thursday | Vaishali | 10:30 AM | BLOG | Blog: Train Team on AI | 2.5 |  | Not Started
W27 | Thursday | Vaishali | 12:30 PM | PAGE | Page: AI Penetration Testing Long Beach | 2.0 |  | Not Started
W27 | Thursday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Ongoing optimization | 1.5 |  | Not Started
W27 | Thursday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlinks | 1.0 |  | Not Started
W27 | Thursday | Vaishali | 5:00 PM | SEO TASK | GBP + social + competitor | 0.5 |  | Not Started
W27 | Thursday | Vaishali | 6:00 PM | SEO TASK | Content refresh old post | 0.5 |  | Not Started
W27 | Thursday | Puneet | 1:00 PM | PAGE | Page: Compliance IT Torrance | 2.0 |  | Not Started
W27 | Thursday | Puneet | 1:30 PM | SEO PLAN | 180-Day: Ongoing optimization | 2.0 |  | Not Started
W27 | Thursday | Puneet | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W27 | Thursday | Puneet | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W27 | Thursday | Puneet | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W27 | Thursday | Puneet | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W27 | Thursday | Mohit | 1:00 PM | PAGE | Page: Mobile App Dev Anaheim | 2.0 |  | Not Started
W27 | Thursday | Mohit | 1:30 PM | SEO PLAN | 180-Day: Ongoing optimization | 2.0 |  | Not Started
W27 | Thursday | Mohit | 5:30 PM | SEO TASK | Internal linking audit + fixes | 1.0 |  | Not Started
W27 | Thursday | Mohit | 7:00 PM | SEO TASK | Backlink outreach (2 partners) | 1.0 |  | Not Started
W27 | Thursday | Mohit | 8:30 PM | SEO TASK | Content refresh old post | 1.0 |  | Not Started
W27 | Thursday | Mohit | 9:30 PM | SEO TASK | GBP + social + competitor + schema | 1.0 |  | Not Started
W27 | Friday | Saroj | 10:30 AM | NEWS | News: AEO Ranking Research | 1.5 |  | Not Started
W27 | Friday | Saroj | 11:00 AM | PAGE | Page: Schema Markup Services Downtown LA | 2.0 |  | Not Started
W27 | Friday | Saroj | 2:00 PM | SEO PLAN | 180-Day: Ongoing optimization | 1.5 |  | Not Started
W27 | Friday | Saroj | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W27 | Friday | Saroj | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W27 | Friday | Saroj | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W27 | Friday | Vaishali | 10:30 AM | NEWS | News: AI Ethics IEEE 2026 | 1.5 |  | Not Started
W27 | Friday | Vaishali | 11:00 AM | PAGE | Page: AI Data Analytics Newport Beach | 2.0 |  | Not Started
W27 | Friday | Vaishali | 2:00 PM | SEO PLAN | 180-Day: Ongoing optimization | 1.5 |  | Not Started
W27 | Friday | Vaishali | 3:30 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W27 | Friday | Vaishali | 5:00 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W27 | Friday | Vaishali | 6:00 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W27 | Friday | Puneet | 1:00 PM | NEWS | News: NIST 2.0 SMBs | 1.5 |  | Not Started
W27 | Friday | Puneet | 1:30 PM | PAGE | Page: IT Consulting Tustin | 2.0 |  | Not Started
W27 | Friday | Puneet | 5:30 PM | SEO PLAN | 180-Day: Ongoing optimization | 1.5 |  | Not Started
W27 | Friday | Puneet | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W27 | Friday | Puneet | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W27 | Friday | Puneet | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started
W27 | Friday | Mohit | 1:00 PM | NEWS | News: AWS re:Invent Takeaways | 1.5 |  | Not Started
W27 | Friday | Mohit | 1:30 PM | PAGE | Page: API Development Newport Beach | 2.0 |  | Not Started
W27 | Friday | Mohit | 5:30 PM | SEO PLAN | 180-Day: Ongoing optimization | 1.5 |  | Not Started
W27 | Friday | Mohit | 7:00 PM | SEO TASK | Internal links + backlink outreach | 1.5 |  | Not Started
W27 | Friday | Mohit | 8:30 PM | SEO TASK | Content refresh + weekly review | 1.0 |  | Not Started
W27 | Friday | Mohit | 9:30 PM | SEO TASK | GBP update + social + competitor check | 0.5 |  | Not Started

## 180-Day SEO Plan
180-DAY SEO PLAN — WEEKLY PHASES
Week | Month | Phase | SEO Focus Task | Est Hrs/Day
W1 | M1 | Phase 1 | Search intent keyword research + topic clustering | 1.5-2.0
W2 | M1 | Phase 2 | Competitor content gap analysis | 1.5-2.0
W3 | M1 | Phase 3 | AI-assisted content plan + topical authority mapping | 1.5-2.0
W4 | M1 | Phase 4 | Technical SEO audit (crawl, index, Core Web Vitals) | 1.5-2.0
W5 | M1 | Phase 5 | Site structure + internal linking plan | 1.5-2.0
W6 | M2 | Phase 6 | Publish high-quality pillar content | 1.5-2.0
W7 | M2 | Phase 7 | Publish high-quality pillar content | 1.5-2.0
W8 | M2 | Phase 8 | On-page SEO (titles, headings, entities, FAQs) | 1.5-2.0
W9 | M2 | Phase 9 | Schema markup (Article, FAQ, Organization) | 1.5-2.0
W10 | M2 | Phase 10 | Indexing optimization + sitemap check | 1.5-2.0
W11 | M3 | Phase 11 | Authority content publishing (case studies, guides) | 1.5-2.0
W12 | M3 | Phase 12 | Linkable asset creation (data, templates, tools) | 1.5-2.0
W13 | M3 | Phase 13 | Digital PR outreach | 1.5-2.0
W14 | M3 | Phase 14 | Internal linking optimization | 1.5-2.0
W15 | M4 | Phase 15 | Content refresh (update old posts) | 1.5-2.0
W16 | M4 | Phase 16 | UX + engagement optimization | 1.5-2.0
W17 | M4 | Phase 17 | Featured snippet optimization | 1.5-2.0
W18 | M4 | Phase 18 | Conversion optimization | 1.5-2.0
W19 | M5 | Phase 19 | Topical authority expansion content | 1.5-2.0
W20 | M5 | Phase 20 | High-quality backlink partnerships | 1.5-2.0
W21 | M5 | Phase 21 | Brand search optimization | 1.5-2.0
W22 | M5 | Phase 22 | AI search optimization (LLM visibility) | 1.5-2.0
W23 | M6 | Phase 23 | Performance audit + ranking analysis | 1.5-2.0
W24 | M6 | Phase 24 | Content pruning (remove weak pages) | 1.5-2.0
W25 | M6 | Phase 25 | ROI tracking + analytics review | 1.5-2.0
W26 | M6 | Phase 26 | Next 6-month SEO strategy planning | 1.5-2.0

## Puneet — Persona A
Puneet Kumar — Persona A
EVENING (1PM–11PM) ¦ Blogs: 26 ¦ News: 26 ¦ Pages: 130 ¦ Managed IT/HIPAA
# | BLOG TITLE | Est Hrs | Due Week | Status | Actual Hrs | Notes
1 | 2026 HIPAA Compliance Checklist for OC | 2.5 | W2 | Not Started |  | https://technijian.com/compliance/hipaa-compliance/2026-hipaa-compliance-checklist-for-orange-county-healthcare-businesses/
2 | Why OC Businesses Need 24/7 IT Support | 2.5 | W3 | Not Started |  | https://technijian.com/it-support-orange-county/why-oc-businesses-need-24-7-it-support/
3 | Top 5 Ransomware Threats OC Healthcare 2026 | 2.5 | W4 | Not Started
4 | FINRA IT Checklist Newport Beach | 2.5 | W5 | Not Started
5 | Cost of HIPAA Non-Compliance CA | 2.5 | W6 | Not Started
6 | Choose HIPAA-Compliant IT in OC | 2.5 | W7 | Not Started
7 | Managed IT vs Break-Fix for OC | 2.5 | W8 | Not Started
8 | Cybersecurity for Irvine Medical Offices | 2.5 | W9 | Not Started
9 | SOC 2 Compliance: Why OC Needs It | 2.5 | W10 | Not Started
10 | Ransomware Targets Small Clinics | 2.5 | W11 | Not Started
11 | Zero Trust Security for OC | 2.5 | W12 | Not Started
12 | Cloud Backup for HIPAA Practices | 2.5 | W13 | Not Started
13 | Prepare for HIPAA Audit 2026 | 2.5 | W14 | Not Started
14 | IT Disaster Recovery Newport Beach | 2.5 | W15 | Not Started
15 | OC Dental Practices Need Managed IT | 2.5 | W16 | Not Started
16 | EDR: Protecting OC Offices | 2.5 | W17 | Not Started
17 | MFA: Protect Patient Data | 2.5 | W18 | Not Started
18 | Downtime Costs OC $10K+/Hour | 2.5 | W19 | Not Started
19 | PCI Compliance for OC Retail | 2.5 | W20 | Not Started
20 | Remote Work Security OC Healthcare | 2.5 | W21 | Not Started
21 | Phishing Prevention OC Medical | 2.5 | W22 | Not Started
22 | IT SLA: OC Response Times | 2.5 | W23 | Not Started
23 | M365 Security for HIPAA | 2.5 | W24 | Not Started
24 | Securing OC Law Firm Data 2026 | 2.5 | W25 | Not Started
25 | 24/7 Network Monitoring OC | 2.5 | W26 | Not Started
26 | Data Encryption for OC Advisors | 2.5 | W27 | Not Started
# | NEWS ARTICLE | Est Hrs | Due Week | Status | Actual Hrs | Notes
1 | HIPAA Enforcement 2026 OC | 1.5 | W2 | done |  | https://technijian.com/compliance/hipaa-compliance/2026-hipaa-compliance-checklist-for-orange-county-healthcare-businesses/
2 | Ransomware Hits SoCal Healthcare | 1.5 | W3 | Not Started
3 | OC Data Breach Lessons | 1.5 | W4 | Not Started
4 | Cyber Insurance Tightens OC | 1.5 | W5 | Not Started
5 | CMMC 2.0 OC Deadline | 1.5 | W6 | Not Started
6 | CPRA Enforcement OC | 1.5 | W7 | Not Started
7 | Mid-Year Cyber Threats OC | 1.5 | W8 | Not Started
8 | Microsoft Zero-Day Patch | 1.5 | W9 | Not Started
9 | FBI Phishing Alert OC | 1.5 | W10 | Not Started
10 | Hospital Ransomware Lessons | 1.5 | W11 | Not Started
11 | Cloud Security 2026 | 1.5 | W12 | Not Started
12 | New HIPAA Penalties CA | 1.5 | W13 | Not Started
13 | OC School Data Breach | 1.5 | W14 | Not Started
14 | Zero Trust Federal Mandate OC | 1.5 | W15 | Not Started
15 | Managed IT SoCal Trends | 1.5 | W16 | Not Started
16 | Fortinet Vulnerability Alert | 1.5 | W17 | Not Started
17 | SEC Cyber Rules OC | 1.5 | W18 | Not Started
18 | Workspace Healthcare Security | 1.5 | W19 | Not Started
19 | Phishing 300% Surge OC | 1.5 | W20 | Not Started
20 | CA AG Privacy Standards | 1.5 | W21 | Not Started
21 | EMR Vulnerability Alert | 1.5 | W22 | Not Started
22 | SoCal IT Security Predictions | 1.5 | W23 | Not Started
23 | FTC Safeguards OC | 1.5 | W24 | Not Started
24 | Dental Ransomware OC | 1.5 | W25 | Not Started
25 | M365 Outage Lessons | 1.5 | W26 | Not Started
26 | NIST 2.0 SMBs | 1.5 | W27 | Not Started
# | LANDING PAGE (Service + City) | Est Hrs | Due Week | Status | Actual Hrs | Notes
1 | Managed IT Services Irvine | 2 | W2 | done |  | https://technijian.com/managed-it-services-irvine/
2 | HIPAA IT Support Newport Beach | 2 | W2 | done |  | https://technijian.com/hipaa-it-support-newport-beach/
3 | 24/7 IT Helpdesk Santa Ana | 2 | W2 | done |  | https://technijian.com/24-7-it-helpdesk-santa-ana/
4 | Cybersecurity Services Anaheim | 2 | W2 | done |  | https://technijian.com/cybersecurity-services-in-anaheim-ca/
5 | Cloud Migration Costa Mesa | 2 | W2 | done |  | https://technijian.com/cloud-migration-in-costa-mesa-ca/
6 | IT Disaster Recovery Long Beach | 2 | W3 | Done |  | https://technijian.com/it-disaster-recovery-services/
7 | Network Monitoring Downtown LA | 2 | W3 | Done |  | https://technijian.com/network-monitoring-downtown-la/
8 | Endpoint Security Torrance | 2 | W3 | done |  | https://technijian.com/endpoint-security-torrance/
9 | Compliance IT Tustin | 2 | W3 | done |  | https://technijian.com/compliance-it-tustin/
10 | IT Consulting Culver City | 2 | W3 | done |  | https://technijian.com/it-consulting-in-culver-city-ca/
11 | Server Management Santa Monica | 2 | W4 | done |  | https://technijian.com/server-management-in-santa-monica-ca/
12 | Data Backup Solutions Irvine | 2 | W4 | done |  | https://technijian.com/data-backup-solutions-in-irvine-ca
13 | Managed IT Services Newport Beach | 2 | W4 | done |  | https://technijian.com/managed-it-services-newport-beach/
14 | HIPAA IT Support Santa Ana | 2 | W4 | done |  | https://technijian.com/hipaa-it-support-santa-ana/
15 | 24/7 IT Helpdesk Anaheim | 2 | W4 | done |  | https://technijian.com/24-7-it-helpdesk-anaheim/
16 | Cybersecurity Services Costa Mesa | 2 | W5 | done |  | https://technijian.com/cybersecurity-services-in-costa-mesa/
17 | Cloud Migration Long Beach | 2 | W5 | done |  | https://technijian.com/cloud-migration-long-beach/
18 | IT Disaster Recovery Downtown LA | 2 | W5 | done |  | https://technijian.com/it-disaster-recovery-downtown-la
19 | Network Monitoring Torrance | 2 | W5 | done |  | https://technijian.com/network-monitoring-torrance
20 | Endpoint Security Tustin | 2 | W5 | done |  | https://technijian.com/endpoint-security-tustin/
21 | Compliance IT Culver City | 2 | W6 | Done |  | https://technijian.com/compliance-it-culver-city/
22 | IT Consulting Santa Monica | 2 | W6 | Done |  | https://technijian.com/it-consulting-santa-monica/
23 | Server Management Irvine | 2 | W6 | Done |  | https://technijian.com/server-management-irvine/
24 | Data Backup Solutions Newport Beach | 2 | W6 | Done |  | https://technijian.com/data-backup-solutions-for-newport-beach/
25 | Managed IT Services Santa Ana | 2 | W6 | Done |  | https://technijian.com/managed-it-services-santa-ana/
26 | HIPAA IT Support Anaheim | 2 | W7 | Done |  | https://technijian.com/hipaa-it-support-anaheim/
27 | 24/7 IT Helpdesk Costa Mesa | 2 | W7 | Done |  | https://technijian.com/24-7-it-helpdesk-costa-mesa/
28 | Cybersecurity Services Long Beach | 2 | W7 | Done |  | https://technijian.com/cybersecurity-services-long-beach/
29 | Cloud Migration Downtown LA | 2 | W7 | Done |  | https://technijian.com/cloud-migration-downtown-la/
30 | IT Disaster Recovery Torrance | 2 | W7 | Done |  | https://technijian.com/it-disaster-recovery-for-torrance/
31 | Network Monitoring Tustin | 2 | W8 | Done |  | https://technijian.com/network-monitoring-for-tustin/
32 | Endpoint Security Culver City | 2 | W8 | Done |  | https://technijian.com/endpoint-security-for-culver-city/
33 | Compliance IT Santa Monica | 2 | W8 | Done |  | https://technijian.com/compliance-it-for-santa-monica/
34 | IT Consulting Irvine | 2 | W8 | Done |  | https://technijian.com/it-consulting-in-irvine/
35 | Server Management Newport Beach | 2 | W8 | Done |  | https://technijian.com/server-management-for-newport-beach/
36 | Data Backup Solutions Santa Ana | 2 | W9 | Done |  | https://technijian.com/data-backup-solutions-santa-ana/
37 | Managed IT Services Anaheim | 2 | W9 | Done |  | https://technijian.com/managed-it-services-anaheim/
38 | HIPAA IT Support Costa Mesa | 2 | W9 | Done |  | https://technijian.com/hipaa-it-support-costa-mesa/
39 | 24/7 IT Helpdesk Long Beach | 2 | W9 | Done |  | https://technijian.com/24-7-it-helpdesk-for-long-beach/
40 | Cybersecurity Services Downtown LA | 2 | W9 | Done |  | https://technijian.com/cybersecurity-services-downtown-la/
41 | Cloud Migration Torrance | 2 | W10 | Done |  | https://technijian.com/cloud-migration-torrance/
42 | IT Disaster Recovery Tustin | 2 | W10
43 | Network Monitoring Culver City | 2 | W10
44 | Endpoint Security Santa Monica | 2 | W10
45 | Compliance IT Irvine | 2 | W10
46 | IT Consulting Newport Beach | 2 | W11 | Not Started
47 | Server Management Santa Ana | 2 | W11 | Not Started
48 | Data Backup Solutions Anaheim | 2 | W11 | Not Started
49 | Managed IT Services Costa Mesa | 2 | W11 | Not Started
50 | HIPAA IT Support Long Beach | 2 | W11 | Not Started
51 | 24/7 IT Helpdesk Downtown LA | 2 | W12 | Not Started
52 | Cybersecurity Services Torrance | 2 | W12 | Not Started
53 | Cloud Migration Tustin | 2 | W12 | Not Started
54 | IT Disaster Recovery Culver City | 2 | W12 | Not Started
55 | Network Monitoring Santa Monica | 2 | W12 | Not Started
56 | Endpoint Security Irvine | 2 | W13 | Not Started
57 | Compliance IT Newport Beach | 2 | W13 | Not Started
58 | IT Consulting Santa Ana | 2 | W13 | Not Started
59 | Server Management Anaheim | 2 | W13 | Not Started
60 | Data Backup Solutions Costa Mesa | 2 | W13 | Not Started
61 | Managed IT Services Long Beach | 2 | W14 | Not Started
62 | HIPAA IT Support Downtown LA | 2 | W14 | Not Started
63 | 24/7 IT Helpdesk Torrance | 2 | W14 | Not Started
64 | Cybersecurity Services Tustin | 2 | W14 | Not Started
65 | Cloud Migration Culver City | 2 | W14 | Not Started
66 | IT Disaster Recovery Santa Monica | 2 | W15 | Not Started
67 | Network Monitoring Irvine | 2 | W15 | Not Started
68 | Endpoint Security Newport Beach | 2 | W15 | Not Started
69 | Compliance IT Santa Ana | 2 | W15 | Not Started
70 | IT Consulting Anaheim | 2 | W15 | Not Started
71 | Server Management Costa Mesa | 2 | W16 | Not Started
72 | Data Backup Solutions Long Beach | 2 | W16 | Not Started
73 | Managed IT Services Downtown LA | 2 | W16 | Not Started
74 | HIPAA IT Support Torrance | 2 | W16 | Not Started
75 | 24/7 IT Helpdesk Tustin | 2 | W16 | Not Started
76 | Cybersecurity Services Culver City | 2 | W17 | Not Started
77 | Cloud Migration Santa Monica | 2 | W17 | Not Started
78 | IT Disaster Recovery Irvine | 2 | W17 | Not Started
79 | Network Monitoring Newport Beach | 2 | W17 | Not Started
80 | Endpoint Security Santa Ana | 2 | W17 | Not Started
81 | Compliance IT Anaheim | 2 | W18 | Not Started
82 | IT Consulting Costa Mesa | 2 | W18 | Not Started
83 | Server Management Long Beach | 2 | W18 | Not Started
84 | Data Backup Solutions Downtown LA | 2 | W18 | Not Started
85 | Managed IT Services Torrance | 2 | W18 | Not Started
86 | HIPAA IT Support Tustin | 2 | W19 | Not Started
87 | 24/7 IT Helpdesk Culver City | 2 | W19 | Not Started
88 | Cybersecurity Services Santa Monica | 2 | W19 | Not Started
89 | Cloud Migration Irvine | 2 | W19 | Not Started
90 | IT Disaster Recovery Newport Beach | 2 | W19 | Not Started
91 | Network Monitoring Santa Ana | 2 | W20 | Not Started
92 | Endpoint Security Anaheim | 2 | W20 | Not Started
93 | Compliance IT Costa Mesa | 2 | W20 | Not Started
94 | IT Consulting Long Beach | 2 | W20 | Not Started
95 | Server Management Downtown LA | 2 | W20 | Not Started
96 | Data Backup Solutions Torrance | 2 | W21 | Not Started
97 | Managed IT Services Tustin | 2 | W21 | Not Started
98 | HIPAA IT Support Culver City | 2 | W21 | Not Started
99 | 24/7 IT Helpdesk Santa Monica | 2 | W21 | Not Started
100 | Cybersecurity Services Irvine | 2 | W21 | Not Started
101 | Cloud Migration Newport Beach | 2 | W22 | Not Started
102 | IT Disaster Recovery Santa Ana | 2 | W22 | Not Started
103 | Network Monitoring Anaheim | 2 | W22 | Not Started
104 | Endpoint Security Costa Mesa | 2 | W22 | Not Started
105 | Compliance IT Long Beach | 2 | W22 | Not Started
106 | IT Consulting Downtown LA | 2 | W23 | Not Started
107 | Server Management Torrance | 2 | W23 | Not Started
108 | Data Backup Solutions Tustin | 2 | W23 | Not Started
109 | Managed IT Services Culver City | 2 | W23 | Not Started
110 | HIPAA IT Support Santa Monica | 2 | W23 | Not Started
111 | 24/7 IT Helpdesk Irvine | 2 | W24 | Not Started
112 | Cybersecurity Services Newport Beach | 2 | W24 | Not Started
113 | Cloud Migration Santa Ana | 2 | W24 | Not Started
114 | IT Disaster Recovery Anaheim | 2 | W24 | Not Started
115 | Network Monitoring Costa Mesa | 2 | W24 | Not Started
116 | Endpoint Security Long Beach | 2 | W25 | Not Started
117 | Compliance IT Downtown LA | 2 | W25 | Not Started
118 | IT Consulting Torrance | 2 | W25 | Not Started
119 | Server Management Tustin | 2 | W25 | Not Started
120 | Data Backup Solutions Culver City | 2 | W25 | Not Started
121 | Managed IT Services Santa Monica | 2 | W26 | Not Started
122 | HIPAA IT Support Irvine | 2 | W26 | Not Started
123 | 24/7 IT Helpdesk Newport Beach | 2 | W26 | Not Started
124 | Cybersecurity Services Santa Ana | 2 | W26 | Not Started
125 | Cloud Migration Anaheim | 2 | W26 | Not Started
126 | IT Disaster Recovery Costa Mesa | 2 | W27 | Not Started
127 | Network Monitoring Long Beach | 2 | W27 | Not Started
128 | Endpoint Security Downtown LA | 2 | W27 | Not Started
129 | Compliance IT Torrance | 2 | W27 | Not Started
130 | IT Consulting Tustin | 2 | W27 | Not Started

## Mohit — Persona B
Mohit Pandey — Persona B
EVENING (1PM–11PM) ¦ Blogs: 26 ¦ News: 26 ¦ Pages: 130 ¦ Software Dev
# | BLOG TITLE | Est Hrs | Due Week | Status | Actual Hrs | Notes
1 | AI-Native SDLC: Why Agile is Dead | 2.5 | W2 | Not Started |  | done
2 | Build vs Buy: AI Agents 2026 | 2.5 | W3 | Not Started
3 | .NET to .NET 8 Migration | 2.5 | W4 | Not Started
4 | React 18 vs Blazor Enterprise | 2.5 | W5 | Not Started
5 | Contract-First Dev Explained | 2.5 | W6 | Not Started
6 | Enterprise Software 6 Weeks AI | 2.5 | W7 | Not Started
7 | MVP Timeline 2026 | 2.5 | W8 | Not Started
8 | Santa Monica Hybrid Dev Teams | 2.5 | W9 | Not Started
9 | API-First Architecture SaaS | 2.5 | W10 | Not Started
10 | AI Code Review Saves 40% | 2.5 | W11 | Not Started
11 | Custom CRM vs Salesforce | 2.5 | W12 | Not Started
12 | Microservices vs Monolith Startups | 2.5 | W13 | Not Started
13 | Technical Debt Cost OC Startups | 2.5 | W14 | Not Started
14 | Software Dev RFP 2026 | 2.5 | W15 | Not Started
15 | CI/CD Pipeline Startups | 2.5 | W16 | Not Started
16 | Offshore Dev = Spaghetti Code | 2.5 | W17 | Not Started
17 | Azure vs AWS SoCal Enterprise | 2.5 | W18 | Not Started
18 | AI Agents Supply Chain | 2.5 | W19 | Not Started
19 | Real-Time Dashboard 2026 | 2.5 | W20 | Not Started
20 | Evaluate Software Dev Partner | 2.5 | W21 | Not Started
21 | PWA vs Native OC Business | 2.5 | W22 | Not Started
22 | Database Architecture Decisions | 2.5 | W23 | Not Started
23 | Irvine Logistics AI | 2.5 | W24 | Not Started
24 | Software IP Protection Guide | 2.5 | W25 | Not Started
25 | DevOps Scaling SaaS | 2.5 | W26 | Not Started
26 | Headless CMS Enterprise | 2.5 | W27 | Not Started
# | NEWS ARTICLE | Est Hrs | Due Week | Status | Actual Hrs | Notes
1 | CA AI Law Dev Impact | 1.5 | W2 | Not Started
2 | React 19 Enterprise | 1.5 | W3 | Not Started
3 | .NET 9 Preview | 1.5 | W4 | Not Started
4 | AI Low-Code Opportunity | 1.5 | W5 | Not Started
5 | SoCal Startup Funding | 1.5 | W6 | Not Started
6 | Azure AI 2026 | 1.5 | W7 | Not Started
7 | SaaS H2 2026 SoCal | 1.5 | W8 | Not Started
8 | GitHub Copilot Workspace | 1.5 | W9 | Not Started
9 | Kubernetes 2026 | 1.5 | W10 | Not Started
10 | TypeScript 6.0 | 1.5 | W11 | Not Started
11 | Irvine Tech Growth | 1.5 | W12 | Not Started
12 | Vercel vs Netlify 2026 | 1.5 | W13 | Not Started
13 | OpenAI API Impact | 1.5 | W14 | Not Started
14 | YC SoCal Startups | 1.5 | W15 | Not Started
15 | Docker Security Enterprise | 1.5 | W16 | Not Started
16 | Silicon Beach Dev | 1.5 | W17 | Not Started
17 | MS Build 2026 | 1.5 | W18 | Not Started
18 | AI Coding Benchmarks | 1.5 | W19 | Not Started
19 | SoCal DX Stories | 1.5 | W20 | Not Started
20 | PostgreSQL vs MongoDB | 1.5 | W21 | Not Started
21 | Irvine Tech Launches | 1.5 | W22 | Not Started
22 | OWASP 2026 | 1.5 | W23 | Not Started
23 | OC Accelerators | 1.5 | W24 | Not Started
24 | Blazor .NET 9 | 1.5 | W25 | Not Started
25 | SoCal DevOps Highlights | 1.5 | W26 | Not Started
26 | AWS re:Invent Takeaways | 1.5 | W27 | Not Started
# | LANDING PAGE (Service + City) | Est Hrs | Due Week | Status | Actual Hrs | Notes | Old Page
1 | AI Software Development Irvine | 2 | W2 | done |  | https://technijian.com/ai-software-dev-irvine/ | https://technijian.com/aerospace/
2 | Custom App Development Santa Monica | 2 | W2 | done |  | https://technijian.com/custom-app-development-santa-monica/ | https://technijian.com/automotive/
3 | Enterprise Web Apps Culver City | 2 | W2 | done |  | https://technijian.com/enterprise-web-application-development-culver-city | https://technijian.com/legal-services/
4 | .NET Development Downtown LA | 2 | W2 | done |  | https://technijian.com/net-development-downtown-los-angeles/ | https://technijian.com/manufacturing
5 | React Development Torrance | 2 | W2 | done |  | https://technijian.com/react-development-in-torrance-california/ | https://technijian.com/retail-e-commerce/
6 | SaaS Development Costa Mesa | 2 | W3 | done |  | https://technijian.com/saas-development-in-costa-mesa/ | https://technijian.com/education/
7 | AI Agent Development Long Beach | 2 | W3 | done |  | https://technijian.com/ai-agent-development-for-long-beach-operations/ | https://technijian.com/construction
8 | CRM Development Anaheim | 2 | W3 | done |  | https://technijian.com/crm-development-anaheim/ | https://technijian.com/government-public-sector
9 | Mobile App Dev Newport Beach | 2 | W3 | done |  | https://technijian.com/mobile-app-development-newport-beach/ | https://technijian.com/nonprofit-organizations/
10 | API Development Tustin | 2 | W3 | done |  | https://technijian.com/api-development-in-tustin-california/ | https://technijian.com/hospitality
11 | Cloud App Development Santa Ana | 2 | W4 | done |  | https://technijian.com/cloud-app-development-santa-ana/ | https://technijian.com/real-estate
12 | DevOps Services Irvine | 2 | W4 | done |  | https://technijian.com/devops-services-irvine | https://technijian.com/telecommunication/
13 | AI Software Development Santa Monica | 2 | W4 | done |  | https://technijian.com/ai-software-development-santa-monica | https://technijian.com/energy-utilities/
14 | Custom App Development Culver City | 2 | W4 | done |  | https://technijian.com/custom-app-development-culver-city
15 | Enterprise Web Apps Downtown LA | 2 | W4 | done |  | https://technijian.com/enterprise-web-apps-for-downtown-la/
16 | .NET Development Torrance | 2 | W5 | done |  | https://technijian.com/net-development-in-torrance-ca/
17 | React Development Costa Mesa | 2 | W5 | done |  | https://technijian.com/react-development-in-costa-mesa-ca
18 | SaaS Development Long Beach | 2 | W5 | done |  | https://technijian.com/saas-development-in-long-beach-ca/
19 | AI Agent Development Anaheim | 2 | W5 | done |  | https://technijian.com/ai-agent-development-in-anaheim-ca/
20 | CRM Development Newport Beach | 2 | W5 | done |  | https://technijian.com/crm-development-in-newport-beach-ca/
21 | Mobile App Dev Tustin | 2 | W6 | done |  | https://technijian.com/mobile-app-dev-tustin/
22 | API Development Santa Ana | 2 | W6 | done |  | https://technijian.com/api-development-santa-ana/
23 | Cloud App Development Irvine | 2 | W6 | done |  | https://technijian.com/cloud-app-development-irvine/
24 | DevOps Services Santa Monica | 2 | W6 | done |  | https://technijian.com/devops-services-santa-monica/
25 | AI Software Development Culver City | 2 | W6 | done |  | https://technijian.com/ai-software-development-culver-city/
26 | Custom App Development Downtown LA | 2 | W7 | done |  | https://technijian.com/custom-app-development-for-downtown-la/
27 | Enterprise Web Apps Torrance | 2 | W7 | done |  | https://technijian.com/enterprise-web-apps-torrance/
28 | .NET Development Costa Mesa | 2 | W7 | done |  | https://technijian.com/net-development-costa-mesa
29 | React Development Long Beach | 2 | W7 | done |  | https://technijian.com/react-development-long-beach/
30 | SaaS Development Anaheim | 2 | W7 | done |  | https://technijian.com/saas-development-anaheim/
31 | AI Agent Development Newport Beach | 2 | W8 | done |  | https://technijian.com/ai-agent-development-for-newport-beach/
32 | CRM Development Tustin | 2 | W8 | done |  | https://technijian.com/crm-development-for-tustin-businesses/
33 | Mobile App Dev Santa Ana | 2 | W8 | done |  | https://technijian.com/mobile-app-dev-santa-ana/
34 | API Development Irvine | 2 | W8 | done |  | https://technijian.com/api-development-in-irvine/
35 | Cloud App Development Santa Monica | 2 | W8 | done |  | https://technijian.com/cloud-app-development-for-santa-monica/
36 | DevOps Services Culver City | 2 | W9 | done |  | https://technijian.com/devops-services-for-culver-city/
37 | AI Software Development Downtown LA | 2 | W9 | done |  | https://technijian.com/ai-software-development-for-downtown-la/
38 | Custom App Development Torrance | 2 | W9 | done |  | https://technijian.com/custom-app-development-for-torrance-businesses/
39 | Enterprise Web Apps Costa Mesa | 2 | W9 | done |  | https://technijian.com/enterprise-web-apps-costa-mesa/
40 | .NET Development Long Beach | 2 | W9 | done |  | https://technijian.com/net-development-for-long-beach/
41 | React Development Anaheim | 2 | W10 | done |  | https://technijian.com/react-development-anaheim/
42 | SaaS Development Newport Beach | 2 | W10 | done |  | https://technijian.com/saas-development-for-newport-beach/
43 | AI Agent Development Tustin | 2 | W10 | done |  | https://technijian.com/ai-agent-development-tustin/
44 | CRM Development Santa Ana | 2 | W10 | done |  | https://technijian.com/crm-development-for-santa-ana-businesses/
45 | Mobile App Dev Irvine | 2 | W10 | done |  | https://technijian.com/mobile-app-development-in-irvine
46 | API Development Santa Monica | 2 | W11 | Not Started
47 | Cloud App Development Culver City | 2 | W11 | Not Started
48 | DevOps Services Downtown LA | 2 | W11 | Not Started
49 | AI Software Development Torrance | 2 | W11 | Not Started
50 | Custom App Development Costa Mesa | 2 | W11 | Not Started
51 | Enterprise Web Apps Long Beach | 2 | W12 | Not Started
52 | .NET Development Anaheim | 2 | W12 | Not Started
53 | React Development Newport Beach | 2 | W12 | Not Started
54 | SaaS Development Tustin | 2 | W12 | Not Started
55 | AI Agent Development Santa Ana | 2 | W12 | Not Started
56 | CRM Development Irvine | 2 | W13 | Not Started
57 | Mobile App Dev Santa Monica | 2 | W13 | Not Started
58 | API Development Culver City | 2 | W13 | Not Started
59 | Cloud App Development Downtown LA | 2 | W13 | Not Started
60 | DevOps Services Torrance | 2 | W13 | Not Started
61 | AI Software Development Costa Mesa | 2 | W14 | Not Started
62 | Custom App Development Long Beach | 2 | W14 | Not Started
63 | Enterprise Web Apps Anaheim | 2 | W14 | Not Started
64 | .NET Development Newport Beach | 2 | W14 | Not Started
65 | React Development Tustin | 2 | W14 | Not Started
66 | SaaS Development Santa Ana | 2 | W15 | Not Started
67 | AI Agent Development Irvine | 2 | W15 | Not Started
68 | CRM Development Santa Monica | 2 | W15 | Not Started
69 | Mobile App Dev Culver City | 2 | W15 | Not Started
70 | API Development Downtown LA | 2 | W15 | Not Started
71 | Cloud App Development Torrance | 2 | W16 | Not Started
72 | DevOps Services Costa Mesa | 2 | W16 | Not Started
73 | AI Software Development Long Beach | 2 | W16 | Not Started
74 | Custom App Development Anaheim | 2 | W16 | Not Started
75 | Enterprise Web Apps Newport Beach | 2 | W16 | Not Started
76 | .NET Development Tustin | 2 | W17 | Not Started
77 | React Development Santa Ana | 2 | W17 | Not Started
78 | SaaS Development Irvine | 2 | W17 | Not Started
79 | AI Agent Development Santa Monica | 2 | W17 | Not Started
80 | CRM Development Culver City | 2 | W17 | Not Started
81 | Mobile App Dev Downtown LA | 2 | W18 | Not Started
82 | API Development Torrance | 2 | W18 | Not Started
83 | Cloud App Development Costa Mesa | 2 | W18 | Not Started
84 | DevOps Services Long Beach | 2 | W18 | Not Started
85 | AI Software Development Anaheim | 2 | W18 | Not Started
86 | Custom App Development Newport Beach | 2 | W19 | Not Started
87 | Enterprise Web Apps Tustin | 2 | W19 | Not Started
88 | .NET Development Santa Ana | 2 | W19 | Not Started
89 | React Development Irvine | 2 | W19 | Not Started
90 | SaaS Development Santa Monica | 2 | W19 | Not Started
91 | AI Agent Development Culver City | 2 | W20 | Not Started
92 | CRM Development Downtown LA | 2 | W20 | Not Started
93 | Mobile App Dev Torrance | 2 | W20 | Not Started
94 | API Development Costa Mesa | 2 | W20 | Not Started
95 | Cloud App Development Long Beach | 2 | W20 | Not Started
96 | DevOps Services Anaheim | 2 | W21 | Not Started
97 | AI Software Development Newport Beach | 2 | W21 | Not Started
98 | Custom App Development Tustin | 2 | W21 | Not Started
99 | Enterprise Web Apps Santa Ana | 2 | W21 | Not Started
100 | .NET Development Irvine | 2 | W21 | Not Started
101 | React Development Santa Monica | 2 | W22 | Not Started
102 | SaaS Development Culver City | 2 | W22 | Not Started
103 | AI Agent Development Downtown LA | 2 | W22 | Not Started
104 | CRM Development Torrance | 2 | W22 | Not Started
105 | Mobile App Dev Costa Mesa | 2 | W22 | Not Started
106 | API Development Long Beach | 2 | W23 | Not Started
107 | Cloud App Development Anaheim | 2 | W23 | Not Started
108 | DevOps Services Newport Beach | 2 | W23 | Not Started
109 | AI Software Development Tustin | 2 | W23 | Not Started
110 | Custom App Development Santa Ana | 2 | W23 | Not Started
111 | Enterprise Web Apps Irvine | 2 | W24 | Not Started
112 | .NET Development Santa Monica | 2 | W24 | Not Started
113 | React Development Culver City | 2 | W24 | Not Started
114 | SaaS Development Downtown LA | 2 | W24 | Not Started
115 | AI Agent Development Torrance | 2 | W24 | Not Started
116 | CRM Development Costa Mesa | 2 | W25 | Not Started
117 | Mobile App Dev Long Beach | 2 | W25 | Not Started
118 | API Development Anaheim | 2 | W25 | Not Started
119 | Cloud App Development Newport Beach | 2 | W25 | Not Started
120 | DevOps Services Tustin | 2 | W25 | Not Started
121 | AI Software Development Santa Ana | 2 | W26 | Not Started
122 | Custom App Development Irvine | 2 | W26 | Not Started
123 | Enterprise Web Apps Santa Monica | 2 | W26 | Not Started
124 | .NET Development Culver City | 2 | W26 | Not Started
125 | React Development Downtown LA | 2 | W26 | Not Started
126 | SaaS Development Torrance | 2 | W27 | Not Started
127 | AI Agent Development Costa Mesa | 2 | W27 | Not Started
128 | CRM Development Long Beach | 2 | W27 | Not Started
129 | Mobile App Dev Anaheim | 2 | W27 | Not Started
130 | API Development Newport Beach | 2 | W27 | Not Started
# | EXTRA | Type | Due | Status | Actual Hrs | Notes
1 | Logistics AI Platform Case Study | Case Study | W12 | Not Started

## Saroj — Persona C
Saroj Kumari — Persona C
MORNING (10:30AM–7:30PM) ¦ Blogs: 26 ¦ News: 26 ¦ Pages: 130 ¦ SEO/Marketing
# | BLOG TITLE | Est Hrs | Due Week | Status | Actual Hrs | Notes
1 | SEO Pricing OC 2026 | 2.5 | W2 | Not Started |  | done
2 | SEO Guy Can't Rank You in ChatGPT | 2.5 | W3 | Not Started |  | done
3 | Google Ads vs SEO for OC | 2.5 | W4 | Not Started
4 | AI Search Kills Traffic Fix It | 2.5 | W5 | Not Started
5 | Local SEO Checklist OC 2026 | 2.5 | W6 | Not Started
6 | Google Reviews Without Begging | 2.5 | W7 | Not Started
7 | Website Not Ranking Code Issue | 2.5 | W8 | Not Started
8 | AEO Complete Guide 2026 | 2.5 | W9 | Done
9 | Schema Markup OC Business | 2.5 | W10 | Not Started
10 | Fix LCP FID CLS Shopify | 2.5 | W11 | Not Started
11 | Rank in Google AI Overviews | 2.5 | W12 | Not Started
12 | Local vs National SEO OC | 2.5 | W13 | Not Started
13 | Optimize GBP for Calls | 2.5 | W14 | Not Started
14 | Technical SEO Audit Checklist | 2.5 | W15 | Not Started
15 | Page Speed OC Restaurants | 2.5 | W16 | Not Started
16 | Link Building OC Businesses | 2.5 | W17 | Not Started
17 | Fix Duplicate Content | 2.5 | W18 | Not Started
18 | SEO for OC HVAC | 2.5 | W19 | Not Started
19 | ChatGPT Recommends Businesses | 2.5 | W20 | Not Started
20 | Content ROI Measure SEO 2026 | 2.5 | W21 | Not Started
21 | Optimize Perplexity & Gemini | 2.5 | W22 | Not Started
22 | SEO Costa Mesa Dental | 2.5 | W23 | Not Started
23 | Mobile-First OC Ready? | 2.5 | W24 | Not Started
24 | SEO Content That Converts | 2.5 | W25 | Not Started
25 | OC SEO Mistakes & Fixes | 2.5 | W26 | Not Started
26 | Voice Search OC Business | 2.5 | W27 | Not Started
# | NEWS ARTICLE | Est Hrs | Due Week | Status | Actual Hrs | Notes
1 | Google Core Update Local | 1.5 | W2 | Not Started
2 | ChatGPT Search Local | 1.5 | W3 | Not Started
3 | GBP 2026 Features | 1.5 | W4 | Not Started
4 | Perplexity Business Listings | 1.5 | W5 | Not Started
5 | AI Overviews CTR Impact | 1.5 | W6 | Not Started
6 | Voice Search Local | 1.5 | W7 | Not Started
7 | Google Ads OC Update | 1.5 | W8 | Not Started
8 | Yelp OC Restaurant SEO | 1.5 | W9 | Not Started
9 | Instagram SEO Local | 1.5 | W10 | Not Started
10 | TikTok Search OC | 1.5 | W11 | Not Started
11 | Apple Maps OC Changes | 1.5 | W12 | Not Started
12 | Bing AI Local Rankings | 1.5 | W13 | Not Started
13 | Reddit SEO Google | 1.5 | W14 | Not Started
14 | YouTube Shorts SEO | 1.5 | W15 | Not Started
15 | Google LSA OC | 1.5 | W16 | Not Started
16 | Schema.org 2026 | 1.5 | W17 | Not Started
17 | CWV Threshold Changes | 1.5 | W18 | Not Started
18 | Google Reviews Crackdown | 1.5 | W19 | Not Started
19 | AI Content Detection | 1.5 | W20 | Not Started
20 | SEMrush vs Ahrefs 2026 | 1.5 | W21 | Not Started
21 | OC Marketing Survey | 1.5 | W22 | Not Started
22 | Facebook Meta SEO | 1.5 | W23 | Not Started
23 | Search Console 2026 | 1.5 | W24 | Not Started
24 | Local Pack Testing | 1.5 | W25 | Not Started
25 | E-E-A-T Authority | 1.5 | W26 | Not Started
26 | AEO Ranking Research | 1.5 | W27 | Not Started
# | LANDING PAGE (Service + City) | Est Hrs | Due Week | Status | Actual Hrs | Notes | Old Pages
1 | SEO Services Costa Mesa | 2 | W2 | Done |  | https://technijian.com/seo-services-costa-mesa/ | https://technijian.com/managed-it-support-and-services-aliso-viejo/
2 | Local SEO Anaheim | 2 | W2 | Done |  | https://technijian.com/local-seo-anaheim | https://technijian.com/it-services-and-solutions-brea/
3 | Technical SEO Long Beach | 2 | W2 | Done |  | https://technijian.com/technical-seo-long-beach | https://technijian.com/dana-point-it-services-managed-it-support-partner/
4 | Answer Engine Optimization Tustin | 2 | W2 | Done |  | https://technijian.com/answer-engine-optimization-tustin/ | https://technijian.com/it-services-support-in-fullerton/
5 | Google Ads Management Culver City | 2 | W2 | Done |  | https://technijian.com/google-ads-management-culver-city/ | https://technijian.com/managed-it-services-and-it-consulting-huntington-beach/
6 | Content Marketing Irvine | 2 | W3 | Done |  | https://technijian.com/content-marketing-irvine/
7 | Link Building Newport Beach | 2 | W3 | Done |  | https://technijian.com/link-building-newport-beach/
8 | SEO Audit Santa Ana | 2 | W3 | Done |  | https://technijian.com/seo-audit-santa-ana/
9 | E-Commerce SEO Downtown LA | 2 | W3 | Done |  | https://technijian.com/ecommerce-seo-downtown-la/
10 | Schema Markup Services Torrance | 2 | W3 | Done |  | https://technijian.com/schema-markup-services-torrance/
11 | Website Speed Optimization Santa Monica | 2 | W4 | Done |  | https://technijian.com/website-speed-optimization-santa-monica/
12 | Social Media Marketing Costa Mesa | 2 | W4 | Done |  | https://technijian.com/social-media-marketing-costa-mesa/
13 | SEO Services Anaheim | 2 | W4 | Done |  | https://technijian.com/seo-services-anaheim
14 | Local SEO Long Beach | 2 | W4 | Done |  | https://technijian.com/local-seo-long-beach
15 | Technical SEO Tustin | 2 | W4 | Done |  | https://technijian.com/technical-seo-tustin/
16 | Answer Engine Optimization Culver City | 2 | W5 | Done |  | https://technijian.com/answer-engine-optimization-culver-city/
17 | Google Ads Management Irvine | 2 | W5 | Done |  | https://technijian.com/google-ads-management-irvine/
18 | Content Marketing Newport Beach | 2 | W5 | Done |  | https://technijian.com/content-marketing-newport-beach/
19 | Link Building Santa Ana | 2 | W5 | Done |  | https://technijian.com/link-building-santa-ana/
20 | SEO Audit Downtown LA | 2 | W5 | Done |  | https://technijian.com/seo-audit-downtown-la/
21 | E-Commerce SEO Torrance | 2 | W6 | Done |  | https://technijian.com/e-commerce-seo-torrance/
22 | Schema Markup Services Santa Monica | 2 | W6 | Done |  | https://technijian.com/schema-markup-services-santa-monica/
23 | Website Speed Optimization Costa Mesa | 2 | W6 | Done |  | https://technijian.com/website-speed-optimization-costa-mesa/
24 | Social Media Marketing Anaheim | 2 | W6 | Done |  | https://technijian.com/social-media-marketing-anaheim/
25 | SEO Services Long Beach | 2 | W6 | Done |  | https://technijian.com/seo-services-long-beach/
26 | Local SEO Tustin | 2 | W7 | Done |  | https://technijian.com/local-seo-tustin/
27 | Technical SEO Culver City | 2 | W7 | Done |  | https://technijian.com/technical-seo-culver-city/
28 | Answer Engine Optimization Irvine | 2 | W7 | Done |  | https://technijian.com/answer-engine-optimization-irvine/
29 | Google Ads Management Newport Beach | 2 | W7 | Not Started
30 | Content Marketing Santa Ana | 2 | W7 | Not Started
31 | Link Building Downtown LA | 2 | W8 | Not Started
32 | SEO Audit Torrance | 2 | W8 | Not Started
33 | E-Commerce SEO Santa Monica | 2 | W8 | Not Started
34 | Schema Markup Services Costa Mesa | 2 | W8 | Not Started
35 | Website Speed Optimization Anaheim | 2 | W8 | Not Started
36 | Social Media Marketing Long Beach | 2 | W9 | Not Started
37 | SEO Services Tustin | 2 | W9 | Not Started
38 | Local SEO Culver City | 2 | W9 | Not Started
39 | Technical SEO Irvine | 2 | W9 | Not Started
40 | Answer Engine Optimization Newport Beach | 2 | W9 | Not Started
41 | Google Ads Management Santa Ana | 2 | W10 | Not Started
42 | Content Marketing Downtown LA | 2 | W10 | Not Started
43 | Link Building Torrance | 2 | W10 | Not Started
44 | SEO Audit Santa Monica | 2 | W10 | Not Started
45 | E-Commerce SEO Costa Mesa | 2 | W10 | Not Started
46 | Schema Markup Services Anaheim | 2 | W11 | Not Started
47 | Website Speed Optimization Long Beach | 2 | W11 | Not Started
48 | Social Media Marketing Tustin | 2 | W11 | Not Started
49 | SEO Services Culver City | 2 | W11 | Not Started
50 | Local SEO Irvine | 2 | W11 | Not Started
51 | Technical SEO Newport Beach | 2 | W12 | Not Started
52 | Answer Engine Optimization Santa Ana | 2 | W12 | Not Started
53 | Google Ads Management Downtown LA | 2 | W12 | Not Started
54 | Content Marketing Torrance | 2 | W12 | Not Started
55 | Link Building Santa Monica | 2 | W12 | Not Started
56 | SEO Audit Costa Mesa | 2 | W13 | Not Started
57 | E-Commerce SEO Anaheim | 2 | W13 | Not Started
58 | Schema Markup Services Long Beach | 2 | W13 | Not Started
59 | Website Speed Optimization Tustin | 2 | W13 | Not Started
60 | Social Media Marketing Culver City | 2 | W13 | Not Started
61 | SEO Services Irvine | 2 | W14 | Not Started
62 | Local SEO Newport Beach | 2 | W14 | Not Started
63 | Technical SEO Santa Ana | 2 | W14 | Not Started
64 | Answer Engine Optimization Downtown LA | 2 | W14 | Not Started
65 | Google Ads Management Torrance | 2 | W14 | Not Started
66 | Content Marketing Santa Monica | 2 | W15 | Not Started
67 | Link Building Costa Mesa | 2 | W15 | Not Started
68 | SEO Audit Anaheim | 2 | W15 | Not Started
69 | E-Commerce SEO Long Beach | 2 | W15 | Not Started
70 | Schema Markup Services Tustin | 2 | W15 | Not Started
71 | Website Speed Optimization Culver City | 2 | W16 | Not Started
72 | Social Media Marketing Irvine | 2 | W16 | Not Started
73 | SEO Services Newport Beach | 2 | W16 | Not Started
74 | Local SEO Santa Ana | 2 | W16 | Not Started
75 | Technical SEO Downtown LA | 2 | W16 | Not Started
76 | Answer Engine Optimization Torrance | 2 | W17 | Not Started
77 | Google Ads Management Santa Monica | 2 | W17 | Not Started
78 | Content Marketing Costa Mesa | 2 | W17 | Not Started
79 | Link Building Anaheim | 2 | W17 | Not Started
80 | SEO Audit Long Beach | 2 | W17 | Not Started
81 | E-Commerce SEO Tustin | 2 | W18 | Not Started
82 | Schema Markup Services Culver City | 2 | W18 | Not Started
83 | Website Speed Optimization Irvine | 2 | W18 | Not Started
84 | Social Media Marketing Newport Beach | 2 | W18 | Not Started
85 | SEO Services Santa Ana | 2 | W18 | Not Started
86 | Local SEO Downtown LA | 2 | W19 | Not Started
87 | Technical SEO Torrance | 2 | W19 | Not Started
88 | Answer Engine Optimization Santa Monica | 2 | W19 | Not Started
89 | Google Ads Management Costa Mesa | 2 | W19 | Not Started
90 | Content Marketing Anaheim | 2 | W19 | Not Started
91 | Link Building Long Beach | 2 | W20 | Not Started
92 | SEO Audit Tustin | 2 | W20 | Not Started
93 | E-Commerce SEO Culver City | 2 | W20 | Not Started
94 | Schema Markup Services Irvine | 2 | W20 | Not Started
95 | Website Speed Optimization Newport Beach | 2 | W20 | Not Started
96 | Social Media Marketing Santa Ana | 2 | W21 | Not Started
97 | SEO Services Downtown LA | 2 | W21 | Not Started
98 | Local SEO Torrance | 2 | W21 | Not Started
99 | Technical SEO Santa Monica | 2 | W21 | Not Started
100 | Answer Engine Optimization Costa Mesa | 2 | W21 | Not Started
101 | Google Ads Management Anaheim | 2 | W22 | Not Started
102 | Content Marketing Long Beach | 2 | W22 | Not Started
103 | Link Building Tustin | 2 | W22 | Not Started
104 | SEO Audit Culver City | 2 | W22 | Not Started
105 | E-Commerce SEO Irvine | 2 | W22 | Not Started
106 | Schema Markup Services Newport Beach | 2 | W23 | Not Started
107 | Website Speed Optimization Santa Ana | 2 | W23 | Not Started
108 | Social Media Marketing Downtown LA | 2 | W23 | Not Started
109 | SEO Services Torrance | 2 | W23 | Not Started
110 | Local SEO Santa Monica | 2 | W23 | Not Started
111 | Technical SEO Costa Mesa | 2 | W24 | Not Started
112 | Answer Engine Optimization Anaheim | 2 | W24 | Not Started
113 | Google Ads Management Long Beach | 2 | W24 | Not Started
114 | Content Marketing Tustin | 2 | W24 | Not Started
115 | Link Building Culver City | 2 | W24 | Not Started
116 | SEO Audit Irvine | 2 | W25 | Not Started
117 | E-Commerce SEO Newport Beach | 2 | W25 | Not Started
118 | Schema Markup Services Santa Ana | 2 | W25 | Not Started
119 | Website Speed Optimization Downtown LA | 2 | W25 | Not Started
120 | Social Media Marketing Torrance | 2 | W25 | Not Started
121 | SEO Services Santa Monica | 2 | W26 | Not Started
122 | Local SEO Costa Mesa | 2 | W26 | Not Started
123 | Technical SEO Anaheim | 2 | W26 | Not Started
124 | Answer Engine Optimization Long Beach | 2 | W26 | Not Started
125 | Google Ads Management Tustin | 2 | W26 | Not Started
126 | Content Marketing Culver City | 2 | W27 | Not Started
127 | Link Building Irvine | 2 | W27 | Not Started
128 | SEO Audit Newport Beach | 2 | W27 | Not Started
129 | E-Commerce SEO Santa Ana | 2 | W27 | Not Started
130 | Schema Markup Services Downtown LA | 2 | W27 | Not Started

## Vaishali — Persona D
Vaishali Rathor — Persona D
MORNING (10:30AM–7:30PM) ¦ Blogs: 26 ¦ News: 26 ¦ Pages: 130 ¦ AI Consulting
# | BLOG TITLE | Est Hrs | Due Week | Status | Actual Hrs | Notes
1 | Enterprise AI Guide 2026 | 2.5 | W2 | Not Started
2 | Copilot vs Gemini vs ChatGPT | 2.5 | W3 | Not Started
3 | Calculate ROI AI Projects | 2.5 | W4 | Not Started
4 | AI Security & Compliance | 2.5 | W5 | Not Started
5 | HackGPT AI Pen Testing | 2.5 | W6 | Not Started
6 | AI Strategy Roadmap Enterprise | 2.5 | W7 | Not Started
7 | Copilot M365 Setup OC | 2.5 | W8 | Not Started
8 | AI Privacy GenAI No Leaks | 2.5 | W9 | Not Started
9 | RAG Architecture Enterprise | 2.5 | W10 | Not Started
10 | AI HR Automation 2026 | 2.5 | W11 | Not Started
11 | AI POC in 2 Weeks | 2.5 | W12 | Not Started
12 | Shadow AI Risks Management | 2.5 | W13 | Not Started
13 | Power BI AI for OC | 2.5 | W14 | Not Started
14 | AI Chatbot vs Agent 2026 | 2.5 | W15 | Not Started
15 | AI ROI Metrics That Matter | 2.5 | W16 | Not Started
16 | AI Governance Framework | 2.5 | W17 | Not Started
17 | Gemini Business Use Cases | 2.5 | W18 | Not Started
18 | AI Predictive Maintenance OC | 2.5 | W19 | Not Started
19 | Choose AI Consulting Partner | 2.5 | W20 | Not Started
20 | AI Financial Compliance | 2.5 | W21 | Not Started
21 | Prompt Engineering Teams | 2.5 | W22 | Not Started
22 | AI Changes PM 2026 | 2.5 | W23 | Not Started
23 | AI Legacy Integration | 2.5 | W24 | Not Started
24 | AI Tech Stack 2026 | 2.5 | W25 | Not Started
25 | AI Sales Copilot Revenue | 2.5 | W26 | Not Started
26 | Train Team on AI | 2.5 | W27 | Not Started
# | NEWS ARTICLE | Est Hrs | Due Week | Status | Actual Hrs | Notes
1 | Copilot 2026 Enterprise | 1.5 | W2 | Not Started
2 | Gemini Enterprise Impact | 1.5 | W3 | Not Started
3 | AI Regulation CA | 1.5 | W4 | Not Started
4 | Enterprise AI SoCal | 1.5 | W5 | Not Started
5 | OpenAI vs Copilot | 1.5 | W6 | Not Started
6 | AI Healthcare OC | 1.5 | W7 | Not Started
7 | Claude Enterprise | 1.5 | W8 | Not Started
8 | ISO 42001 Governance | 1.5 | W9 | Not Started
9 | SoCal AI Summit | 1.5 | W10 | Not Started
10 | Power BI AI Release | 1.5 | W11 | Not Started
11 | Salesforce Einstein | 1.5 | W12 | Not Started
12 | AI Legal OC | 1.5 | W13 | Not Started
13 | Meta AI Enterprise | 1.5 | W14 | Not Started
14 | SoCal Manufacturing AI | 1.5 | W15 | Not Started
15 | ServiceNow AI | 1.5 | W16 | Not Started
16 | AI Privacy CA Laws | 1.5 | W17 | Not Started
17 | Gartner AI Hype Cycle | 1.5 | W18 | Not Started
18 | OC CIO AI Survey | 1.5 | W19 | Not Started
19 | Fabric AI Analytics | 1.5 | W20 | Not Started
20 | AI Pen Test Tools | 1.5 | W21 | Not Started
21 | SoCal AI Startups | 1.5 | W22 | Not Started
22 | ChatGPT vs Copilot | 1.5 | W23 | Not Started
23 | AI Supply Chain | 1.5 | W24 | Not Started
24 | OC Healthcare AI | 1.5 | W25 | Not Started
25 | NVIDIA Enterprise GPUs | 1.5 | W26 | Not Started
26 | AI Ethics IEEE 2026 | 1.5 | W27 | Not Started
# | LANDING PAGE (Service + City) | Est Hrs | Due Week | Status | Actual Hrs | Notes | Old Pages | Notes
1 | AI Consulting Irvine | 2 | W2 | Done |  | https://technijian.com/ai-consulting-irvine/ | https://technijian.com/yorba-linda-it-services-support/ | https://technijian.com/yorba-linda/
2 | Copilot Implementation Downtown LA | 2 | W2 | Done |  | https://technijian.com/copilot-implementation/ | https://technijian.com/entertainment-media/ | https://technijian.com/entertainment-media/
3 | Gemini Integration Torrance | 2 | W2 | Done |  | https://technijian.com/gemini-integration/ | https://technijian.com/professional-services/ | https://technijian.com/professional-services/
4 | Enterprise AI Strategy Culver City | 2 | W2 | Done |  | https://technijian.com/enterprise-ai-strategy/ | https://technijian.com/technology-software-development/ | https://technijian.com/technology-software-development/
5 | AI Security Consulting Santa Monica | 2 | W2 | Done |  | https://technijian.com/ai-security-consulting/ | https://technijian.com/managed-it-services-foothill-ranch/ | https://technijian.com/managed-it-services-foothill-ranch/
6 | AI Automation Services Costa Mesa | 2 | W3 | Done |  | https://technijian.com/ai-automation-services/ | https://technijian.com/managed-it-services-newport-coast/ | https://technijian.com/managed-it-services-newport-coast/
7 | Power BI AI Integration Anaheim | 2 | W3 | Done |  | https://technijian.com/power-bi-ai/
8 | AI Training Long Beach | 2 | W3 | Done |  | https://technijian.com/ai-training-long-beach/
9 | AI Penetration Testing Newport Beach | 2 | W3 | Done |  | https://technijian.com/ai-penetration-testing/
10 | AI Data Analytics Tustin | 2 | W3 | Done |  | https://technijian.com/ai-data-analytics-tustin/
11 | Digital Transformation Santa Ana | 2 | W4 | Done |  | https://technijian.com/digital-transformation/
12 | AI Process Automation Irvine | 2 | W4 | Done |  | https://technijian.com/ai-process-automation-irvine/
13 | AI Consulting Downtown LA | 2 | W4 | Done |  | https://technijian.com/ai-consulting-downtown-la/
14 | Copilot Implementation Torrance | 2 | W4 | Done |  | https://technijian.com/copilot-implementation-torrance/
15 | Gemini Integration Culver City | 2 | W4 | Done |  | https://technijian.com/gemini-integration-culver-city/
16 | Enterprise AI Strategy Santa Monica | 2 | W5 | Done |  | https://technijian.com/enterprise-ai-strategy-santa-monica/
17 | AI Security Consulting Costa Mesa | 2 | W5 | Done |  | https://technijian.com/ai-security-consulting-costa-mesa/
18 | AI Automation Services Anaheim | 2 | W5 | Done |  | https://technijian.com/ai-automation-services-anaheim/
19 | Power BI AI Integration Long Beach | 2 | W5 | Done |  | https://technijian.com/power-bi-ai-integration/
20 | AI Training Newport Beach | 2 | W5 | Done |  | https://technijian.com/ai-training-newport-beach/
21 | AI Penetration Testing Tustin | 2 | W6 | Done |  | https://technijian.com/ai-penetration-testing-tustin/
22 | AI Data Analytics Santa Ana | 2 | W6 | Done |  | https://technijian.com/ai-data-analytics-santa-ana/
23 | Digital Transformation Irvine | 2 | W6 | Done |  | https://technijian.com/digital-transformation-irvine/
24 | AI Process Automation Downtown LA | 2 | W6 | Done |  | https://technijian.com/ai-process-automation-downtown-la/
25 | AI Consulting Torrance | 2 | W6 | Done |  | https://technijian.com/ai-consulting-services-in-torrance/
26 | Copilot Implementation Culver City | 2 | W7 | Done |  | https://technijian.com/microsoft-copilot-implementation-culver-city/
27 | Gemini Integration Santa Monica | 2 | W7 | Done |  | https://technijian.com/google-gemini-integration-santa-monica/
28 | Enterprise AI Strategy Costa Mesa | 2 | W7 | Done |  | https://technijian.com/enterprise-ai-strategy-costa-mesa/
29 | AI Security Consulting Anaheim | 2 | W7 | Done |  | https://technijian.com/ai-security-consulting-anaheim/
30 | AI Automation Services Long Beach | 2 | W7 | Done |  | https://technijian.com/ai-automation-long-beach/
31 | Power BI AI Integration Newport Beach | 2 | W8 | Done |  | https://technijian.com/power-bi-ai-integration-newport-beach/
32 | AI Training Tustin | 2 | W8 | Done |  | https://technijian.com/ai-training-tustin-businesses/
33 | AI Penetration Testing Santa Ana | 2 | W8 | Done |  | https://technijian.com/ai-penetration-testing-services/
34 | AI Data Analytics Irvine | 2 | W8 | Done |  | https://technijian.com/ai-data-analytics/
35 | Digital Transformation Downtown LA | 2 | W8 | Done |  | https://technijian.com/digital-transformation/
36 | AI Process Automation Torrance | 2 | W9 | Done |  | https://technijian.com/ai-process-automation-torrance/
37 | AI Consulting Culver City | 2 | W9 | Done |  | https://technijian.com/ai-consulting-culver-city/
38 | Copilot Implementation Santa Monica | 2 | W9 | Done |  | https://technijian.com/copilot-implementation-for-santa-monica/
40 | Enterprise AI Strategy Anaheim | 2 | W9 | Done |  | https://technijian.com/enterprise-ai-strategy-anaheim/
41 | AI Security Consulting Long Beach | 2 | W10 | Done |  | https://technijian.com/ai-security-consulting-long-beach/
42 | AI Automation Services Newport Beach | 2 | W10 | Done |  | https://technijian.com/ai-automation-services-newport-beach/
43 | Power BI AI Integration Tustin | 2 | W10 | Done |  | https://technijian.com/power-bi-ai-integration-tustin/
44 | AI Training Santa Ana | 2 | W10 | Done |  | https://technijian.com/ai-training-santa-ana/
45 | AI Penetration Testing Irvine | 2 | W10 | Done |  | https://technijian.com/ai-penetration-testing-irvine/
46 | AI Data Analytics Downtown LA | 2 | W11 | Done |  | https://technijian.com/ai-data-analytics-downtown-la/
47 | Digital Transformation Torrance | 2 | W11 | Done |  | https://technijian.com/digital-transformation-torrance/
48 | AI Process Automation Culver City | 2 | W11 | Done |  | https://technijian.com/ai-process-automation-culver-city/
49 | AI Consulting Santa Monica | 2 | W11 | Done |  | https://technijian.com/ai-consulting-in-santa-monica/
50 | Copilot Implementation Costa Mesa | 2 | W11 | Done |  | https://technijian.com/copilot-implementation-in-costa-mesa/
51 | Gemini Integration Anaheim | 2 | W12 | Done |  | https://technijian.com/gemini-integration-in-anaheim/
52 | Enterprise AI Strategy Long Beach | 2 | W12 | Done |  | https://technijian.com/enterprise-ai-strategy-in-long-beach/
53 | AI Security Consulting Newport Beach | 2 | W12 | Done |  | https://technijian.com/ai-security-consulting-newport-beach/
54 | AI Automation Services Tustin | 2 | W12 | Done |  | https://technijian.com/ai-automation-services-in-tustin/
55 | Power BI AI Integration Santa Ana | 2 | W12 | Done |  | https://technijian.com/power-bi-ai-integration-santa-ana/
56 | AI Training Irvine | 2 | W13 | Working
57 | AI Penetration Testing Downtown LA | 2 | W13 | Not Started
58 | AI Data Analytics Torrance | 2 | W13 | Not Started
59 | Digital Transformation Culver City | 2 | W13 | Not Started
60 | AI Process Automation Santa Monica | 2 | W13 | Not Started
61 | AI Consulting Costa Mesa | 2 | W14 | Not Started
62 | Copilot Implementation Anaheim | 2 | W14 | Not Started
63 | Gemini Integration Long Beach | 2 | W14 | Not Started
64 | Enterprise AI Strategy Newport Beach | 2 | W14 | Not Started
65 | AI Security Consulting Tustin | 2 | W14 | Not Started
66 | AI Automation Services Santa Ana | 2 | W15 | Not Started
67 | Power BI AI Integration Irvine | 2 | W15 | Not Started
68 | AI Training Downtown LA | 2 | W15 | Not Started
69 | AI Penetration Testing Torrance | 2 | W15 | Not Started
70 | AI Data Analytics Culver City | 2 | W15 | Not Started
71 | Digital Transformation Santa Monica | 2 | W16 | Not Started
72 | AI Process Automation Costa Mesa | 2 | W16 | Not Started
73 | AI Consulting Anaheim | 2 | W16 | Not Started
74 | Copilot Implementation Long Beach | 2 | W16 | Not Started
75 | Gemini Integration Newport Beach | 2 | W16 | Not Started
76 | Enterprise AI Strategy Tustin | 2 | W17 | Not Started
77 | AI Security Consulting Santa Ana | 2 | W17 | Not Started
78 | AI Automation Services Irvine | 2 | W17 | Not Started
79 | Power BI AI Integration Downtown LA | 2 | W17 | Not Started
80 | AI Training Torrance | 2 | W17 | Not Started
81 | AI Penetration Testing Culver City | 2 | W18 | Not Started
82 | AI Data Analytics Santa Monica | 2 | W18 | Not Started
83 | Digital Transformation Costa Mesa | 2 | W18 | Not Started
84 | AI Process Automation Anaheim | 2 | W18 | Not Started
85 | AI Consulting Long Beach | 2 | W18 | Not Started
86 | Copilot Implementation Newport Beach | 2 | W19 | Not Started
87 | Gemini Integration Tustin | 2 | W19 | Not Started
88 | Enterprise AI Strategy Santa Ana | 2 | W19 | Not Started
89 | AI Security Consulting Irvine | 2 | W19 | Not Started
90 | AI Automation Services Downtown LA | 2 | W19 | Not Started
91 | Power BI AI Integration Torrance | 2 | W20 | Not Started
92 | AI Training Culver City | 2 | W20 | Not Started
93 | AI Penetration Testing Santa Monica | 2 | W20 | Not Started
94 | AI Data Analytics Costa Mesa | 2 | W20 | Not Started
95 | Digital Transformation Anaheim | 2 | W20 | Not Started
96 | AI Process Automation Long Beach | 2 | W21 | Not Started
97 | AI Consulting Newport Beach | 2 | W21 | Not Started
98 | Copilot Implementation Tustin | 2 | W21 | Not Started
99 | Gemini Integration Santa Ana | 2 | W21 | Not Started
100 | Enterprise AI Strategy Irvine | 2 | W21 | Not Started
101 | AI Security Consulting Downtown LA | 2 | W22 | Not Started
102 | AI Automation Services Torrance | 2 | W22 | Not Started
103 | Power BI AI Integration Culver City | 2 | W22 | Not Started
104 | AI Training Santa Monica | 2 | W22 | Not Started
105 | AI Penetration Testing Costa Mesa | 2 | W22 | Not Started
106 | AI Data Analytics Anaheim | 2 | W23 | Not Started
107 | Digital Transformation Long Beach | 2 | W23 | Not Started
108 | AI Process Automation Newport Beach | 2 | W23 | Not Started
109 | AI Consulting Tustin | 2 | W23 | Not Started
110 | Copilot Implementation Santa Ana | 2 | W23 | Not Started
111 | Gemini Integration Irvine | 2 | W24 | Not Started
112 | Enterprise AI Strategy Downtown LA | 2 | W24 | Not Started
113 | AI Security Consulting Torrance | 2 | W24 | Not Started
114 | AI Automation Services Culver City | 2 | W24 | Not Started
115 | Power BI AI Integration Santa Monica | 2 | W24 | Not Started
116 | AI Training Costa Mesa | 2 | W25 | Not Started
117 | AI Penetration Testing Anaheim | 2 | W25 | Not Started
118 | AI Data Analytics Long Beach | 2 | W25 | Not Started
119 | Digital Transformation Newport Beach | 2 | W25 | Not Started
120 | AI Process Automation Tustin | 2 | W25 | Not Started
121 | AI Consulting Santa Ana | 2 | W26 | Not Started
122 | Copilot Implementation Irvine | 2 | W26 | Not Started
123 | Gemini Integration Downtown LA | 2 | W26 | Not Started
124 | Enterprise AI Strategy Torrance | 2 | W26 | Not Started
125 | AI Security Consulting Culver City | 2 | W26 | Not Started
126 | AI Automation Services Santa Monica | 2 | W27 | Not Started
127 | Power BI AI Integration Costa Mesa | 2 | W27 | Not Started
128 | AI Training Anaheim | 2 | W27 | Not Started
129 | AI Penetration Testing Long Beach | 2 | W27 | Not Started
130 | AI Data Analytics Newport Beach | 2 | W27 | Not Started
# | EXTRA | Type | Due | Status | Actual Hrs | Notes
1 | AI Readiness Checklist | Lead Magnet PDF | W12 | Not Started

## Shift Schedules
SHIFT TIME BLOCKS — WORK TASKS ONLY
MORNING — Saroj & Vaishali (10:30 AM – 7:30 PM)
Time Block | Task | Blog Day | Non-Blog Day | Friday
10:30-11:00 | GSC + Login + Priorities | 0.5 hrs | 0.5 hrs | 0.5 hrs
11:00-1:00 | MAIN: Blog / Page / News | 2.5 (blog) | 2.0 (page) | 1.5 (news)
1:00-3:00 | Page (blog day) / SEO Plan | 2.0 (page) | 2.0 (SEO plan) | 2.0 (page)
3:00-4:30 | 180-Day SEO Plan Task | 1.5 | — | 1.5
4:30-6:00 | Internal Links + Backlinks | 1.0 | 2.0 | 1.5
6:00-7:00 | GBP + Social + Competitor + Refresh | 0.5 | 1.5 | 1.0
7:00-7:30 | Content Refresh / Wrap-up | — | — | —
| TOTAL | 8.0 hrs | 8.0 hrs | 8.0 hrs
EVENING — Puneet & Mohit (1:00 PM – 11:00 PM)
Time Block | Task | Blog Day | Non-Blog Day | Friday
1:00-1:30 | GSC + Login + Priorities | 0.5 hrs | 0.5 hrs | 0.5 hrs
1:30-4:00 | MAIN: Blog / Page / News | 2.5 (blog) | 2.0 (page) | 1.5 (news)
4:00-6:00 | Page (blog day) / SEO Plan | 2.0 (page) | 2.0 (SEO plan) | 2.0 (page)
6:00-7:30 | 180-Day SEO Plan Task | 1.5 | — | 1.5
7:30-8:30 | Internal Links + Backlinks | 1.0 | 2.0 | 1.5
8:30-10:00 | GBP + Social + Competitor + Refresh | 0.5 | 1.5 | 1.0
10:00-11:00 | Content Refresh / Wrap-up | — | 2.0 | —
| TOTAL | 8.0 hrs | 8.0 hrs | 8.0 hrs